## MP_new
* Construction Phase 7.1 = 7A, 7.2 = 7B
Scenario | BWF | MWF | Plover | MSB | Meadow | Water Used (a-f/y) | Hard Transition Area (sq mi) | Soft Transition Area (sq mi) | Groundwater Pumped (a-f/y) |  | ** Step 0 DCM assignments from "Anticipated 2017-2018 Dust Season Operation Designations" (letter to P. Kiddoo, 09/29/17)
Base | 1086.8953 | 6087.8928 | 4593.626 | 11705.63 | 1318.7206 | 73351 | - | - | 0 |  | User input (analysis script must be run to update calculations)
0 | 2283.0754 | 5955.4412 | 4591.8692 | 10609.9089 | 1827.8776 | 64619.0552 | - | - | 0 |  | User input (workbook will update automatically)
1 | 2259.1482 | 5712.0836 | 4674.6429 | 10535.0867 | 1767.1608 | 59692.4344 | 2.9686 | 0.38254 | 5000 |  | Analysis script output
2 | 2071.4634 | 5526.1246 | 4508.7256 | 10475.9252 | 1349.1691 | 56608.7507 | 2.997 | 1.2844 | 9000 |  | Workbook formula calculation
3 | 1992.8514 | 5519.5187 | 4673.2444 | 10537.909 | 1187.7036 | 53633.0442 | 2.9412 | 2.1477 | 9000
4 | 1992.8514 | 5652.5435 | 4478.945 | 10545.5239 | 1187.3054 | 52352.4746 | 2.7524 | 0.99582 | 9000
5 | 1992.8514 | 5510.5642 | 4302.1312 | 10542.7878 | 1186.8663 | 51375.1937 | 2.4664 | 1.3354 | 9000
Scenario | BWF | MWF | Plover | MSB | Meadow | Water | Water Savings in Step (a-f/y) w/o GW | Total Water Savings (a-f/y) w/o GW | Water Saved in Step (a-f/y) with GW | Total Water Saved (a-f/y) with GW
Base | 100% | 100% | 100% | 100% | 100% | 100% | 0 | 0 | 0 | 0
0 | 210.1% | 97.82% | 99.96% | 90.64% | 138.6% | 88.1% | 8731.9448 | 0 | 8731.9448 | 0
1 | 207.9% | 93.83% | 101.8% | 90% | 134% | 81.38% | 4926.6207 | 4926.6207 | 9926.6207 | 9926.6207
2 | 190.6% | 90.77% | 98.15% | 89.49% | 102.3% | 77.18% | 3083.6838 | 8010.3045 | 12083.6838 | 17010.3045
3 | 183.4% | 90.66% | 101.7% | 90.02% | 90.06% | 73.12% | 2975.7064 | 10986.0109 | 11975.7064 | 19986.0109
4 | 183.4% | 92.85% | 97.5% | 90.09% | 90.03% | 71.37% | 1280.5697 | 12266.5806 | 10280.5697 | 21266.5806
5 | 183.4% | 90.52% | 93.65% | 90.07% | 90% | 70.04% | 977.2808 | 13243.8614 | 9977.2808 | 22243.8614
DCA | Area (ac) | Area (sq mi) | Construction Phase* | Base | DWM | Step 0** | MP | Step | Transition Type
Channel Area North | 133.675 | 0.20887 | 7 | ENV | ENV | ENV | ENV | 0 | none
Channel Area South | 197.954 | 0.3093 | 7 | ENV | ENV | ENV | ENV | 0 | none
Corridor 1 | 88.391 | 0.13811 | 5 | Gravel | Gravel | Gravel | Gravel | 0 | none
DuckPond-L2 | 10.31 | 0.016109 | 10 | None | None | Gravel | Gravel | 0 | none
Phase 8_a | 1252.054 | 1.9563 | 8 | Gravel | Gravel | Gravel | Gravel | 0 | none
Phase 8_b | 34.538 | 0.053966 | 8 | Gravel | Gravel | Gravel | Gravel | 0 | none
T10-1_a | 40.901 | 0.063908 | 7 | SFP | DWM_Dec | DWM_Dec | DWM_Jan | 4 | hard
T10-1_b | 243.085 | 0.37982 | 7 | SFP | DWM_Dec | DWM_Dec | DWM_Dec | 0 | none
T10-1_c | 166.435 | 0.26005 | 7 | SFP | DWM_Dec | DWM_Dec | DWM_Dec | 0 | none
T10-1a | 41.264 | 0.064475 | 9 | None | DWM_Jan | DWM_Dec | MSB | 4 | hard
T10-2N | 201.977 | 0.31559 | 7 | SFP | DWM_Jan | DWM_Jan | MSB | 5 | hard
T10-2S | 701.226 | 1.0957 | 7 | SFL | DWM_Jan | DWM_Jan | MSB | 5 | hard
T10-3a | 316.485 | 0.49451 | 10 | None | None | Gravel | Gravel | 0 | none
T10-3E | 178.597 | 0.27906 | 7 | SFP | DWM_Jan | DWM_Jan | MSB | 4 | hard
T10-3W | 103.259 | 0.16134 | 7 | Brine | Brine (DWM) | Brine (DWM) | Brine | 0 | hard
T11 | 432.983 | 0.67654 | 4 | SFP | SFP | Brine | Brine | 0 | none
T1-1 | 150.962 | 0.23588 | 5 | SFP | DWM_Dec | DWM_Dec | MWF and MSB | 5 | hard
T12-1 | 216.742 | 0.33866 | 7.1 | None | None | Tillage | Tillage | 0 | none
T13-1_a | 380.463 | 0.59447 | 7 | SFL | SFL (DWM) | SFL (DWM) | Brine | 2 | hard
T13-1_b | 368.125 | 0.5752 | 7 | SFL | SFL (DWM) | SFL (DWM) | Brine | 3 | hard
T13-1 Addition_a | 4.856 | 0.0075875 | 7 | SFL | DWM_Jan | SFL | MSB | 1 | hard
T13-1 Addition_b | 4.969 | 0.0077641 | 7 | SFL | DWM_Jan | SFL | MSB | 1 | hard
T13-1 Addition_c | 9.94 | 0.015531 | 7 | SFL | DWM_Jan | SFL | MSB | 1 | hard
T13-1 Addition_d | 50.363 | 0.078692 | 5 | SFL | DWM_Jan | SFL | MSB | 1 | hard
T13-1 Addition_e | 9.972 | 0.015581 | 5 | SFL | DWM_Jan | SFL | MSB | 1 | hard
T13-2 | 390.278 | 0.60981 | 5 | SFP | SFP | SFP | Tillage | 3 | soft
T13-3_a | 231.407 | 0.36157 | 5 | SFP | SFP | SFP | Tillage | 3 | soft
T13-3_b | 205.838 | 0.32162 | 5 | SFP | SFP | SFP | Tillage | 3 | soft
T15 | 76.467 | 0.11948 | 9 | None | None | Gravel | Gravel | 0 | none
T16_a | 56.064 | 0.0876 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_b | 309.049 | 0.48289 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_c | 151.36 | 0.2365 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_d | 159.613 | 0.2494 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_e | 110.831 | 0.17317 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_f | 159.525 | 0.24926 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_g | 5.221 | 0.0081578 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_h | 36.977 | 0.057777 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_i | 78.471 | 0.12261 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T16_j | 19.969 | 0.031202 | 7 | SFP | DWM_Jan | MWF and MSB | MWF and MSB | 0 | none
T17-1_a | 368 | 0.575 | 7 | SFP | DWM_Plovers | DWM_Plovers | DWM_Jan | 4 | hard
T17-1_b | 155 | 0.24219 | 7 | SFP | DWM_Plovers | DWM_Plovers |  |  | hard
T17-2_a | 432 | 0.675 | 7 | SFP | DWM_Plovers | DWM_Plovers | DWM_Jan | 5 | hard
T17-2_b | 174 | 0.27188 | 7 | SFP | DWM_Plovers | DWM_Plovers |  |  | hard
T18-0 | 343.097 | 0.53609 | 7 | SFP | DWM_Jan | DWM_Jan | DWM_Jan | 0 | none
T18N | 547.026 | 0.85473 | 4 | SFP | SFP | SFP | Tillage | 3 | soft
T18N Addition | 21.404 | 0.033444 | 7 | SFP | SFP | SFP | Tillage | 1 | soft
T18S_a | 669.563 | 1.0462 | 4 | SFP | SFP | SFP | SFP | 0 | none
T18S_b | 421.589 | 0.65873 | 4 | SFP | SFP | SFP | Brine | 0 | hard
T18S_c | 69.152 | 0.10805 | 4 | SFP | SFP | SFP | Brine | 0 | hard
T1A-1 | 249.563 | 0.38994 | 7 | Sand Fences | Sand Fences | Sand Fences | Sand Fences | 0 | none
T1A-2_a | 446.283 | 0.69732 | 7 | SFL | SFL | T1A-2 Unique | BWF | 0 | hard
T1A-2_b | 28.525 | 0.04457 | 7.1 | SFL | SFL | T1A-2 Unique | BWF | 0 | hard
T1A-2_c | 1.201 | 0.0018766 | 7.1 | SFL | SFL | T1A-2 Unique | BWF | 0 | hard
T1A-2_d | 33.003 | 0.051567 | 7.1 | SFL | SFL | T1A-2 Unique | BWF | 0 | hard
T1A-2_e | 194.694 | 0.30421 | 7.1 | SFL | SFL | T1A-2 Unique | BWF | 0 | hard
T1A-3_a | 303.938 | 0.4749 | 7.1 | None | None | Gravel | Gravel | 0 | none
T1A-3_b | 162.589 | 0.25405 | 7.1 | None | None | Gravel | Gravel | 0 | none
T1A-3_c | 41.963 | 0.065567 | 7.2 | None | None | Gravel | Gravel | 0 | none
T1A-4 | 617.935 | 0.96552 | 7.1 | None | None | SFLS | SFLS | 0 | none
T20 | 139.093 | 0.21733 | 9 | None | None | Gravel | Gravel | 0 | none
T2-1 | 334.325 | 0.52238 | 5 | SFL | SFL | DWM_Oct | MWF | 4 | hard
T2-1 Addition | 184.201 | 0.28781 | 7 | SFL | SFL | SFL | SFL | 0 | none
T21-1 | 104.304 | 0.16298 | 10 | None | None | Gravel | Gravel | 0 | none
T21-2 | 55.835 | 0.087242 | 10 | None | None | Gravel | Gravel | 0 | none
T2-1b | 50.403 | 0.078755 | 9 | None | None | Veg 11 | Veg 11 | 0 | none
T2-1c | 101.733 | 0.15896 | 9 | None | None | Veg 11 | Veg 11 | 0 | none
T21E | 274.48 | 0.42888 | 7 | SFP | SFP | DWM_Oct | MSB | 4 | hard
T21W | 43.76 | 0.068375 | 7 | SFL | DWM_Jan | DWM_Jan | MSB | 1 | hard
T22 | 367.719 | 0.57456 | 9 | None | None | Gravel | Gravel | 0 | none
T2-2_a | 119.238 | 0.18631 | 5 | SFP | SFP | DWM_Oct | MSB | 4 | hard
T2-2_b | 14.401 | 0.022502 | 5 | SFP | SFP | Tillage | Tillage | 0 | none
T2-3 | 75.103 | 0.11735 | 5 | SFL | SFL | Tillage | Tillage | 0 | none
T23-5 | 194.471 | 0.30386 | 7 | SFP | SFP (DWM) | SFP (DWM) | MSB | 3 | hard
T23NE_a | 74.637 | 0.11662 | 1 | SFL | SFL | Brine | Brine | 0 | none
T23NE_b | 102.915 | 0.1608 | 1 | SFL | SFL | SFL | Tillage | 1 | soft
T23NE_c | 36.169 | 0.056514 | 1 | SFL | SFL | Brine | Brine | 0 | none
T23NE_d | 38.795 | 0.060617 | 1 | SFL | SFL | SFL | Tillage | 1 | soft
T23NW_a | 159.331 | 0.24895 | 1 | SFL | SFL | SFL | Tillage | 4 | soft
T23NW_b | 61.792 | 0.09655 | 1 | SFL | SFL | SFL | Tillage | 1 | soft
T23SE | 477.992 | 0.74686 | 1 | SFL | SFL | SFL | Tillage | 4 | soft
T23SW | 226.484 | 0.35388 | 1 | SFL | SFL | SFL | Tillage | 5 | soft
T24_a | 1024.275 | 1.6004 | 1 | SFL | SFL | SFL | SFL | 0 | none
T24_b | 80.443 | 0.12569 | 1 | SFL | SFL | SFL | Tillage | 5 | soft
T2-4_a | 92.735 | 0.1449 | 5 | SFL | SFL | Brine | Brine | 0 | none
T2-4_b | 57.237 | 0.089433 | 5 | SFL | SFL | Tillage | Tillage | 0 | none
T2-4_c | 31.075 | 0.048555 | 5 | SFL | SFL | Tillage | Tillage | 0 | none
T24 Addition | 42.511 | 0.066423 | 4 | SFL | SFL | Tillage | Tillage | 0 | none
T2-5 | 65.526 | 0.10238 | 5 | Brine | Brine | Brine | Brine | 0 | none
T25-3 | 161.258 | 0.25197 | 7 | SFL | DWM_Jan | DWM_Jan | MSB | 1 | hard
T25N | 258.503 | 0.40391 | 1 | SFL | SFL | SFL | SFL | 0 | none
T25S | 822.018 | 1.2844 | 1 | SFL | SFL (DWM) | SFL (DWM) | Tillage | 2 | soft
T26_a | 491.515 | 0.76799 | 1 | SFL | SFL (DWM) | SFL (DWM) | SFLS | 0 | hard
T26_b | 363.639 | 0.56819 | 1 | SFL | SFL (DWM) | SFL (DWM) | Gravel | 2 | hard
T27 Addition | 50.593 | 0.079052 | 5 | SFL | SFL | Brine | Brine | 0 | none
T27N | 550.137 | 0.85959 | 1 | SFL | SFL | SFL | SFL | 0 | none
T27S | 547.748 | 0.85586 | 1 | SFL | SFL | SFL | Tillage | 5 | soft
T28N_a | 106.684 | 0.16669 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_b | 19.772 | 0.030894 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_c | 23.013 | 0.035958 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_d | 62.124 | 0.097069 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_e | 18.916 | 0.029556 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_f | 11.4 | 0.017813 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_g | 192.545 | 0.30085 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_h | 13.319 | 0.020811 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28N_i | 7.54 | 0.011781 | 7.1 | SFL | SFL | T28N Unique | Meadow | 0 | hard
T28S_a | 174.503 | 0.27266 | 7.1 | SFL | SFL | T28S Unique | Meadow | 0 | hard
T28S_b | 38.743 | 0.060536 | 7.1 | SFL | SFL | T28S Unique | Meadow | 0 | hard
T28S_c | 19.064 | 0.029788 | 7.1 | SFL | SFL | T28S Unique | Meadow | 0 | hard
T28S_d | 69.334 | 0.10833 | 7.1 | SFL | SFL | T28S Unique | Meadow | 0 | hard
T29-1 | 220.758 | 0.34493 | 5 | SFP | SFP (DWM) | SFP (DWM) | Gravel | 1 | hard
T29-2_a | 363.166 | 0.56745 | 5 | SFP | SFP (DWM) | SFP (DWM) | Gravel | 1 | hard
T29-2_b | 118.499 | 0.18515 | 5 | SFP | SFP (DWM) | SFP (DWM) | SFLS | 0 | hard
T29-3 | 259.247 | 0.40507 | 5 | SFP | SFP | Brine | Brine | 0 | none
T29-4_a | 108.567 | 0.16964 | 5 | SFL | SFL | SFL | MSB | 1 | hard
T29-4_b | 55.083 | 0.086067 | 5 | SFL | SFL | Brine | Brine | 0 | none
T30-1_a | 226.955 | 0.35462 | 7.1 | SFL | SFL | T30-1 Unique | Breeding Waterfowl & Meadow | 0 | hard
T30-1_b | 39.997 | 0.062495 | 7.1 | SFL | SFL | T30-1 Unique | Breeding Waterfowl & Meadow | 0 | hard
T30-1_c | 422.64 | 0.66038 | 7.1 | SFL | SFL | T30-1 Unique | Breeding Waterfowl & Meadow | 0 | hard
T30-2 | 318.37 | 0.49745 | 5 | SFP | SFP (DWM) | SFP (DWM) | Gravel | 1 | hard
T30-3 | 173.619 | 0.27128 | 5 | SFP | SFP | SFP | Gravel | 4 | hard
T32-1_a | 74.541 | 0.11647 | 7.1 | None | None | T32-1 Unique | Meadow | 0 | hard
T32-1_b | 38.154 | 0.059616 | 7.2 | None | None | T32-1 Unique | Meadow | 0 | hard
T32-2 | 604.014 | 0.94377 | 9 | None | None | Gravel | Gravel | 0 | none
T35-1 | 67.614 | 0.10565 | 5 | SFP | SFP | Gravel | Gravel | 0 | none
T35-2 | 91.647 | 0.1432 | 5 | SFP | SFP | Gravel | Gravel | 0 | none
T35-3 | 31.122 | 0.048628 | 9 | None | None | Gravel | Gravel | 0 | none
T36-1E_a | 161.408 | 0.2522 | 5 | SFL | SFL | T36-1E Unique | Meadow | 0 | hard
T36-1E_b | 128.266 | 0.20042 | 7.1 | SFL | SFL | T36-1E Unique | Meadow | 0 | hard
T36-1W_a | 181.74 | 0.28397 | 5 | SFL | SFL | T36-1W Unique | Meadow | 0 | hard
T36-1W_b | 177.118 | 0.27675 | 7.1 | SFL | SFL | T36-1W Unique | Meadow | 0 | hard
T36-2E | 274.819 | 0.4294 | 5 | SFP | SFP (DWM) | SFP (DWM) | Gravel | 1 | hard
T36-2W_a | 248.619 | 0.38847 | 5 | SFP | SFP | SFP | MSB | 3 | hard
T36-2W_b | 143.232 | 0.2238 | 5 | SFP | SFP | Brine | Brine | 0 | none
T36-3 Addition | 22.895 | 0.035773 | 7 | Brine | Brine | Brine | Brine | 0 | none
T36-3E | 139.511 | 0.21799 | 5 | Brine | Brine | Brine | Brine | 0 | none
T36-3W | 78.439 | 0.12256 | 5 | Brine | Brine | Brine | Brine | 0 | none
T37-1 | 137.95 | 0.21555 | 7.2 | None | None | Gravel | Gravel | 0 | none
T37-1a | 116.148 | 0.18148 | 9 | None | None | Gravel | Gravel | 0 | none
T37-2_a | 177.725 | 0.2777 | 7.1 | None | None | DWM_Jan | MWF and MSB | 3 | hard
T37-2_b | 17.968 | 0.028075 | 7.1 | None | None | None | MSB | 2 | hard
T37-2_c | 73.62 | 0.11503 | 7.2 | None | None | Veg 11 | MSB | 3 | hard
T37-2_d | 100.786 | 0.15748 | 7.1 | None | None | DWM_Jan | MSB | 3 | hard
T37-2a_a | 91.721 | 0.14331 | 9 | None | None | DWM_Oct | MWF and MSB | 5 | hard
T37-2a_b | 0.609 | 0.00095156 | 9 | None | None | DWM_Oct | MWF and MSB | 5 | hard
T37-2b | 41.739 | 0.065217 | 9 | None | None | DWM_Jan | MSB | 1 | hard
T37-2c | 31.41 | 0.049078 | 9 | None | None | DWM_Jan | MSB | 2 | hard
T37-2d_a | 114.68 | 0.17919 | 9 | None | None | DWM_Jan | MSB | 3 | hard
T37-2d_b | 3.015 | 0.0047109 | 9 | None | None | Gravel | MSB | 3 | hard
T3NE_a | 108.995 | 0.1703 | 2 | SFL | SFL | Tillage | Tillage | 0 | none
T3NE_b | 40.85 | 0.063828 | 2 | SFL | SFL | Brine | Brine | 0 | none
T3SE | 320.198 | 0.50031 | 2 | SFL | SFL | Tillage | Tillage | 0 | none
T3SE Addition | 77.894 | 0.12171 | 5 | SFL | SFL | SFL | MSB | 1 | hard
T3SW | 388.346 | 0.60679 | 2 | SFL | SFL | Tillage | Tillage | 0 | none
T4-3 | 150.063 | 0.23447 | 1 | SFL | SFL | SFL | MWF and MSB | 4 | hard
T4-3 Addition | 87.82 | 0.13722 | 5 | SFL | SFL | SFL | SFLS | 0 | hard
T4-4 | 162.287 | 0.25357 | 1 | SFP | SFP | SFP | SFP | 0 | none
T4-5 | 67.558 | 0.10556 | 1 | SFP | SFP | SFP | MSB | 1 | hard
T5-1 | 83.932 | 0.13114 | 5 | SFL | SFL | SFL | SFL | 0 | none
T5-1 Addition | 20.143 | 0.031473 | 7 | Veg 08 | Veg 08 | SFL | DWM_Jan | 3 | hard
T5-2 | 19.917 | 0.03112 | 5 | SFL | SFL | SFL | Tillage | 1 | soft
T5-3 | 139.397 | 0.21781 | 1 | SFL | SFL (DWM) | DWM_Jan | MSB | 3 | hard
T5-3 Addition | 81.071 | 0.12667 | 7 | SFP | SFP (DWM) | DWM_Jan | MSB | 4 | hard
T5-3B | 40.166 | 0.062759 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 1 | hard
T5-3C | 19.809 | 0.030952 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 1 | hard
T5-4 | 43.616 | 0.06815 | 5 | SFP | SFP | SFL | SFL | 0 | none
T5-4B | 40.178 | 0.062778 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 1 | hard
T5-4C | 40.166 | 0.062759 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-4D | 40.167 | 0.062761 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-5A | 40.166 | 0.062759 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-5D | 40.169 | 0.062764 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T5-6A | 40.152 | 0.062738 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-6B | 40.169 | 0.062764 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-6C | 40.176 | 0.062775 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-6D | 40.172 | 0.062769 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-7A | 40.155 | 0.062742 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-7B | 40.17 | 0.062766 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T5-7D | 40.14 | 0.062719 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-4C | 40.161 | 0.062752 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-4D | 40.174 | 0.062772 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-5A | 40.168 | 0.062762 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-5B | 40.152 | 0.062738 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-5C | 40.169 | 0.062764 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-5D | 40.172 | 0.062769 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-6A | 40.156 | 0.062744 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-6B | 40.15 | 0.062734 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-6C | 40.169 | 0.062764 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-6D | 40.175 | 0.062773 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-7A | 40.159 | 0.062748 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-7B | 40.15 | 0.062734 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T6-7C | 40.147 | 0.06273 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T6-7D | 40.153 | 0.062739 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-4A | 40.185 | 0.062789 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-4C | 40.163 | 0.062755 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-4D | 40.181 | 0.062783 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-5A | 40.182 | 0.062784 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-5B | 40.164 | 0.062756 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 2 | hard
T7-5C | 40.166 | 0.062759 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-5D | 40.184 | 0.062787 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-6A | 40.167 | 0.062761 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-6B | 40.149 | 0.062733 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-6C | 40.163 | 0.062755 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-6D | 40.181 | 0.062783 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-7A | 40.167 | 0.062761 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-7B | 40.146 | 0.062728 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T7-7C | 40.129 | 0.062702 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T7-7D | 40.145 | 0.062727 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T8-3A | 40.149 | 0.062733 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 3 | hard
T8-3B | 39.852 | 0.062269 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-4A | 40.147 | 0.06273 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-4B | 40.152 | 0.062738 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-4C | 40.167 | 0.062761 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-4D | 40.571 | 0.063392 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-5A | 39.921 | 0.062377 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-5B | 40.161 | 0.062752 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-5C | 40.16 | 0.06275 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-5D | 40.184 | 0.062787 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-6A | 40.169 | 0.062764 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-6B | 40.146 | 0.062728 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8-6C | 41.739 | 0.065217 | 1 | Veg 08 | Veg 08 | Veg 08 | MSB | 1 | hard
T8-6D | 43.217 | 0.067527 | 1 | Veg 08 | Veg 08 | Veg 08 | Veg 08 | 0 | none
T8W | 125.15 | 0.19555 | 4 | Brine | Brine | Brine | Brine | 0 | none
T9 | 293.873 | 0.45918 | 4 | SFP | DWM_Dec | DWM_Dec | DWM_Dec | 0 | none

## 10 YEAR PROJECTION
User Input
Sheet Calculation
Cumulative Step Capital Reference Table - used in "Step" sheet calculations - automatically generated, do not alter
Master Project |  |  | Project Phase | COST PER YEAR (Fiscal Year Ending) | [19 empty] | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
|  | CE |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | Total |  |  | 1 | 1500000 | 3818762 | 22743906 | 105275816 | 44025336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Step 1 |  | 10 | Labor | 2020: 500000; 2021: 1000000; 2022: 1000000; 2023: 500000; 2024: 500000 | 3500000 |  |  | 2 | 1500000 | 3818762 | 22743906 | 106775816 | 47712988 | 41854256 | 75545556 | 40354256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated Construction Cost: | 151876200 | 37 | Planning | 2020: 1000000; 2021: 1000000; 2022: 1000000; 2023: 500000 | 3500000 |  |  | 3 | 1500000 | 3818762 | 22743906 | 106775816 | 47712988 | 41854256 | 77045556 | 44008420 | 40916592 | 73770692 | 39416592 | 0 | 0 | 0 | 0 | 0
Sq. Miles: | 3.3511 | 30 | Construction | 2022: 15187620; 2023: 98719530; 2024: 37969050 | 151876200 |  |  | 4 | 1500000 | 3818762 | 22743906 | 106775816 | 47712988 | 41854256 | 77045556 | 44008420 | 40916592 | 75270692 | 42769518 | 32481928 | 57805078 | 30981928 | 0 | 0
Comment: |  | 37 | Design | 2021: 1518762; 2022: 1518762; 2023: 1518762; 2024: 1518762 | 6075048 |  |  | 5 | 1500000 | 3818762 | 22743906 | 106775816 | 47712988 | 41854256 | 77045556 | 44008420 | 40916592 | 75270692 | 42769518 | 33981928 | 61015974 | 59487016 | 50277488 | 27005088
|  | 37 | Construction Management | 2022: 3037524; 2023: 3037524; 2024: 3037524 | 9112572
|  | 41 | Materials/ Misc | 2021: 300000; 2022: 1000000; 2023: 1000000; 2024: 1000000 | 3300000 |  |  | Cumulative MP-Owned O&M - used in "Step" sheet calculations - automatically generated, do not alter
Step 1 Subtotals |  |  |  | 1500000 | 3818762 | 22743906 | 105275816 | 44025336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177363820 |  |  |  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Year Step 1 MP O&M Added | [8 empty] | 1604773.9052 | [10 empty] | 1604773.9052 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 1604773.9052
Step 2 |  | 10 | Labor |  |  |  | 500000 | 1000000 | 1000000 | 500000 | 500000 | [8 empty] | 3500000 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 5009419.7708
Estimated Construction Cost: | 138765200 | 37 | Planning |  |  |  | 1000000 | 1000000 | 1000000 | 500000 | [9 empty] | 3500000 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 9818594.1959 | 9818594.1959 | 9818594.1959 | 9818594.1959 | 9818594.1959
Sq. Miles: | 4.2814 | 30 | Construction | [5 empty] | 34691300 | 69382600 | 34691300 | [8 empty] | 138765200 |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 9818594.1959 | 9818594.1959 | 9818594.1959 | 12329634.0364 | 12329634.0364
Comment: |  | 37 | Design |  |  |  |  | 1387652 | 1387652 | 1387652 | 1387652 | [8 empty] | 5550608 |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 1604773.9052 | 1604773.9052 | 1604773.9052 | 5009419.7708 | 5009419.7708 | 5009419.7708 | 9818594.1959 | 9818594.1959 | 9818594.1959 | 12329634.0364 | 15271572.2754
|  | 37 | Construction Management | [5 empty] | 2775304 | 2775304 | 2775304 | [8 empty] | 8325912
|  | 41 | Materials |  |  |  |  | 300000 | 1000000 | 1000000 | 1000000 | [8 empty] | 3300000
Step 2 Subtotals |  |  |  | 0 | 0 | 0 | 1500000 | 3687652 | 41854256 | 75545556 | 40354256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162941720
Year Step 2 MP O&M Added | [11 empty] | 3404645.8656 | [7 empty] | 3404645.8656
Step 3 |  | 10 | Labor | [6 empty] | 500000 | 1000000 | 1000000 | 500000 | 500000 | [5 empty] | 3500000
Estimated Construction Cost: | 135416400 | 37 | Planning | [6 empty] | 1000000 | 1000000 | 1000000 | 500000 | [6 empty] | 3500000
Sq. Miles: | 5.0889 | 30 | Construction | [8 empty] | 33854100 | 67708200 | 33854100 | [5 empty] | 135416400
Comment: |  | 37 | Design | [7 empty] | 1354164 | 1354164 | 1354164 | 1354164 | [5 empty] | 5416656
|  | 37 | Construction Management | [8 empty] | 2708328 | 2708328 | 2708328 | [5 empty] | 8124984
|  | 41 | Materials | [7 empty] | 300000 | 1000000 | 1000000 | 1000000 | [5 empty] | 3300000
Step 3 Subtotals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 3654164 | 40916592 | 73770692 | 39416592 | 0 | 0 | 0 | 0 | 0 | 159258040
Year Step 3 MP O&M Added | [14 empty] | 4809174.4251 |  |  |  |  | 4809174.4251
Step 4 |  | 10 | Labor | [9 empty] | 500000 | 1000000 | 1000000 | 500000 | 500000 |  |  | 3500000
Estimated Construction Cost: | 105292600 | 37 | Planning | [9 empty] | 1000000 | 1000000 | 1000000 | 500000 |  |  |  | 3500000
Sq. Miles: | 3.7483 | 30 | Construction | [11 empty] | 26323150 | 52646300 | 26323150 |  |  | 105292600
Comment: |  | 37 | Design | [10 empty] | 1052926 | 1052926 | 1052926 | 1052926 |  |  | 4211704
|  | 37 | Construction Management | [11 empty] | 2105852 | 2105852 | 2105852 |  |  | 6317556
|  | 41 | Materials | [10 empty] | 300000 | 1000000 | 1000000 | 1000000 |  |  | 3300000
Step 4 Subtotals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 3352926 | 32481928 | 57805078 | 30981928 | 0 | 0 | 126121860
Year Step 4 MP O&M Added | [17 empty] | 2511039.8404 |  | 2511039.8404
Step 5 |  | 10 | Labor | [11 empty] | 500000 | 1000000 | 1000000 | 500000 | 500000 | 3500000
Estimated Construction Cost: | 91089600 | 37 | Planning | [11 empty] | 1000000 | 1000000 | 1000000 | 500000 |  | 3500000
Sq. Miles: | 3.8018 | 30 | Construction | [13 empty] | 22772400 | 45544800 | 22772400 | 91089600
Comment: |  | 37 | Design | [12 empty] | 910896 | 910896 | 910896 | 910896 | 3643584
|  | 37 | Construction Management | [13 empty] | 1821792 | 1821792 | 1821792 | 5465376
|  | 41 | Materials | [12 empty] | 300000 | 1000000 | 1000000 | 1000000 | 3300000
Step 5 Subtotals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 3210896 | 28505088 | 50277488 | 27005088 | 110498560
Year Step 5 MP O&M Added | [18 empty] | 2941938.2391 | 2941938.2391
CAPITAL SUBTOTAL BY FISCAL YEAR |  |  |  | 1500000 | 3818762 | 22743906 | 106775816 | 47712988 | 41854256 | 77045556 | 44008420 | 40916592 | 75270692 | 42769518 | 33981928 | 61015974 | 59487016 | 50277488 | 27005088 | 736184000
Cumulative Capital Cost Total |  |  |  | 1500000 | 5318762 | 28062668 | 134838484 | 182551472 | 224405728 | 301451284 | 345459704 | 386376296 | 461646988 | 504416506 | 538398434 | 599414408 | 658901424 | 709178912 | 736184000
|  | CE Code | 10 | 500000 | 1000000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1500000 | 1500000 | 1500000 | 500000 | 500000
|  |  | 37 | 1000000 | 2518762 | 5556286 | 6056286 | 6943938 | 5162956 | 5662956 | 6517120 | 5062492 | 5562492 | 6115418 | 5158778 | 5569674 | 6891466 | 3232688 | 2732688
|  |  | 30 | 0 | 0 | 15187620 | 98719530 | 37969050 | 34691300 | 69382600 | 34691300 | 33854100 | 67708200 | 33854100 | 26323150 | 52646300 | 49095550 | 45544800 | 22772400
|  |  | 41 | 0 | 300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1300000 | 2000000 | 1000000 | 1000000
OWENS LAKE EFFECIENCY MEASURES
ADDITIONS AND BETTERMENTS |  | 10 | Labor | [18 empty] | 0
|  | 30 | Construction |  |  |  | 5300000 | 9666000 | 9864000 | 10062000 | 5695000 | 9666000 | [9 empty] | 50253000
|  | 37 | Professional Services
Comment: |  | 41 | Materials | [18 empty] | 0
0
OLSAP |  | 10 | Labor |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | [6 empty] | 1500000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services | [18 empty] | 0
Comment: |  | 41 | Materials | [18 empty] | 0
0
Groundwater Well Drilling & Data Gathering |  | 10 | Labor |  |  | 243000 | 248000 | 253000 | 258000 | [12 empty] | 1002000
|  | 30 | Construction |  |  | 2640000 |  | 2255000 | 767000 | [12 empty] | 5662000
|  | 37 | Professional Services |  |  | 400000 | 400000 | 400000 | 400000 | [12 empty] | 1600000
Comment: |  | 41 | Materials |  |  |  | 200000 | 100000 | 100000 | [12 empty] | 400000
0
SFWCRFT |  | 10 | Labor |  |  | 200000 | 206000 | 212000 | 218000 | [12 empty] | 836000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services |  |  | 1100000 | 1100000 | 1100000 | 1100000 | [12 empty] | 4400000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Regulatory Fines |  | 10 | Labor |  |  | 207000 | 215000 | 222000 | 230000 | 238000 | 246000 | 255000 | 264000 | 273000 | 283000 | [6 empty] | 2433000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services |  |  | 780000 | 808000 | 836000 | 864000 | 896000 | 927000 | 959000 | 993000 | 1028000 | 1063000 | [6 empty] | 9154000
Comment: |  | 41 | Materials | [18 empty] | 0
|  | 99 | Other Direct - Fines |  |  | 6500000 | 6728000 | 6963000 | 7207000 | 7459000 | 7720000 | 7990000 | 8270000 | 8560000 | 8860000 | [6 empty] | 76257000
T13 |  | 10 | Labor |  |  | 160000 | 166000 | [14 empty] | 326000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services-Design |  |  | 130000 | 135000 | [14 empty] | 265000
Comment: |  | 41 | Materials |  |  | 871000 | [15 empty] | 871000
0
T5-1 Add |  | 10 | Labor |  |  | 280000 | 290000 | [14 empty] | 570000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services - Design |  |  | 130000 | 135000 | [14 empty] | 265000
Comment: |  | 41 | Materials |  |  | 850000 | [15 empty] | 850000
0
T17-2 |  | 10 | Labor |  |  | 160000 | 166000 | [14 empty] | 326000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services - Design |  |  | 130000 | 135000 | [14 empty] | 265000
Comment: |  | 41 | Materials |  |  | 533000 | [15 empty] | 533000
0
Subcommittees |  | 10 | Labor |  |  | 527000 | 545000 | 564000 | 584000 | 604000 | 626000 | 647000 | 670000 | 693000 | 718000 | [6 empty] | 6178000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Profession Srvcs-Science |  |  | 975000 | 1010000 | 1045000 | 1081000 | 1119000 | 1158000 | 1200000 | 1240000 | 1284000 | 1330000 | [6 empty] | 11442000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Soil Binder Study |  | 10 | Labor |  |  | 162000 | 118000 | 122000 | 126000 | 130000 | 135000 | [10 empty] | 793000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Srvcs - Science |  |  | 520000 | 539000 | 558000 | 577000 | 597000 | 618000 | [10 empty] | 3409000
Comment: |  | 41 | Materials |  |  | 208000 |  | 223000 |  | 239000 | [11 empty] | 670000
0
GIS and As-Builts |  | 10 | Labor |  |  | 2000000 | 1000000 | 1000000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | [6 empty] | 7500000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services |  |  | 2000000 | 1000000 | 1000000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | [6 empty] | 7500000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Science Contract |  | 10 | Labor |  |  | 329000 | 341000 | 353000 | 365000 | 378000 | 391000 | 405000 | 419000 | 431000 | 449000 | [6 empty] | 3861000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Srvcs - Science |  |  | 6500000 | 6728000 | 6963000 | 7207000 | 7459000 | 7720000 | 7991000 | 8270000 | 8560000 | 8860000 | [6 empty] | 76258000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Tribal Consultations and Monitoring |  | 10 | Labor | [18 empty] | 0
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services | [18 empty] | 0
Comment: |  | 41 | Materials | [18 empty] | 0
0
SCADA |  | 10 | Labor |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | [6 empty] | 5000000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services - Design |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | [6 empty] | 4000000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Brine Study |  | 10 | Labor |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | [6 empty] | 4000000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services - Design |  |  | 500000 | 500000 | 1000000 | 1000000 | 1000000 | 2000000 | 2000000 | 1000000 | 1000000 | 1000000 | [6 empty] | 11000000
Comment: |  | 41 | Materials | [18 empty] | 0
0
TWB2 Infrastructure |  | 10 | Labor |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | [6 empty] | 5000000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services - Design |  |  | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | [6 empty] | 3000000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Satellite Imagery |  | 10 | Labor |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | [6 empty] | 2000000
|  | 30 | Construction | [18 empty] | 0
|  | 37 | Professional Services |  |  | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | [6 empty] | 3000000
Comment: |  | 41 | Materials | [18 empty] | 0
0
Agency Payments |  | 10 | Labor | [18 empty] | 0
|  | 30 | Construction | [18 empty] | 0
Comment: | State Lands | 39 | Other Outside Services |  |  | 100000 | 200000 | 800000 | 800000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | [6 empty] | 2600000
| GBUAPCD | 39 | Other Outside Services |  |  | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 600000 | 600000 | 600000 | 600000 | [6 empty] | 38400000
|  | 41 | Materials | [18 empty] | 0
Gravel Contract |  | 10 | Labor |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | [6 empty] | 1500000
Total Cost: |  | 41 | Materials |  | 5000000 | 6000000 | 6000000 | [14 empty] | 17000000
Owens Lake Spare Parts (IFB 693) |  | 10 | Labor | [18 empty] | 0
Total Cost: |  | 41 | Materials |  | 5000000 | 6000000 | 6000000 | [14 empty] | 17000000
Irrigation System Materials (IFB 661) |  | 10 | Labor |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | [6 empty] | 2000000
Total Cost: |  | 41 | Materials | 5075324 | 32608 | 6400000 | 5000000 | 4000000 | [13 empty] | 20507932
Seeding Materials (IFB 761) |  | 10 | Labor |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | [6 empty] | 1500000
Total Cost: |  | 41 | Materials |  | 938000 | 1000000 | 1100000 | [14 empty] | 3038000
0
SUBTOTAL BY FISCAL YEAR |  |  |  | 5075324 | 10970608 | 57785000 | 55563000 | 48885000 | 42998000 | 40631000 | 37586000 | 36063000 | 26076000 | 26779000 | 27513000 | 0 | 0 | 0 | 0 |  | 0 | 415924932
[5 empty] | 10 | 6518000 | 5545000 | 4976000 | 4531000 | 4100000 | 4148000 | 4057000 | 4103000 | 4147000 | 4200000 | 0 | 0 | 0 | 0 |  | 0 |  | 46325000
[5 empty] | 37 | 14165000 | 13490000 | 13902000 | 13729000 | 12571000 | 13923000 | 13650000 | 13003000 | 13372000 | 13753000 | 0 | 0 | 0 | 0 |  | 0 |  | 135558000
[5 empty] | 30 | 2640000 | 5300000 | 11921000 | 10631000 | 10062000 | 5695000 | 9666000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 55915000
[5 empty] | 41 | 21862000 | 18300000 | 4323000 | 100000 | 239000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 44824000
[5 empty] | 39 | 6100000 | 6200000 | 6800000 | 6800000 | 6200000 | 6100000 | 700000 | 700000 | 700000 | 700000 | 0 | 0 | 0 | 0 |  | 0 |  | 41000000
[5 empty] | 99 | 6500000 | 6728000 | 6963000 | 7207000 | 7459000 | 7720000 | 7990000 | 8270000 | 8560000 | 8860000 | 0 | 0 | 0 | 0 |  | 0 |  | 76257000
399879000

## MP Analysis Input
User input (analysis script must be run to update calculations) |  |  | Forced DCA Changes* |  |  | * These are John D's final recommendations. Can be changed to test other forced changes…
|  |  | dca | force | step | dca | force | step
Analysis Variables |  |  | Channel Area North |  |  | Channel Area North
Hard Transition Limit | 3 | square miles (per step) | Channel Area South |  |  | Channel Area South
Soft Transition Limit | 3 | square miles (per step) | Corridor 1 |  |  | Corridor 1
|  |  | DuckPond-L2 |  |  | DuckPond-L2
Habitat Area Targets |  | decimal % of Base case area | Phase 8_a |  |  | Phase 8_a
BWF | 0.9 | bw | Phase 8_b |  |  | Phase 8_b
MWF | 0.9 | mw | T10-1_a |  |  | T10-1_a | MSB and SNPL | 1
Plover | 0.9 | pl | T10-1_b |  |  | T10-1_b | MSB and SNPL | 1
MSB | 0.9 | ms | T10-1_c |  |  | T10-1_c | MSB and SNPL | 1
Meadow | 0.9 | md | T10-1a |  |  | T10-1a | Brine | 5
|  |  | T10-2N |  |  | T10-2N | Tillage | 1
Soft Transition DCMS |  |  | T10-2S |  |  | T10-2S | Tillage | 1
Tillage |  |  | T10-3a |  |  | T10-3a
- |  |  | T10-3E |  |  | T10-3E | Brine | 3
- |  |  | T10-3W |  |  | T10-3W
- |  |  | T11 |  |  | T11 | Brine | 3
- |  |  | T1-1 |  |  | T1-1 | MSB and SNPL | 1
- |  |  | T12-1 |  |  | T12-1
- |  |  | T13-1_a |  |  | T13-1_a | SNPL_realistic | 4
|  |  | T13-1_b |  |  | T13-1_b | SNPL_realistic | 4
Waterless DCM Preference List |  | Notes: | T13-1 Addition_a |  |  | T13-1 Addition_a | SNPL_realistic | 2
Tillage | 1st choice | Lowest capital cost, highest maintenance cost. | T13-1 Addition_b |  |  | T13-1 Addition_b | SNPL_realistic | 2
Gravel | 2nd choice | Limited by soil capacity (not viable close to brine pool). | T13-1 Addition_c |  |  | T13-1 Addition_c | SNPL_realistic | 2
Brine | 3rd choice | More durable, long-term control measure. Supply limited. | T13-1 Addition_d |  |  | T13-1 Addition_d | SNPL_realistic | 2
Till-Brine | 4th choice | Dummy DCM, already accounted for as separate Tillage and Brine DCMs. Kept in this list for consistency with Step 0 assignments. | T13-1 Addition_e |  |  | T13-1 Addition_e | SNPL_realistic | 2
|  |  | T13-2 |  |  | T13-2 | MWF and MSB | 3
|  |  | T13-3_a |  |  | T13-3_a | TIllage | 5
|  |  | T13-3_b |  |  | T13-3_b | TIllage | 5
|  |  | T15 |  |  | T15
|  |  | T16_a |  |  | T16_a
|  |  | T16_b |  |  | T16_b
|  |  | T16_c |  |  | T16_c
|  |  | T16_d |  |  | T16_d
|  |  | T16_e |  |  | T16_e
|  |  | T16_f |  |  | T16_f
|  |  | T16_g |  |  | T16_g
|  |  | T16_h |  |  | T16_h
|  |  | T16_i |  |  | T16_i
|  |  | T16_j |  |  | T16_j
|  |  | T17-1 |  |  | T17-1 | MWF and SNPL | 4
|  |  | T17-2 |  |  | T17-2 | Tillage | 4
|  |  | T18-0 |  |  | T18-0 | Till-Brine | 5
|  |  | T18N |  |  | T18N | MWF and MSB | 3
|  |  | T18N Addition |  |  | T18N Addition | MWF and MSB | 2
|  |  | T18S_a |  |  | T18S_a | Till-Brine | 2
|  |  | T18S_b | Brine | 2 | T18S_b | Till-Brine | 2
|  |  | T18S_c |  |  | T18S_c | Till-Brine | 2
|  |  | T1A-1 |  |  | T1A-1
|  |  | T1A-2_a |  |  | T1A-2_a | MSB and SNPL_gravel | 2
|  |  | T1A-2_b |  |  | T1A-2_b | MSB and SNPL_gravel | 2
|  |  | T1A-2_c |  |  | T1A-2_c | MSB and SNPL_gravel | 2
|  |  | T1A-2_d |  |  | T1A-2_d | MSB and SNPL_gravel | 2
|  |  | T1A-2_e |  |  | T1A-2_e | MSB and SNPL_gravel | 2
|  |  | T1A-3_a |  |  | T1A-3_a
|  |  | T1A-3_b |  |  | T1A-3_b
|  |  | T1A-3_c |  |  | T1A-3_c
|  |  | T1A-4 |  |  | T1A-4 | Till-Brine | 3
|  |  | T20 |  |  | T20
|  |  | T2-1 |  |  | T2-1 | Till-Brine | 1
|  |  | T2-1 Addition |  |  | T2-1 Addition | MWF and MSB | 2
|  |  | T21-1 |  |  | T21-1
|  |  | T21-2 |  |  | T21-2
|  |  | T2-1b |  |  | T2-1b
|  |  | T2-1c |  |  | T2-1c
|  |  | T21E |  |  | T21E | MWF | 2
|  |  | T21W |  |  | T21W | Tillage | 2
|  |  | T22 |  |  | T22
|  |  | T2-2_a |  |  | T2-2_a | MSB | 2
|  |  | T2-2_b |  |  | T2-2_b | MSB | 2
|  |  | T2-3 |  |  | T2-3
|  |  | T23-5 |  |  | T23-5 | Brine | 2
|  |  | T23NE_a |  |  | T23NE_a | Till-Brine | 1
|  |  | T23NE_b |  |  | T23NE_b | Till-Brine | 1
|  |  | T23NE_c |  |  | T23NE_c | Till-Brine | 1
|  |  | T23NE_d |  |  | T23NE_d | Till-Brine | 1
|  |  | T23NW_a |  |  | T23NW_a | Till-Brine | 1
|  |  | T23NW_b |  |  | T23NW_b | Till-Brine | 1
|  |  | T23SE |  |  | T23SE | MSB and SNPL_gravel_MWF | 1
|  |  | T23SW |  |  | T23SW | Till-Brine | 1
|  |  | T24_a |  |  | T24_a | SNPL_with gravel | 3
|  |  | T24_b |  |  | T24_b | SNPL_with gravel | 3
|  |  | T2-4_a |  |  | T2-4_a
|  |  | T2-4_b |  |  | T2-4_b
|  |  | T2-4_c |  |  | T2-4_c
|  |  | T24 Addition |  |  | T24 Addition
|  |  | T2-5 |  |  | T2-5
|  |  | T25-3 |  |  | T25-3 | SNPL_realistic | 2
|  |  | T25N |  |  | T25N | MWF and MSB | 2
|  |  | T25S |  |  | T25S | MWF and MSB | 2
|  |  | T26_a |  |  | T26_a | MSB and SNPL | 5
|  |  | T26_b |  |  | T26_b | MSB and SNPL | 5
|  |  | T27 Addition |  |  | T27 Addition | Brine | 5
|  |  | T27N |  |  | T27N | MSB | 5
|  |  | T27S |  |  | T27S | SNPL_with gravel | 5
|  |  | T28N_a |  |  | T28N_a
|  |  | T28N_b |  |  | T28N_b
|  |  | T28N_c |  |  | T28N_c
|  |  | T28N_d |  |  | T28N_d
|  |  | T28N_e |  |  | T28N_e
|  |  | T28N_f |  |  | T28N_f
|  |  | T28N_g |  |  | T28N_g
|  |  | T28N_h |  |  | T28N_h
|  |  | T28N_i |  |  | T28N_i
|  |  | T28S_a |  |  | T28S_a
|  |  | T28S_b |  |  | T28S_b
|  |  | T28S_c |  |  | T28S_c
|  |  | T28S_d |  |  | T28S_d
|  |  | T29-1 |  |  | T29-1 | MWF and MSB | 1
|  |  | T29-2_a |  |  | T29-2_a | MWF and MSB | 1
|  |  | T29-2_b |  |  | T29-2_b | MWF and MSB | 1
|  |  | T29-3 |  |  | T29-3 | Brine | 4
|  |  | T29-4_a |  |  | T29-4_a
|  |  | T29-4_b |  |  | T29-4_b
|  |  | T30-1_a |  |  | T30-1_a
|  |  | T30-1_b |  |  | T30-1_b
|  |  | T30-1_c |  |  | T30-1_c
|  |  | T30-2 |  |  | T30-2 | MWF and MSB | 4
|  |  | T30-3 |  |  | T30-3 | MSB | 1
|  |  | T32-1_a |  |  | T32-1_a
|  |  | T32-1_b |  |  | T32-1_b
|  |  | T32-2 |  |  | T32-2
|  |  | T35-1 |  |  | T35-1
|  |  | T35-2 |  |  | T35-2
|  |  | T35-3 |  |  | T35-3
|  |  | T36-1E_a |  |  | T36-1E_a
|  |  | T36-1E_b |  |  | T36-1E_b
|  |  | T36-1W_a |  |  | T36-1W_a
|  |  | T36-1W_b |  |  | T36-1W_b
|  |  | T36-2E |  |  | T36-2E | MWF and MSB | 1
|  |  | T36-2W_a |  |  | T36-2W_a | Brine | 5
|  |  | T36-2W_b |  |  | T36-2W_b | Brine | 5
|  |  | T36-3 Addition |  |  | T36-3 Addition
|  |  | T36-3E |  |  | T36-3E
|  |  | T36-3W |  |  | T36-3W
|  |  | T37-1 |  |  | T37-1
|  |  | T37-1a |  |  | T37-1a
|  |  | T37-2_a |  |  | T37-2_a | Till-Brine | 4
|  |  | T37-2_b |  |  | T37-2_b | Till-Brine | 4
|  |  | T37-2_c |  |  | T37-2_c | Till-Brine | 4
|  |  | T37-2_d |  |  | T37-2_d | Till-Brine | 4
|  |  | T37-2a_a |  |  | T37-2a_a | SNPL_realistic | 2
|  |  | T37-2a_b |  |  | T37-2a_b | SNPL_realistic | 2
|  |  | T37-2b |  |  | T37-2b | Brine | 2
|  |  | T37-2c |  |  | T37-2c | Brine | 2
|  |  | T37-2d_a |  |  | T37-2d_a | SNPL_realistic | 2
|  |  | T37-2d_b |  |  | T37-2d_b | SNPL_realistic | 2
|  |  | T3NE_a |  |  | T3NE_a
|  |  | T3NE_b |  |  | T3NE_b
|  |  | T3SE |  |  | T3SE
|  |  | T3SE Addition |  |  | T3SE Addition | SNPL_realistic | 2
|  |  | T3SW |  |  | T3SW
|  |  | T4-3 |  |  | T4-3 | Till-Brine | 1
|  |  | T4-3 Addition |  |  | T4-3 Addition | Till-Brine | 1
|  |  | T4-4 |  |  | T4-4 | Till-Brine | 1
|  |  | T4-5 |  |  | T4-5 | Till-Brine | 1
|  |  | T5-1 |  |  | T5-1 | Till-Brine | 1
|  |  | T5-1 Addition |  |  | T5-1 Addition
|  |  | T5-2 |  |  | T5-2 | Till-Brine | 1
|  |  | T5-3 |  |  | T5-3 | Till-Brine | 1
|  |  | T5-3 Addition |  |  | T5-3 Addition | MWF and MSB | 1
|  |  | T5-3B |  |  | T5-3B
|  |  | T5-3C |  |  | T5-3C
|  |  | T5-4 |  |  | T5-4
|  |  | T5-4B |  |  | T5-4B
|  |  | T5-4C |  |  | T5-4C
|  |  | T5-4D |  |  | T5-4D
|  |  | T5-5A |  |  | T5-5A
|  |  | T5-5D |  |  | T5-5D
|  |  | T5-6A |  |  | T5-6A
|  |  | T5-6B |  |  | T5-6B
|  |  | T5-6C |  |  | T5-6C
|  |  | T5-6D |  |  | T5-6D
|  |  | T5-7A |  |  | T5-7A
|  |  | T5-7B |  |  | T5-7B
|  |  | T5-7D |  |  | T5-7D
|  |  | T6-4C |  |  | T6-4C
|  |  | T6-4D |  |  | T6-4D
|  |  | T6-5A |  |  | T6-5A
|  |  | T6-5B |  |  | T6-5B
|  |  | T6-5C |  |  | T6-5C
|  |  | T6-5D |  |  | T6-5D
|  |  | T6-6A |  |  | T6-6A
|  |  | T6-6B |  |  | T6-6B
|  |  | T6-6C |  |  | T6-6C
|  |  | T6-6D |  |  | T6-6D
|  |  | T6-7A |  |  | T6-7A
|  |  | T6-7B |  |  | T6-7B
|  |  | T6-7C |  |  | T6-7C
|  |  | T6-7D |  |  | T6-7D
|  |  | T7-4A |  |  | T7-4A
|  |  | T7-4C |  |  | T7-4C
|  |  | T7-4D |  |  | T7-4D
|  |  | T7-5A |  |  | T7-5A
|  |  | T7-5B |  |  | T7-5B
|  |  | T7-5C |  |  | T7-5C
|  |  | T7-5D |  |  | T7-5D
|  |  | T7-6A |  |  | T7-6A
|  |  | T7-6B |  |  | T7-6B
|  |  | T7-6C |  |  | T7-6C
|  |  | T7-6D |  |  | T7-6D
|  |  | T7-7A |  |  | T7-7A
|  |  | T7-7B |  |  | T7-7B
|  |  | T7-7C |  |  | T7-7C
|  |  | T7-7D |  |  | T7-7D
|  |  | T8-3A |  |  | T8-3A
|  |  | T8-3B |  |  | T8-3B
|  |  | T8-4A |  |  | T8-4A
|  |  | T8-4B |  |  | T8-4B
|  |  | T8-4C |  |  | T8-4C
|  |  | T8-4D |  |  | T8-4D
|  |  | T8-5A |  |  | T8-5A
|  |  | T8-5B |  |  | T8-5B
|  |  | T8-5C |  |  | T8-5C
|  |  | T8-5D |  |  | T8-5D
|  |  | T8-6A |  |  | T8-6A
|  |  | T8-6B |  |  | T8-6B
|  |  | T8-6C |  |  | T8-6C
|  |  | T8-6D |  |  | T8-6D
|  |  | T8W |  |  | T8W
|  |  | T9 |  |  | T9 | MWF and MSB | 2

## Constraints Input
Hardwired Contrainst (written into code): | [6 empty] | See DCM Master List to right ------> | [6 empty] | DCM List
Channel areas locked to ENV - not in TDCA | [11 empty] | DCM MASTER LIST |  | SFP
Nothing ENV except for Channel Areas | [11 empty] | SFP | Shallow Flood Pond | Veg 08
No additional sand fences allowed (besides existing T1A-1) | [11 empty] | Veg 08 | Managed Vegetation (2008) | Veg 11
Current areas defined as habitat should reamin unchanged. | [11 empty] | Veg 11 | Managed Vegetation (2011) | ENV
All DCAs under waterless DCM in Step 0 should be kept as-is. | [11 empty] | ENV | Enhanced Native Vegetation | SFL
All DCAs must be under dust control - no "None" DCMs allowed | [11 empty] | SFL | Shallow Flood Lateral | DWM_Jan
Meadow is hard to establish, don't add Meadow, only remove | [11 empty] | DWM_Jan | Dynamic Water Management, January start | DWM_Oct
Till-Brine is a bastard DCM, do not allow. | [11 empty] | DWM_Oct | Dynamic Water Management, October start | DWM_Dec
Phase 7a, 9/10 areas: only allow change in steps 4 or 5 | [11 empty] | DWM_Dec | Dynamic Water Management, December start | BWF
Phase 1 - 3 areas only allow change in steps 1 - 2 | [11 empty] | BWF | Breeding Waterfowl | MWF
Phase 4 - 5 areas only allow change in steps 1 - 3
dca | type | dcms | [7 empty] | Ops Comments | constrain | MWF | Migrating Waterfowl | SNPL_realistic
T10-1_a | not | Gravel | Tillage | Veg 08 | Veg 11 | SFL |  |  |  | T10-1SF | tillage,gravel,veg,S.F lats | SNPL_realistic | Snowy Plover | SNPL_with gravel
T10-1_b | not | Gravel | Tillage | Veg 08 | Veg 11 | SFL | [5 empty] | SNPL_with gravel | Snowy Plover w/ Gravel
T10-1_c | not | Gravel | Tillage | Veg 08 | Veg 11 | SFL | [5 empty] | MSB | Migrating Shorebirds
T10-1a | not | Veg 08 | Veg 11 | Gravel | SFL | Tillage | Brine |  |  | T10-1A | veg,gravel,S.F lats, tillage,brine | Meadow | Meadow | MSB
T10-2N | not | Veg 08 | Veg 11 | [6 empty] | T10-2 Pond Post DWM | veg | MWF and MSB | Migrating Waterfowl & Migrating Shorebirds | Meadow
T10-2S | not | Veg 08 | Veg 11 | [8 empty] | MSB and SNPL | Migrating Shorebirds & Snowy Plover | MWF and MSB
T10-3E | only | Brine | [7 empty] | T10-3 Pond (East) | only brine | MSB and SNPL_gravel | Migrating Shorebirds & Snowy Plover w/ Gravel | MSB and SNPL
T10-3W | only | Brine | [7 empty] | T10-3 Brine (West) | only brine | MSB and SNPL_gravel_MWF | Migrating Shorebirds & Snowy Plover w/ Gravel & Migrating Waterfowl | MSB and SNPL_gravel
T11 | not | Veg 08 | Veg 11 | [6 empty] | T11 | veg | MWF and SNPL | Migrating Waterfowl & Snowy Plover | MSB and SNPL_gravel_MWF
T13-1 Addition_a | only | SFL | [7 empty] | T13-1 Add. | tillage,gravel,veg,S.F lats,brine | MWF and SNPL_with gravel | Migrating Waterfowl & Snowy Plover w/ Gravel | MWF and SNPL
T13-1 Addition_b | only | SFL | [9 empty] | DWM_Dust Control | Dynamic Water Management, January start
T13-1 Addition_c | only | SFL | [9 empty] | DWM_Plovers | Dynamic Water Management, January start & Snowy Plover
T13-1 Addition_d | only | SFL | [9 empty] | DWM_Spring_only | Dynamic Water Management, October start
T13-1 Addition_e | only | SFL | [9 empty] | SFLS | Shallow Flood Sprinklers
T13-1_a | not | Gravel | Tillage | [6 empty] | T13-1SF | tillage,gravel | Gravel | Gravel | MWF and SNPL_with gravel
T13-1_b | not | Gravel | Tillage | [6 empty] | T13-1 POND | tillage,gravel | Tillage | Tillage | DWM_Dust Control
T16_a | not | Veg 08 | Veg 11 | [6 empty] | T16 Original Large Pond | veg | Till-Brine | Till-Brine | DWM_Plovers
T16_b | not | Veg 08 | Veg 11 | [8 empty] | Sand Fences | Sand Fences
T16_c | not | Veg 08 | Veg 11 | [8 empty] | Brine | Brine
T16_d | not | Veg 08 | Veg 11 | [8 empty] | Breeding Waterfowl & Meadow | Breeding Waterfowl & Meadow
T16_e | not | Veg 08 | Veg 11
T16_f | not | Veg 08 | Veg 11
T16_g | not | Veg 08 | Veg 11
T16_h | not | Veg 08 | Veg 11
T16_i | not | Veg 08 | Veg 11
T17-1_a | only | Tillage | [7 empty] | T17-1&-2 | top only MSB/SNPL |  |  | DWM_Spring_only
T17-1_b | only | MSB and SNPL | [8 empty] | Bottom only Tillage
T17-2_a | only | Tillage | [11 empty] | SFLS
T17-2_b | only | MSB and SNPL
T18S_a | not | Veg 08 | Veg 11 | Gravel | [5 empty] | T18S - Brine | veg,gravel |  |  | Gravel
T18S_b | not | Veg 08 | Veg 11 | Gravel
T18S_c | only | Brine | [7 empty] | T18s_c | only brine
T1A-4 | not | Veg 08 | Veg 11 | Gravel | Tillage |  |  |  |  | T1A-4 | Veg, brine preferred |  |  | Tillage
T1A-2_e | only | BWF | [7 empty] | T1A-2_e | only BWF
T21W | not | SFP | Veg 08 | Veg 11 | ENV | SFL | DWM_Jan | DWM_Oct | DWM_Dec | T31W | only Gravel
T23-5 | only | Brine | [7 empty] | T23-5 | only brine |  |  | Till-Brine
T23NE_a | not | Veg 08 | Veg 11 | [6 empty] | T23E | veg |  |  | Sand Fences
T23NE_b | not | Veg 08 | Veg 11
T23NE_c | not | Veg 08 | Veg 11
T23NE_d | not | Veg 08 | Veg 11
T23NW_a | not | Veg 08 | Veg 11
T23NW_b | not | Veg 08 | Veg 11 | [6 empty] | T23W | veg |  |  | Brine
T23SE | not | Veg 08 | Veg 11 | [10 empty] | Breeding Waterfowl & Meadow
T23SW | not | Veg 08 | Veg 11 | [10 empty] | None
T24_a | only | Brine | [7 empty] | T24_a | only Brine
T2-4_a | not | Veg 08 | Veg 11 | [6 empty] | T2-4 POND | Veg
T24_b | only | Brine | [7 empty] | T24_b | only Brine
T2-4_b | not | Veg 08 | Veg 11
T2-4_c | not | Veg 08 | Veg 11
T2-5 | not | Veg 08 | Veg 11 | Tillage | [5 empty] | T2-5 | veg, tillage
T25-3 | only | Brine | [7 empty] | T25-3 | only brine
T25N | not | Veg 08 | Veg 11 | [6 empty] | T25 | veg
T25S | not | Veg 08 | Veg 11
T26_a | not | Tillage | [7 empty] | T26 | tillage
T26_b | not | Tillage
T27 Addition | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel | SFLS |  |  | T27Add | veg,tillage,gravel,S.F lats,S.F sprinklers
T27N | not | Veg 08 | Veg 11 | [6 empty] | T27 only | veg
T27S | not | Veg 08 | Veg 11
T28N_a | not | Tillage | [7 empty] | T28-1 | tillage
T28N_b | not | Tillage
T28N_c | not | Tillage
T28N_d | not | Tillage
T28N_e | not | Tillage
T28N_f | not | Tillage
T28N_g | not | Tillage
T28N_h | not | Tillage
T28N_i | not | Tillage
T28S_a | not | Tillage | [7 empty] | T28-2 | tillage
T28S_b | not | Tillage
T28S_c | not | Tillage
T28S_d | not | Tillage
T29-1 | not | Tillage | [7 empty] | T29-1 | tillage
T29-2_a | not | Tillage | [7 empty] | T29-2 | tillage
T29-2_b | not | Tillage
T29-3 | not | Tillage | Veg 08 | Veg 11 | [5 empty] | T29-3 | tillage,veg
T29-4_a | not | Tillage | Veg 08 | Veg 11 | [5 empty] | T29-4 | no tillage,veg
T29-4_b | not | Tillage
T30-1_a | not | Tillage | [7 empty] | T30-1SF | tillage
T30-1_b | not | Tillage
T30-1_c | not | Tillage
T30-2 | not | Tillage | [7 empty] | T30-2 | tillage
T30-3 | not | Tillage | [7 empty] | T30-3 | tillage
T36-1E_a | not | Tillage | [7 empty] | T36-1 MV/SF SPRINKLER | tillage
T36-1E_b | not | Tillage
T36-1W_a | not | Tillage | [7 empty] | T36-1 POND | tillage
T36-1W_b | not | Tillage
T36-2E | only | Brine | [7 empty] | T36-2 Brine | only brine
T36-2W_a | not | Tillage | Veg 08 | Veg 11 | Gravel |  |  |  |  | T36-2 POND | tillage,veg, brine preferred
T36-2W_b | not | Tillage | Veg 08 | Veg 11 | Gravel
T36-3 Addition | not | Tillage | Veg 08 | Veg 11 | Gravel
T36-3E | not | Tillage | Veg 08 | Veg 11 | Gravel |  |  |  |  | T36-3 Post Brine&Addition | tillage,veg, brine preferred
T36-3W | not | Tillage | Veg 08 | Veg 11 | Gravel
T37-2_a | not | Veg 08 | Veg 11 | SFL | Tillage |  |  |  |  | T37-2 Laterals inc MV trans | veg,S.F lats
T37-2_b | not | Veg 08 | Veg 11 | SFL | Tillage
T37-2_c | only | BWF
T37-2a_a | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2A Laterals | veg,S.F lats,tillage, gravel
T37-2a_b | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel
T37-2b | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2B Pond | veg,S.F lats,tillage,gravel
T37-2c | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2C Pond | veg,S.F lats,tillage,gravel
T37-2d_a | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2D Laterals | veg,S.F lats,tillage, gravel
T37-2d_b | not | Veg 08 | Veg 11 | SFL | Tillage | Gravel
T3SE Addition | not | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T3SE ADD (inc all SF) | Tillage, Gravel, Veg, Brine
T4-3 | not | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-3 | Tillage, Gravel, Veg, Brine
T4-3 Addition | not | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-3 Addition | Tillage, Gravel, Veg, Brine
T4-4 | not | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-4 | Tillage, Gravel, Veg, Brine
T4-5 | only | Brine | [7 empty] | T4-5 | only brine
T5-1 | not | Gravel | Tillage | Brine | [5 empty] | T5-1SF | Gravel, Tillage, Brine
T5-1 Addition | only | Meadow | [7 empty] | T5-1SF Addition | only meadow
T5-2 | not | Veg 08 | Veg 11 | [6 empty] | T5-2SF | Veg
T5-3 | not | Veg 08 | Veg 11 | Tillage | [5 empty] | T5-3SF | Veg, Tillage
T5-3 Addition | not | Veg 08 | Veg 11 | Tillage
T5-3B | not | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T5-3-2 | Gravel, Tillage, Veg
T5-3C | not | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T5-3-3 | Gravel, Tillage, Veg
T5-4 | not | SFP | Veg 08 | Veg 11 | ENV | SFL | DWM_Jan | DWM_Oct | DWM_Dec | T5-4 | only brine
T8W | not | Veg 08 | Veg 11 | [6 empty] | T8W | veg
T9 | not | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T9 | gravel,tillage,veg
Step Constraints |  | steps
T5-1 Addition | not | 1 | 2
T17-1_a | not | 1 | 2
T17-1_b | not | 1 | 2
T18S_a | only | 2
T18S_b | only | 2
T18S_c | only | 2 | [7 empty] | T18S: only allow change in step 1
Phase Constraints* |  | steps |  |  |  |  | * Phase 7.1 = 7a, phase 7.2 = 7b
1 | only | 1 | 2 | 3 | 4 | 5
2 | only | 1 | 2 | 3 | 4 | 5
3 | only | 1 | 2 | 3 | 4 | 5
4 | only | 1 | 2 | 3 | 4 | 5
5 | only | 3 | 4 | 5
7 | only | 3 | 4 | 5
7.1 | only | 3 | 4 | 5
7.2 | only | 3 | 4 | 5
8 | only | 3 | 4 | 5
9 | only | 3 | 4 | 5
10 | only | 3 | 4 | 5

## As-Built HV & WD
DCA | DCM | BW | MW | Pl | MS | Md | Water (f/y) |  | Habitat value and water demand exceptions from Generic Values, for DCA/DCM/Step0 combinations. The source data for these exceptions was taken from JD workbook, sheets 'Base_20171129', 'DWM', and 'SiteHSV'. #N/A values indicate that there is no exception assignment for that column (i.e. Water) for that combination, and will cause the formulas in MP_new to revert to the generic values for those columns.
Channel Area North | ENV | 0.16195 | 0.064286 | 0 | 0.067594 | 0.00090226 | #N/A
Channel Area South | ENV | 0.24036 | 0.055076 | 0 | 0.055025 | 0.0031472 | #N/A
Corridor 1 | Gravel | 0 | 0.020819 | 0 | 0.053015 | 0 | #N/A
Phase 8_a | Gravel | 0 | 0.020833 | 0 | 0.053031 | 0 | #N/A
Phase 8_b | Gravel | 0 | 0.020833 | 0 | 0.053031 | 0 | #N/A
T10-1_a | SFP | 0 | 0.36048 | 0.28614 | 0.57886 | 0 | #N/A
T10-1_a | DWM_Dec | 0 | 0.19033 | 0.35454 | 0.57333 | 9.4567e-06 | 1.5475
T10-1_b | SFP | 0 | 0.36048 | 0.28614 | 0.57886 | 0 | #N/A
T10-1_b | DWM_Dec | 0 | 0.19033 | 0.35454 | 0.57333 | 9.4567e-06 | 1.5475
T10-1_c | SFP | 0 | 0.36048 | 0.28614 | 0.57886 | 0 | #N/A
T10-1_c | DWM_Dec | 0 | 0.19033 | 0.35454 | 0.57333 | 9.4567e-06 | 1.5475
T10-1a | None | 0 | 0.044067 | 0.038467 | 0.28558 | 0.0060866 | #N/A
T10-1a | DWM_Dec | 0 | 0.018077 | 0.37029 | 0.29215 | 0 | 1.07
T10-2N | SFP | 0 | 0.2909 | 0.35 | 0.61413 | 0 | #N/A
T10-2N | DWM_Jan | 0 | 0.12347 | 0.20259 | 0.44935 | 1.5357e-06 | 0.98
T10-2S | SFL | 0 | 0.44059 | 0.22291 | 0.64274 | 2.8653e-05 | #N/A
T10-2S | DWM_Jan | 0 | 0.25342 | 0.14004 | 0.45679 | 3.3626e-05 | 0.98
T10-3a | None | 0 | 0.002095 | 0 | 0.038885 | 0 | #N/A
T10-3a | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T10-3E | SFP | 0 | 0.07784 | 0.24809 | 0.48498 | 0 | #N/A
T10-3E | DWM_Jan | 0 | 0.017723 | 0.1089 | 0.30536 | 0 | 0.98
T10-3W | Brine | 0 | 0 | 0 | 0.048735 | 0 | #N/A
T10-3W | Brine (DWM) | 0 | 0 | 0 | 0.028681 | 0 | 0
T11 | SFP | 0 | 0.14385 | 0.20775 | 0.64847 | 0 | #N/A
T1-1 | SFP | 0 | 0.27021 | 0.10984 | 0.62146 | 0 | #N/A
T1-1 | DWM_Dec | 0 | 0.060567 | 0.098273 | 0.41548 | 2.3538e-05 | 1.07
T12-1 | None | 0 | 0.0020399 | 0 | 0.025916 | 0 | #N/A
T12-1 | Tillage | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T13-1 Addition_a | SFL | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1 Addition_a | DWM_Jan | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1 Addition_b | SFL | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1 Addition_b | DWM_Jan | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1 Addition_c | SFL | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1 Addition_c | DWM_Jan | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1 Addition_d | SFL | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1 Addition_d | DWM_Jan | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1 Addition_e | SFL | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1 Addition_e | DWM_Jan | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1_a | SFL | 0 | 0.49977 | 0.1942 | 0.47774 | 0.013102 | #N/A
T13-1_a | SFL (DWM) | 0 | 0.5471 | 0.23965 | 0.37891 | 0.0074933 | 3.9275
T13-1_b | SFL | 0 | 0.4844 | 0.1943 | 0.44919 | 0.017481 | #N/A
T13-1_b | SFL (DWM) | 0 | 0.5471 | 0.23965 | 0.37891 | 0.0074933 | 3.9275
T13-2 | SFP | 0 | 0.52095 | 0.24452 | 0.54181 | 0 | #N/A
T13-3_a | SFP | 0 | 0.16473 | 0.11766 | 0.54647 | 0 | #N/A
T13-3_b | SFP | 0 | 0.16473 | 0.11766 | 0.54647 | 0 | #N/A
T15 | None | 0 | 0.0021021 | 0 | 0.038888 | 0 | #N/A
T15 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T16_a | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A |  | Custom water duties for T16 habitat ponds from Jason Olin email 04/05/2018
T16_a | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98 |  | Note on T16: T16 pond water duties from Jason Olin are for pond acreage only, not aggregate over entire DCA
T16_a | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673 |  | Factor T16 water duties to reflect pond portion of approximately 300 acres ponds / 1100 acres dry.
T16_a | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673 |  | T16 factor = | 0.27273
T16_b | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_b | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_b | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_b | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_c | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_c | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_c | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_c | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_d | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_d | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_d | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_d | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_e | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_e | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_e | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_e | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_f | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_f | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_f | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_f | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_g | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_g | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_g | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_g | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_h | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_h | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_h | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_h | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_i | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_i | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_i | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_i | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16_j | SFP | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T16_j | DWM_Jan | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T16_j | T16 Unique | 0 | 0.21573 | 0.16353 | 0.55741 | 0 | 1.4673
T16_j | MWF and MSB | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T17-1_a | SFP | 0 | 0.41573 | 0.19139 | 0.53254 | 0.00013361 | #N/A
T17-1_a | DWM_Plovers | 0 | 0.52499 | 0.24903 | 0.54358 | 0.00014091 | 4.0675
T17-1_b | SFP | 0 | 0.41573 | 0.19139 | 0.53254 | 0.00013361 | #N/A
T17-1_b | DWM_Plovers | 0 | 0.52499 | 0.24903 | 0.54358 | 0.00014091 | 4.0675
T17-2_a | SFP | 0 | 0.54504 | 0.15909 | 0.43034 | 0.00043276 | #N/A
T17-2_a | DWM_Plovers | 0 | 0.48845 | 0.22657 | 0.40288 | 0.00044054 | 4.0675
T17-2_b | SFP | 0 | 0.54504 | 0.15909 | 0.43034 | 0.00043276 | #N/A
T17-2_b | DWM_Plovers | 0 | 0.48845 | 0.22657 | 0.40288 | 0.00044054 | 4.0675
T18-0 | SFP | 0 | 0.64266 | 0.1012 | 0.72369 | 0 | #N/A
T18-0 | DWM_Jan | 0 | 0.26634 | 0.089231 | 0.46826 | 0 | 0.98
T18N | SFP | 0 | 0.40857 | 0.048339 | 0.47854 | 0 | #N/A
T18N Addition | SFP | 0 | 0.18169 | 0.077934 | 0.58263 | 0 | #N/A
T18S_a | SFP | 0 | 0.39128 | 0.16361 | 0.54432 | 8.6081e-06 | #N/A
T18S_b | SFP | 0 | 0.39128 | 0.16361 | 0.54432 | 8.6081e-06 | #N/A
T18S_c | SFP | 0 | 0.39128 | 0.16361 | 0.54432 | 8.6081e-06 | #N/A
T1A-1 | Sand Fences | 0 | 0.049155 | 0.15378 | 0.33056 | 0.01723 | #N/A
T1A-2_a | SFL | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-2_a | T1A-2 Unique | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 2.73 | SFL
T1A-2_b | SFL | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-2_b | T1A-2 Unique | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 2.68 | SFLS
T1A-2_c | SFL | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-2_c | T1A-2 Unique | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 2.73 | SFL
T1A-2_d | SFL | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-2_d | T1A-2 Unique | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 2.68 | SFLS
T1A-2_e | SFL | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-2_e | T1A-2 Unique | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 3.18 | Veg 11
T1A-3_a | None | 0 | 0.002094 | 0 | 0.039075 | 0 | #N/A
T1A-3_a | Gravel | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T1A-3_b | None | 0 | 0.002094 | 0 | 0.039075 | 0 | #N/A
T1A-3_b | Gravel | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T1A-3_c | None | 0 | 0.002094 | 0 | 0.039075 | 0 | #N/A
T1A-3_c | Gravel | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T1A-4 | None | 0 | 0.0020972 | 0 | 0.038937 | 0 | #N/A
T1A-4 | SFLS | 0 | 0.22988 | 0.44433 | 0.70522 | 0 | 2.9248
T20 | None | 0 | 0.0020946 | 0 | 0.038858 | 0.0007945 | #N/A
T20 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-1 | SFL | 0 | 0.43157 | 0.28854 | 0.56621 | 0.0028863 | #N/A
T2-1 Addition | SFL | 0 | 0.2452 | 0.33233 | 0.57181 | 0.0055616 | #N/A
T21-1 | None | 0 | 0.0053937 | 0.041127 | 0.24002 | 0 | #N/A
T21-1 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T21-2 | None | 0 | 0.0021591 | 0 | 0.038864 | 0 | #N/A
T21-2 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-1b | None | 0.17261 | 0.04684 | 0.094477 | 0.24217 | 0.10205 | #N/A
T2-1b | Veg 11 | 0.22579 | 0.05244 | 0.03434 | 0.21506 | 0.56533 | 1.49
T2-1c | None | 0.14497 | 0.029972 | 0.019378 | 0.20256 | 0.019106 | #N/A
T2-1c | Veg 11 | 0.27713 | 0.072657 | 0.067099 | 0.27404 | 0.55788 | 1.49
T21E | SFP | 0 | 0.58696 | 0.064924 | 0.54361 | 0.0011619 | #N/A
T21W | SFL | 0 | 0.050694 | 0.28287 | 0.40833 | 0 | #N/A
T21W | DWM_Jan | 0 | 0.018261 | 0.012997 | 0.19203 | 0 | 0.98
T22 | None | 0 | 0.0089332 | 0.065073 | 0.28455 | 0 | #N/A
T22 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-2_a | SFP | 0 | 0.43736 | 0.20998 | 0.63968 | 0 | #N/A
T2-2_b | SFP | 0 | 0.43736 | 0.20998 | 0.63968 | 0 | #N/A
T2-3 | SFL | 0 | 0.2755 | 0.24926 | 0.55904 | 0 | #N/A
T2-3 | Tillage | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T23-5 | SFP | 0 | 0.061546 | 0.099498 | 0.32545 | 0 | #N/A
T23-5 | SFP (DWM) | 0 | 0.030434 | 0.13872 | 0.28501 | 0 | 4.36
T23NE_a | SFL | 0 | 0.036317 | 0.078282 | 0.3037 | 0.00019889 | #N/A
T23NE_b | SFL | 0 | 0.036317 | 0.078282 | 0.3037 | 0.00019889 | #N/A
T23NE_c | SFL | 0 | 0.036317 | 0.078282 | 0.3037 | 0.00019889 | #N/A
T23NE_d | SFL | 0 | 0.036317 | 0.078282 | 0.3037 | 0.00019889 | #N/A
T23NW_a | SFL | 0 | 0.058019 | 0.095593 | 0.33617 | 9.0868e-05 | #N/A
T23NW_b | SFL | 0 | 0.058019 | 0.095593 | 0.33617 | 9.0868e-05 | #N/A
T23SE | SFL | 0 | 0.20544 | 0.36786 | 0.52268 | 0.00031526 | #N/A
T23SW | SFL | 0 | 0.32498 | 0.26229 | 0.53403 | 0 | #N/A
T24 Addition | SFL | 0 | 0 | 0.076596 | 0.15059 | 0.00094563 | #N/A
T24 Addition | Tillage | 0 | 0.0020833 | 0 | 0.038891 | 0.0047833 | 0
T24_a | SFL | 0 | 0.16625 | 0.45057 | 0.53616 | 0.0018369 | #N/A
T2-4_a | SFL | 0 | 0.073045 | 0.11542 | 0.39834 | 0.00061009 | #N/A
T2-4_a | Brine | 0 | 0.03741 | 0.042449 | 0.26195 | 0 | 0
T24_b | SFL | 0 | 0.16625 | 0.45057 | 0.53616 | 0.0018369 | #N/A
T2-4_b | SFL | 0 | 0.073045 | 0.11542 | 0.39834 | 0.00061009 | #N/A
T2-4_b | Tillage | 0 | 0.03741 | 0.042449 | 0.26195 | 0 | 0
T2-4_c | SFL | 0 | 0.073045 | 0.11542 | 0.39834 | 0.00061009 | #N/A
T2-4_c | Tillage | 0 | 0.03741 | 0.042449 | 0.26195 | 0 | 0
T2-5 | Brine | 0 | 0 | 0.012117 | 0.091718 | 0 | #N/A
T25-3 | SFL | 0 | 0.012808 | 0.091774 | 0.25106 | 0 | #N/A
T25-3 | DWM_Jan | 0 | 0.010657 | 0 | 0.16245 | 0 | 0.98
T25N | SFL | 0 | 0.30315 | 0.22013 | 0.56424 | 0.0015935 | #N/A
T25S | SFL | 0 | 0.2674 | 0.34968 | 0.58755 | 0.00046438 | #N/A
T25S | SFL (DWM) | 0 | 0.26893 | 0.43623 | 0.6019 | 0.00046115 | 3.9275
T26_a | SFL | 0 | 0.10497 | 0.35856 | 0.43736 | 0.0027373 | #N/A
T26_a | SFL (DWM) | 0 | 0.30609 | 0.41117 | 0.54295 | 0.0027297 | 3.9275
T26_b | SFL | 0 | 0.10497 | 0.35856 | 0.43736 | 0.0027373 | #N/A
T26_b | SFL (DWM) | 0 | 0.30609 | 0.41117 | 0.54295 | 0.0027297 | 3.9275
T27 Addition | SFL | 0 | 0 | 0.080952 | 0.15913 | 0 | #N/A
T27N | SFL | 0 | 0.18734 | 0.39907 | 0.49622 | 0.00056611 | #N/A
T27S | SFL | 0 | 0.16263 | 0.43534 | 0.49043 | 0 | #N/A
T28N_a | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_a | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 2.68 | SFLS
T28N_b | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_b | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 0 | Gravel
T28N_c | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_c | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 2.73 | SFL
T28N_d | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_d | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 0 | Gravel
T28N_e | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_e | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 2.68 | SFLS
T28N_f | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_f | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 2.68 | SFLS
T28N_g | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_g | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 3.18 | Veg 11
T28N_h | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_h | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 3.18 | Veg 11
T28N_i | SFL | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28N_i | T28N Unique | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 3.18 | Veg 11
T28S_a | SFL | 0.16577 | 0.19373 | 0.2385 | 0.43723 | 0.0963 | #N/A
T28S_a | T28S Unique | 0.42809 | 0.31381 | 0.29568 | 0.5454 | 0.30164 | 2.68 | SFLS
T28S_b | SFL | 0.16577 | 0.19373 | 0.2385 | 0.43723 | 0.0963 | #N/A
T28S_b | T28S Unique | 0.42809 | 0.31381 | 0.29568 | 0.5454 | 0.30164 | 0 | Gravel
T28S_c | SFL | 0.16577 | 0.19373 | 0.2385 | 0.43723 | 0.0963 | #N/A
T28S_c | T28S Unique | 0.42809 | 0.31381 | 0.29568 | 0.5454 | 0.30164 | 0 | Gravel
T28S_d | SFL | 0.16577 | 0.19373 | 0.2385 | 0.43723 | 0.0963 | #N/A
T28S_d | T28S Unique | 0.42809 | 0.31381 | 0.29568 | 0.5454 | 0.30164 | 3.18 | Veg 11
T29-1 | SFP | 0 | 0.55214 | 0.021338 | 0.2848 | 0 | #N/A
T29-1 | SFP (DWM) | 0 | 0.58799 | 0.073502 | 0.30122 | 0 | 4.8375
T29-2_a | SFP | 0 | 0.18252 | 0.10761 | 0.48586 | 0.015996 | #N/A
T29-2_a | SFP (DWM) | 0 | 0.2126 | 0.2114 | 0.5437 | 0.015986 | 4.8375
T29-2_b | SFP | 0 | 0.18252 | 0.10761 | 0.48586 | 0.015996 | #N/A
T29-2_b | SFP (DWM) | 0 | 0.2126 | 0.2114 | 0.5437 | 0.015986 | 4.8375
T29-3 | SFP | 0 | 0.13568 | 0.036691 | 0.36722 | 0 | #N/A
T29-4_a | SFL | 0 | 0.13258 | 0.13337 | 0.39412 | 0 | #N/A
T29-4_b | SFL | 0 | 0.13258 | 0.13337 | 0.39412 | 0 | #N/A
T29-4_b | Brine | 0 | 0 | 0.0081639 | 0.089233 | 0 | 0
T30-1_a | SFL | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | #N/A
T30-1_a | T30-1 Unique | 0.70312 | 0.3476 | 0.029161 | 0.35826 | 0.55611 | 2.73 | SFL
T30-1_b | SFL | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | #N/A
T30-1_b | T30-1 Unique | 0.70312 | 0.3476 | 0.029161 | 0.35826 | 0.55611 | 3.18 | Veg 11
T30-1_c | SFL | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | #N/A
T30-1_c | T30-1 Unique | 0.70312 | 0.3476 | 0.029161 | 0.35826 | 0.55611 | 3.18 | Veg 11
T30-2 | SFP | 0 | 0.48725 | 0.042537 | 0.40893 | 0.001136 | #N/A
T30-2 | SFP (DWM) | 0 | 0.66577 | 0.082649 | 0.38977 | 0.0011511 | 4.8375
T30-3 | SFP | 0 | 0.37749 | 0.077083 | 0.47257 | 0.00011574 | #N/A
T32-1_a | None | 0.057665 | 0.020856 | 0 | 0.037166 | 0 | #N/A
T32-1_a | T32-1 Unique | 0.095588 | 0.053913 | 0.021605 | 0.1975 | 0 | 3.18 | Veg 11
T32-1_b | None | 0.057665 | 0.020856 | 0 | 0.037166 | 0 | #N/A
T32-1_b | T32-1 Unique | 0.095588 | 0.053913 | 0.021605 | 0.1975 | 0 | 0 | None
T32-2 | None | 0.029393 | 0.0020793 | 0 | 0.030058 | 0.07755 | #N/A
T32-2 | Gravel | 0.029398 | 0.0020833 | 0 | 0.030052 | 0.044908 | 0
T35-1 | SFP | 0 | 0.28514 | 0.060921 | 0.35542 | 0 | #N/A
T35-1 | Gravel | 0 | 0.0020833 | 0 | 0.035469 | 0 | 0
T35-2 | SFP | 0 | 0.019214 | 0.047162 | 0.32686 | 0 | #N/A
T35-2 | Gravel | 0 | 0.0020833 | 0 | 0.033473 | 0 | 0
T35-3 | None | 0 | 0.0061327 | 0.062295 | 0.24369 | 0 | #N/A
T35-3 | Gravel | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T36-1E_a | SFL | 0.34112 | 0.43232 | 0.1069 | 0.34802 | 0.079369 | #N/A
T36-1E_a | T36-1E Unique | 0.58 | 0.24977 | 0.025694 | 0.13738 | 0.22433 | 2.73 | SFL
T36-1E_b | SFL | 0.34112 | 0.43232 | 0.1069 | 0.34802 | 0.079369 | #N/A
T36-1E_b | T36-1E Unique | 0.58 | 0.24977 | 0.025694 | 0.13738 | 0.22433 | 3.18 | Veg 11
T36-1W_a | SFL | 0 | 0.43217 | 0.16652 | 0.48653 | 0.041349 | #N/A
T36-1W_a | T36-1W Unique | 0.58 | 0.24977 | 0.025694 | 0.13738 | 0.22433 | 2.73 | SFL
T36-1W_b | SFL | 0 | 0.43217 | 0.16652 | 0.48653 | 0.041349 | #N/A
T36-1W_b | T36-1W Unique | 0.58 | 0.24977 | 0.025694 | 0.13738 | 0.22433 | 3.18 | Veg 11
T36-2E | SFP | 0 | 0.35914 | 0.070631 | 0.52908 | 0.00097897 | #N/A
T36-2E | SFP (DWM) | 0 | 0.21697 | 0.1352 | 0.49463 | 0.00098888 | 4.8375
T36-2W_a | SFP | 0 | 0.020735 | 0.057099 | 0.27873 | 0.00079162 | #N/A
T36-2W_b | SFP | 0 | 0.020735 | 0.057099 | 0.27873 | 0.00079162 | #N/A
T36-3 Addition | Brine | 0 | 0 | 0.035047 | 0.16916 | 0.014486 | #N/A
T36-3E | Brine | 0 | 0 | 0.04689 | 0.19804 | 0 | #N/A
T36-3W | Brine | 0 | 0 | 0.094794 | 0.19782 | 0 | #N/A
T37-1a | None | 0.067301 | 0.020848 | 0 | 0.037111 | 0.098443 | #N/A
T37-1a | Gravel | 0.067305 | 0.020833 | 0 | 0.037123 | 0.098457 | 0
T37-2_a | None | 0 | 0.0020911 | 0 | 0.038936 | 0.00052938 | #N/A
T37-2_a | DWM_Jan | 0 | 0.013333 | 0.078132 | 0.26089 | 0.00054074 | 3
T37-2_b | None | 0 | 0.0020911 | 0 | 0.038936 | 0.00052938 | #N/A
T37-2_c | None | 0 | 0.0020911 | 0 | 0.038936 | 0.00052938 | #N/A
T37-2_c | Veg 11 | 0 | 0.013333 | 0.078132 | 0.26089 | 0.00054074 | 3
T37-2_d | None | 0 | 0.0020911 | 0 | 0.038936 | 0.00052938 | #N/A
T37-2_d | DWM_Jan | 0 | 0.013333 | 0.078132 | 0.26089 | 0.00054074 | 3
T37-2a_a | None | 0.029419 | 0.0023225 | 0 | 0.095224 | 0.014623 | #N/A
T37-2a_a | DWM_Oct | 0 | 0.036309 | 0.38728 | 0.45553 | 0.0037659 | 0.98
T37-2a_b | None | 0.029419 | 0.0023225 | 0 | 0.095224 | 0.014623 | #N/A
T37-2a_b | DWM_Oct | 0 | 0.036309 | 0.38728 | 0.45553 | 0.0037659 | 0.98
T37-2b | None | 0 | 0.0028869 | 0.0069768 | 0.14026 | 0 | #N/A
T37-2b | DWM_Jan | 0 | 0 | 0.068719 | 0.13973 | 0 | 0.98
T37-2c | None | 0 | 0.0028784 | 0.014712 | 0.17814 | 0 | #N/A
T37-2c | DWM_Jan | 0 | 0 | 0.072063 | 0.14037 | 0 | 0.98
T37-2d_a | None | 0 | 0.0033319 | 0.027572 | 0.18717 | 0 | #N/A
T37-2d_a | DWM_Jan | 0 | 0.022986 | 0.37026 | 0.28644 | 0 | 0.98
T37-2d_b | None | 0 | 0.0033319 | 0.027572 | 0.18717 | 0
T37-2d_b | DWM_Jan | 0 | 0.022986 | 0.37026 | 0.28644 | 0
T3NE_a | SFL | 0 | 0.026743 | 0.14471 | 0.32587 | 0 | #N/A
T3NE_a | Tillage | 0 | 0.06483 | 0.18275 | 0.42103 | 0 | 0
T3NE_b | SFL | 0 | 0.026743 | 0.14471 | 0.32587 | 0 | #N/A
T3NE_b | Brine | 0 | 0.06483 | 0.18275 | 0.42103 | 0 | 0
T3SE | SFL | 0 | 0.0060245 | 0.12432 | 0.23649 | 0 | #N/A
T3SE | Tillage | 0 | 0.06483 | 0.18275 | 0.42103 | 0 | 0
T3SE Add | Tillage | 0 | 0.09866 | 0.43115 | 0.53577 | 0 | 0
T3SE Addition | SFL | 0 | 0.0034839 | 0.16426 | 0.22994 | 0 | #N/A
T3SW | SFL | 0 | 0.020517 | 0.15777 | 0.27534 | 0 | #N/A
T3SW | Tillage | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T4-3 | SFL | 0 | 0.01834 | 0.31981 | 0.38916 | 0.00093708 | #N/A
T4-3 Addition | SFL | 0 | 0.020938 | 0.37471 | 0.40034 | 0.001373 | #N/A
T4-4 | SFP | 0 | 0.13839 | 0.12687 | 0.56 | 0.001548 | #N/A
T4-5 | SFP | 0 | 0 | 0.026042 | 0.16771 | 0 | #N/A
T5-1 | SFL | 0.33218 | 0.16424 | 0.19387 | 0.39062 | 0.17743 | #N/A
T5-1 Addition | Veg 08 | 0 | 0.043719 | 0.090955 | 0.29799 | 0 | #N/A
T5-2 | SFL | 0 | 0.19697 | 0.31768 | 0.51465 | 0.0040404 | #N/A
T5-3 | SFL | 0.36257 | 0.25474 | 0.32091 | 0.50093 | 0.01681 | #N/A
T5-3 | SFL (DWM) | 0.25624 | 0.12353 | 0.21793 | 0.37232 | 0.016612 | 3.9275
T5-3 Addition | SFP | 0.36811 | 0.40447 | 0.14417 | 0.40881 | 0.053598 | #N/A
T5-3 Addition | SFP (DWM) | 0.30727 | 0.21172 | 0.27806 | 0.43337 | 0.031523 | 4.8375
T5-3B | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.4545 | #N/A
T5-3C | Veg 08 | 0.20609 | 0.053299 | 0.036548 | 0.25178 | 0.31827 | #N/A
T5-4 | SFP | 0 | 0.14839 | 0.34055 | 0.59332 | 0.0041475 | #N/A
T5-4 | Brine | 0 | 0.0125 | 0 | 0.053033 | 0 | 0
T5-4B | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.4245 | #N/A
T5-4C | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3535 | #N/A
T5-4D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.518 | #N/A
T5-5A | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.34675 | #N/A
T5-5D | Veg 08 | 0.22175 | 0.05325 | 0.041 | 0.2515 | 0.20025 | #N/A
T5-6A | Veg 08 | 0.1635 | 0.05325 | 0.0325 | 0.23475 | 0.306 | #N/A
T5-6B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.446 | #N/A
T5-6C | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.443 | #N/A
T5-6D | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3605 | #N/A
T5-7A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.353 | #N/A
T5-7B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.44525 | #N/A
T5-7D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35175 | #N/A
T6-4C | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.48825 | #N/A
T6-4D | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.36375 | #N/A
T6-5A | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3885 | #N/A
T6-5B | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.41325 | #N/A
T6-5C | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.2855 | #N/A
T6-5D | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.2615 | #N/A
T6-6A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.4405 | #N/A
T6-6B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.4365 | #N/A
T6-6C | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.271 | #N/A
T6-6D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36875 | #N/A
T6-7A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.358 | #N/A
T6-7B | Veg 08 | 0.22175 | 0.05325 | 0.0325 | 0.23475 | 0.23525 | #N/A
T6-7C | Veg 08 | 0.22175 | 0.05325 | 0.041 | 0.2515 | 0.176 | #N/A
T6-7D | Veg 08 | 0.22175 | 0.05325 | 0.0325 | 0.23475 | 0.188 | #N/A
T7-4A | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.43825 | #N/A
T7-4C | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3925 | #N/A
T7-4D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.436 | #N/A
T7-5A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.343 | #N/A
T7-5B | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.31725 | #N/A
T7-5C | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.45525 | #N/A
T7-5D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36525 | #N/A
T7-6A | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.329 | #N/A
T7-6B | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.336 | #N/A
T7-6C | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.363 | #N/A
T7-6D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35125 | #N/A
T7-7A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35275 | #N/A
T7-7B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36075 | #N/A
T7-7C | Veg 08 | 0.16341 | 0.053383 | 0.021805 | 0.23484 | 0.31429 | #N/A
T7-7D | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3255 | #N/A
T8-3A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.506 | #N/A
T8-3B | Veg 08 | 0.16348 | 0.053401 | 0.027456 | 0.23476 | 0.37935 | #N/A
T8-4A | Veg 08 | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3605 | #N/A
T8-4B | Veg 08 | 0.1635 | 0.05325 | 0.0325 | 0.23475 | 0.352 | #N/A
T8-4C | Veg 08 | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.40125 | #N/A
T8-4D | Veg 08 | 0.16337 | 0.053218 | 0.015099 | 0.2349 | 0.35124 | #N/A
T8-5A | Veg 08 | 0.16348 | 0.053401 | 0.015113 | 0.23476 | 0.36322 | #N/A
T8-5B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35525 | #N/A
T8-5C | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36125 | #N/A
T8-5D | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36675 | #N/A
T8-6A | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36625 | #N/A
T8-6B | Veg 08 | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.349 | #N/A
T8-6C | Veg 08 | 0.16337 | 0.053253 | 0.021928 | 0.2347 | 0.29952 | #N/A
T8-6D | Veg 08 | 0.16349 | 0.053256 | 0.015116 | 0.23488 | 0.34093 | #N/A
T8W | Brine | 0 | 0 | 0.040289 | 0.17576 | 0 | #N/A
T9 | SFP | 0 | 0.12155 | 0.25929 | 0.52223 | 0.0019126 | #N/A
T9 | DWM_Dec | 0 | 0.093123 | 0.25077 | 0.48157 | 0.001906 | 1.07

## Design HV & WD
Generic habitat value and water demand by MP DCM designation.
|  | Habitat factors (% of area) generated as average of Base Case habitat values for each DCM |  |  |  |  | color = source | Habitat factors and Water values Copied from John Dickey workbook sheet 'WD_HV_gen'. | [5 empty] | Water duties from Jason Olin (email 04/05/18)
MP_id | Desc | BW | MW | Pl | MS | Md | Water (f/y) | BW | MW | Pl | MS | Md | Water (f/y) |  | Water (f/y)
SFP | Shallow Flood Pond | 0.021492 | 0.28007 | 0.12329 | 0.44243 | 0.0068052 | 3.13 | 0.021492 | 0.28007 | 0.12329 | 0.44243 | 0.0068052 | 4.36 | Shallow Flood Lateral | 2.73 |  | yes
Veg 08 | Managed Vegetation (2008) | 0.16833 | 0.053258 | 0.02126 | 0.23564 | 0.3619 | 1.01 | 0.16833 | 0.053258 | 0.02126 | 0.23564 | 0.3619 | 1.35 | Sprinkler Shallow Flood | 2.68 |  | no
Veg 11 | Managed Vegetation (2011) | 0.019222 | 0.022222 | 0.030318 | 0.1247 | 0.00017646 | 2.65 | 0.019222 | 0.022222 | 0.030318 | 0.1247 | 0.00017646 | 1.49 | Drip Tube Managed Veg | 1.01
ENV | Enhanced Native Vegetation | 0.20116 | 0.059681 | 0 | 0.06131 | 0.0020247 | 0.72 | 0.20116 | 0.059681 | 0 | 0.06131 | 0.0020247 | 0.72 | Sprinkler Managed Veg | 2.65 | normal operating conditions, estblishment is higher water use
SFL | Shallow Flood Lateral | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 2.73 | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 3.51 | Ponds | 3.13 | Note: "Ponds" and "Habitat Ponds" water duties are considered to be aggregate values for entire DCA.
DWM_Jan | Dynamic Water Management, January start | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 0.98 | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 0.98 | Habitat Ponds | 3.86
DWM_Oct | Dynamic Water Management, October start | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | T16 Habitat Ponds | 5.38 | Note: "T16 Habitat Pond" water duties are considered to be specific to actual pond acreage (and will be adjusted for each HDCM). These will go into the custom sheet for MP steps
DWM_Dec | Dynamic Water Management, December start | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 1.07 | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 1.07
BWF | Breeding Waterfowl | 0.53251 | 0.61029 | 0.1152 | 0.47706 | 0 | 3.86 | 0.53251 | 0.61029 | 0.1152 | 0.47706 | 0 | 4.1
MWF | Migrating Waterfowl | 0 | 0.755 | 0.14514 | 0.5702 | 0 | 3.86 | 0 | 0.755 | 0.14514 | 0.5702 | 0 | 4.71
SNPL_realistic | Snowy Plover | 0 | 0.27 | 0.53908 | 0.56125 | 0 | 3.86 | 0 | 0.27 | 0.53908 | 0.56125 | 0 | 3.46
SNPL_with gravel | Snowy Plover w/ Gravel | 0 | 0.077355 | 0.52288 | 0.54848 | 0 | 3.86 | 0 | 0.077355 | 0.52288 | 0.54848 | 0 | 3.46
MSB | Migrating Shorebirds | 0 | 0.3525 | 0.39217 | 0.89443 | 0 | 3.86 | 0 | 0.3525 | 0.39217 | 0.89443 | 0 | 4.71
Meadow | Meadow | 0.15384 | 0.02 | 0 | 0 | 0.9725 | 1.49 | 0.15384 | 0.02 | 0 | 0 | 0.9725 | 1.49
MWF and MSB | Migrating Waterfowl & Migrating Shorebirds | 0 | 0.755 | 0.15839 | 0.73202 | 0 | 3.86 | 0 | 0.755 | 0.15839 | 0.73202 | 0 | 4.71
MSB and SNPL | Migrating Shorebirds & Snowy Plover | 0 | 0.12 | 0.53908 | 0.89443 | 0 | 3.86 | 0 | 0.12 | 0.53908 | 0.89443 | 0 | 4.71
MSB and SNPL_gravel | Migrating Shorebirds & Snowy Plover w/ Gravel | 0 | 0.1146 | 0.52288 | 0.87407 | 0 | 3.86 | 0 | 0.1146 | 0.52288 | 0.87407 | 0 | 4.71
MSB and SNPL_gravel_MWF | Migrating Shorebirds & Snowy Plover w/ Gravel & Migrating Waterfowl | 0 | 0.382 | 0.52288 | 0.87407 | 0 | 3.86 | 0 | 0.382 | 0.52288 | 0.87407 | 0 | 4.71
MWF and SNPL | Migrating Waterfowl & Snowy Plover | 0 | 0.37267 | 0.50391 | 0.63196 | 0 | 3.86 | 0 | 0.37267 | 0.50391 | 0.63196 | 0 | 4.71
MWF and SNPL_with gravel | Migrating Waterfowl & Snowy Plover w/ Gravel | 0 | 0.35187 | 0.56982 | 0.61023 | 0 | 3.86 | 0 | 0.35187 | 0.56982 | 0.61023 | 0 | 4.71
DWM_Dust Control | Dynamic Water Management, January start | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 0.98 | 0 | 0.041543 | 0.12906 | 0.30121 | 0 | 0.98
DWM_Plovers | Dynamic Water Management, January start & Snowy Plover | 0 | 0.047273 | 0.36071 | 0.3909 | 0 | 3.59 | 0 | 0.047273 | 0.36071 | 0.3909 | 0 | 3.59
DWM_Spring_only | Dynamic Water Management, October start | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51
SFLS | Shallow Flood Sprinklers | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 2.68 | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 3
Gravel | Gravel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tillage | Tillage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Till-Brine | Till-Brine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sand Fences | Sand Fences | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.049155 | 0.15378 | 0.33056 | 0.01723 | 0
Brine | Brine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.048735 | 0 | 0
Breeding Waterfowl & Meadow | Breeding Waterfowl & Meadow | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | 3.51 | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | 3.51
None | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: in general case, waterless DCMs have no habitat value. In a few specific instances in Base case, some DCAs under waterless DCMs had habitat (see "Custom HV and WD" sheet).

## Cost Analysis Input
step | start | complete |  | dust_dcm | capital/SM | om/SM-Y | mp_name | desc | hab_id | dust_dcm | O&M Estimates fopr 2017/2018(from email from J. Valenzuela, 05/01/18)
0 | 2000 | 2017 | 0 | Traditional Shallow Flood | 25 | 0.27874 | Breeding Waterfowl & Meadow | Breeding Waterfowl & Meadow | BWF&MDW | Habitat DCM | SIP DCM | Step 0 (sq mi) | % of O&M | O&M Cost ($ million) | O&M Cost ($ million / sq. mi.)
1 | 2020 | 2023 | 1 | Sprinkler Shallow Flood | 32 | 0.34503 | Brine | Brine | Brine | Brine with BACM Backup | Traditional Shallow Flood | 15.606 | 0.15 | 4.35 | 0.27874
2 | 2023 | 2026 | 2 | Managed Vegetation Farm | 36 | 1.6403 | BWF | Breeding Waterfowl | BWF | Traditional Shallow Flood | Sprinkler Shallow Flood | 11.767 | 0.14 | 4.06 | 0.34503
3 | 2026 | 2029 | 3 | Managed Vegetation Phase 7a, 9 and 10 | 36 | 2.3525 | DWM_Dec | Dynamic Water Management - DEC | DWM_Dec | Traditional Shallow Flood | Managed Vegetation Farm | 3.536 | 0.2 | 5.8 | 1.6403
4 | 2029 | 2032 | 4 | Gravel | 37 | 0.23293 | DWM_Dust Control | Dynamic Water Management - Dust Control | DWM_Dust Control | Traditional Shallow Flood | Managed Vegetation Phase 7a, 9 and 10 | 2.712 | 0.22 | 6.38 | 2.3525
5 | 2031 | 2035 | 5 | Brine with BACM Backup | 22 | 0.68035 | DWM_Jan | Dynamic Water Management - JAN | DWM_Jan | Traditional Shallow Flood | Gravel | 6.225 | 0.05 | 1.45 | 0.23293
|  |  |  | Tillage with BACM Backup | 1 | 1.4864 | DWM_Oct | Dynamic Water Management - OCT | DWM_Oct | Traditional Shallow Flood | Brine with BACM Backup | 3.41 | 0.08 | 2.32 | 0.68035
|  |  |  | Channel Areas Reduced MDCE BACM | 10 | 0.1124 | DWM_Plovers | Dynamic Water Management - Plovers | DWM_Plovers | Traditional Shallow Flood | Tillage with BACM Backup | 1.951 | 0.1 | 2.9 | 1.4864
|  |  |  | Sand Fences | 15 | 0.59794 | DWM_Spring_only | Dynamic Water Management - Spring Plovers | DWM_Spring_only | Traditional Shallow Flood | Channel Areas Reduced MDCE BACM | 0.516 | 0.002 | 0.058 | 0.1124
|  |  |  | Habitat DCM | 35 | 0.53075 | ENV | Enhanced native vegetation | ENV | Channel Areas Reduced MDCE BACM | Sand Fences | 0.388 | 0.008 | 0.232 | 0.59794
|  |  |  | see O&M calculations at end of sheet ------> |  |  | Gravel | Gravel | GR | Gravel | Habitat DCM | 2.732 | 0.05 | 1.45 | 0.53075
|  |  |  | capital, om and replacement costs in $ million / square mile |  |  | Meadow | Meadow | Meadow | Managed Vegetation Phase 7a, 9 and 10 | Total | 48.843 | 1 | 29
|  |  |  | lifespan in years |  |  | MSB | Shorebirds | MSB | Habitat DCM
[7 empty] | MSB and SNPL | Shorebirds Plus | MSB and SNPL | Habitat DCM
|  |  |  | Cell Color-Coding |  |  | MSB and SNPL_gravel | Shorebirds Plus | MSB and SNPL_gravel | Habitat DCM
|  |  |  | User input (workbook will update automatically) |  |  | MSB and SNPL_gravel_MWF | Shorebirds Plus | MSB and SNPL_gravel_MWF | Habitat DCM
|  |  |  | Workbook formula calculation |  |  | MWF | Migratory Waterfowl | MWF | Habitat DCM
[7 empty] | MWF and MSB | Migratory Waterfowl Plus | MWF and MSB | Habitat DCM
[7 empty] | MWF and SNPL | Migratory Waterfowl Plus | MWF and SNPL | Habitat DCM
[7 empty] | MWF and SNPL_with gravel | Migratory Waterfowl Plus | MWF and SNPL_with gravel | Habitat DCM
[7 empty] | None | No DCM | None | None
[7 empty] | Sand Fences | Sand Fences | SAF | Sand Fences
[7 empty] | SFL | Shallow Flood Lateral | SFL | Sprinkler Shallow Flood
[7 empty] | SFLS | Shallow Flood Lateral with shoulder | SFLS | Sprinkler Shallow Flood
[7 empty] | SFP | Shallow Flood Pond | SFP | Traditional Shallow Flood
[7 empty] | SNPL_realistic | Snowy Plover | SNPL_realistic | Habitat DCM
[7 empty] | SNPL_with gravel | Snowy Plover w/ Gravel | SNPL_with gravel | Habitat DCM
[7 empty] | Tillage | Tillage | TL | Tillage with BACM Backup
[7 empty] | Till-Brine | Till-Brine | TB | Tillage with BACM Backup
[7 empty] | Veg 08 | Managed Vegetation (2008) | MV | Managed Vegetation Farm
[7 empty] | Veg 11 | Managed Vegetation (2011) | MVN | Managed Vegetation Phase 7a, 9 and 10
[7 empty] | T16 Unique | As-Built Habitat Area | T16U | Habitat DCM
[7 empty] | T1A-2 Unique | As-Built Habitat Area | T1A-2U | Habitat DCM
[7 empty] | T28N Unique | As-Built Habitat Area | T28NU | Habitat DCM
[7 empty] | T28S Unique | As-Built Habitat Area | T28SU | Habitat DCM
[7 empty] | T30-1 Unique | As-Built Habitat Area | T30-1U | Habitat DCM
[7 empty] | T32-1 Unique | As-Built Habitat Area | T32-1U | Habitat DCM
[7 empty] | T36-1W Unique | As-Built Habitat Area | T36-1WU | Habitat DCM
[7 empty] | T36-1E Unique | As-Built Habitat Area | T36-1EU | Habitat DCM
[7 empty] | Brine (DWM) | Brine | Brine | Brine with BACM Backup
[7 empty] | SFL (DWM) | Shallow Flood Lateral | SFL | Sprinkler Shallow Flood
[7 empty] | SFP (DWM) | Shallow Flood Pond | SFP | Traditional Shallow Flood

## Area Summary
Total Area under SIP DCM and MP Habitat (square miles).
| FY | 2024 | 2027 | 2030 | 2033 | 2035
SIP DCM | Thru Step 0 (sq. miles) | Thru Step 1 (sq. miles) | Thru Step 2 (sq. miles) | Thru Step 3 (sq. miles) | Thru Step 4 (sq. miles) | Full Master Project (sq. miles) | User input (analysis script must be run to update calculations)
Workbook formula calculation
Brine with BACM Backup | 3.41 | 3.41 | 4.002 | 4.574 | 4.574 | 4.574 | Analysis script output
Channel Areas Reduced MDCE BACM | 0.516 | 0.516 | 0.516 | 0.516 | 0.516 | 0.516
Gravel | 6.225 | 8.056 | 8.621 | 8.621 | 8.892 | 8.892
Habitat DCM | 2.732 | 3.885 | 5.711 | 8.054 | 9.888 | 11.709
Managed Vegetation Farm | 3.536 | 3.315 | 1.566 | 0.879 | 0.879 | 0.879
Managed Vegetation Phase 7a, 9 and 10 | 2.712 | 2.712 | 2.712 | 2.598 | 2.598 | 2.598
Sand Fences | 0.388 | 0.388 | 0.388 | 0.388 | 0.388 | 0.388
Sprinkler Shallow Flood | 11.767 | 10.976 | 8.54 | 7.936 | 6.712 | 5.382
Tillage with BACM Backup | 1.951 | 2.332 | 3.611 | 5.748 | 6.74 | 8.069
Traditional Shallow Flood | 15.606 | 13.253 | 13.204 | 9.555 | 7.685 | 5.864
total | 48.87 | 48.87 | 48.87 | 48.87 | 48.87 | 48.87
Construction Cost Per Step ($Millions)
| Step 0 ($M) | Step 1 ($M) | Step 2 ($M) | Step 3 ($M) | Step 4 ($M) | Step 5 ($M)
Brine with BACM Backup | - | 0 | 13.024 | 12.584 | 0 | 0
Channel Areas Reduced MDCE BACM | - | 0 | 0 | 0 | 0 | 0
Gravel | - | 67.747 | 20.905 | 0 | 10.027 | 0
Habitat DCM | - | 40.355 | 63.91 | 82.005 | 64.19 | 63.735
Managed Vegetation Farm | - | 0 | 0 | 0 | 0 | 0
Managed Vegetation Phase 7a, 9 and 10 | - | 0 | 0 | 0 | 0 | 0
Sand Fences | - | 0 | 0 | 0 | 0 | 0
Sprinkler Shallow Flood | - | 0 | 0 | 0 | 0 | 0
Tillage with BACM Backup | - | 0.381 | 1.279 | 2.137 | 0.992 | 1.329
Traditional Shallow Flood | - | 0 | 0 | 0 | 0 | 0
Total Construction Cost ($Millions) |  | 108.483 | 99.118 | 96.726 | 75.209 | 65.064
MP O&M Change ($Millions/year)
| Step 0 ($M/y) | Step 1 ($M/y) | Step 2 ($M/y) | Step 3 ($M/y) | Step 4 ($M/y) | Step 5 ($M/y)
Brine with BACM Backup | 0 | 0 | 0.40277 | 0.38916 | 0 | 0
Channel Areas Reduced MDCE BACM | 0 | 0 | 0 | 0 | 0 | 0
Gravel | 0 | 0.4265 | 0.13161 | 0 | 0.063124 | 0
Habitat DCM | 0 | 0.61195 | 0.96914 | 1.2435 | 0.97339 | 0.96649
Managed Vegetation Farm | 0 | -0.3625 | -2.8688 | -1.1269 | 0 | 0
Managed Vegetation Phase 7a, 9 and 10 | 0 | 0 | 0 | -0.26819 | 0 | 0
Sand Fences | 0 | 0 | 0 | 0 | 0 | 0
Sprinkler Shallow Flood | 0 | -0.27292 | -0.8405 | -0.2084 | -0.42232 | -0.45889
Tillage with BACM Backup | 0 | 0.56632 | 1.9011 | 3.1765 | 1.4745 | 1.9754
Traditional Shallow Flood | 0 | -0.65587 | -0.013658 | -1.0171 | -0.52124 | -0.50758
MP Areas New O&M (Total) ($M/y) | 0 | 1.6048 | 3.4046 | 4.8092 | 2.511 | 2.9419
Lakewide Net O&M Change ($M/y) | 0 | 0.31348 | -0.31835 | 2.1886 | 1.5675 | 1.9755
O&M Breakdown by Step
| Step 0 ($M/y) | Step 1 ($M/y) | Step 2 ($M/y) | Step 3 ($M/y) | Step 4 ($M/y) | Step 5 ($M/y)
MP Owned O&M (by step) | 0 | 1.6048 | 3.4046 | 4.8092 | 2.511 | 2.9419
MP Owned O&M (cumulative) | 0 | 1.6048 | 5.0094 | 9.8186 | 12.3296 | 15.2716
Outside MP O&M | 29 | 27.7087 | 23.9857 | 21.3651 | 20.4216 | 19.4551
Total | 29 | 29.3135 | 28.9951 | 31.1837 | 32.7512 | 34.7267

## Step Analysis
Projected Costs and Revenues Through Step | [7 empty] | 1
User Input |  |  | Scenario Assumptions
Sheet Calculation |  |  |  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
Payoff Year | 2018 NPV Benefit ($Million) | $/AF for Water Saved during Project Lifespan | Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft) | [12 empty] | Water rates from email from J. Valenzuela, July 9, 2018.
2021 | 354.3087 | 675.4201 | 2020 | 2020 | 2020 | 4.25% | 2.9% | 3% | 4% | 0% | 30 | 5% | No | 475 | 15 | Untreated | 5% | Yes | 73
|  | Projected Annual Cost 2020 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$242.422) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$596.731) | [5 empty] | LADWP Rate of Return | [5 empty] | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Project Lifespan | FYE | Total Capital | MP-Owned O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  |  | Year | Tier 1 Untreated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
TRUE | 2020 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 59619.0552 | 0 | 5000 | 695 | 3.475 | 3.475 | 0 | 0 | 0 | 0 |  |  | 2018 | 0 | 2018 |  | 1015 | 695 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
TRUE | 2021 | 3.8188 | 0 | 0.365 | 3.9295 | 0 | 0.3796 | 3.9295 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 4.3091 | 5.8091 | 59619.0552 | 5000 | 10000 | 776 | 7.76 | 11.235 | 3.4509 | 5.4259 | 2021 | 361.7263 |  |  | 2019 | 0 | 2019 |  | 1095 | 776 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
TRUE | 2022 | 22.7439 | 0 | 0.365 | 24.0822 | 0 | 0.39478 | 24.0822 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 24.477 | 30.2861 | 59619.0552 | 5000 | 10000 | 838 | 8.38 | 19.615 | -16.097 | -10.6711 | 0 | 426.8428 |  |  | 2020 | 0 | 2020 |  | 1161 | 838 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
TRUE | 2023 | 105.2758 | 0 | 0.657 | 114.703 | 0 | 0.73904 | 114.703 | 0 | 0.73904 | 0 | 0 | 0 | 0 | 0 | 115.442 | 145.7281 | 59619.0552 | 9000 | 14000 | 919 | 12.866 | 32.481 | -102.576 | -113.2471 | 0 | 2903.7717 |  |  | 2021 | 0 | 2021 |  | 1242 | 919 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
TRUE | 2024 | 44.0253 | 0 | 0.657 | 49.3588 | 0 | 0.7686 | 49.3588 | 0 | 0.7686 | 0 | 0 | 0 | 0 | 0 | 50.1273 | 195.8554 | 59619.0552 | 9000 | 14000 | 993 | 13.902 | 46.383 | -36.2253 | -149.4724 | 0 | 2820.2348 |  |  | 2022 | 0 | 2022 |  | 1316 | 993 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
TRUE | 2025 | 0 | 1.6048 | 0.657 | 0 | 1.8604 | 0.79934 | 0 | 1.8604 | 0.79934 | 0 | 0 | 0 | 0 | 0 | 2.6597 | 198.5152 | 59692.4344 | 9000 | 13926.6207 | 1049 | 14.609 | 60.992 | 11.9493 | -137.5231 | 0 | 2054.8346 |  |  | 2023 | 0 | 2023 |  | 1372 | 1049 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
TRUE | 2026 | 0 | 1.6048 | 0.657 | 0 | 1.9162 | 0.83131 | 0 | 1.9162 | 0.83131 | 0 | 0 | 0 | 0 | 0 | 2.7475 | 201.2627 | 59692.4344 | 9000 | 13926.6207 | 1143 | 15.9181 | 76.9102 | 13.1706 | -124.3525 | 0 | 1538.0027 |  |  | 2024 | 0 | 2024 |  | 1466 | 1143 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
TRUE | 2027 | 0 | 1.6048 | 0.657 | 0 | 1.9737 | 0.86457 | 0 | 1.9737 | 0.86457 | 0 | 0 | 0 | 0 | 0 | 2.8382 | 204.1009 | 59692.4344 | 9000 | 13926.6207 | 1222 | 17.0183 | 93.9285 | 14.1801 | -110.1724 | 0 | 1162.4032 |  |  | 2025 | 0 | 2025 |  | 1545 | 1222 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
TRUE | 2028 | 0 | 1.6048 | 0.657 | 0 | 2.0329 | 0.89915 | 0 | 2.0329 | 0.89915 | 0 | 0 | 0 | 0 | 0 | 2.932 | 207.0329 | 59692.4344 | 9000 | 13926.6207 | 1265 | 17.6172 | 111.5457 | 14.6851 | -95.4873 | 0 | 878.3953 |  |  | 2026 | 0 | 2026 |  | 1588 | 1265 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
TRUE | 2029 | 0 | 1.6048 | 0.657 | 0 | 2.0939 | 0.93512 | 0 | 2.0939 | 0.93512 | 0 | 0 | 0 | 0 | 0 | 3.029 | 210.0619 | 59692.4344 | 9000 | 13926.6207 | 1382 | 19.2466 | 130.7922 | 16.2176 | -79.2697 | 0 | 646.3969 |  |  | 2027 | 0 | 2027 |  | 1705 | 1382 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
TRUE | 2030 | 0 | 1.6048 | 0.657 | 0 | 2.1567 | 0.97252 | 0 | 2.1567 | 0.97252 | 0 | 0 | 0 | 0 | 0 | 3.1292 | 213.1911 | 59692.4344 | 9000 | 13926.6207 | 1464 | 20.3886 | 151.1808 | 17.2594 | -62.0103 | 0 | 454.0891 |  |  | 2028 | 0 | 2028 |  | 1787 | 1464 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
TRUE | 2031 | 0 | 1.6048 | 0.657 | 0 | 2.2214 | 1.0114 | 0 | 2.2214 | 1.0114 | 0 | 0 | 0 | 0 | 0 | 3.2328 | 216.4239 | 59692.4344 | 9000 | 13926.6207 | 1518 | 21.1406 | 172.3214 | 17.9078 | -44.1025 | 0 | 293.0663 |  |  | 2029 | 0 | 2029 |  | 1858 | 1518 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
TRUE | 2032 | 0 | 1.6048 | 0.657 | 0 | 2.288 | 1.0519 | 0 | 2.288 | 1.0519 | 0 | 0 | 0 | 0 | 0 | 3.3399 | 219.7638 | 59692.4344 | 9000 | 13926.6207 | 1674 | 23.3132 | 195.6346 | 19.9733 | -24.1292 | 0 | 146.7598 |  |  | 2030 | 0 | 2030 |  | 2030 | 1674 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
TRUE | 2033 | 0 | 1.6048 | 0.657 | 0 | 2.3567 | 1.094 | 0 | 2.3567 | 1.094 | 0 | 0 | 0 | 0 | 0 | 3.4506 | 223.2144 | 59692.4344 | 9000 | 13926.6207 | 1784 | 24.8451 | 220.4797 | 21.3945 | -2.7347 | 0 | 15.3345 |  |  | 2031 | 0 | 2031 |  | 2158 | 1784 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
TRUE | 2034 | 0 | 1.6048 | 0.657 | 0 | 2.4274 | 1.1377 | 0 | 2.4274 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 3.5651 | 226.7795 | 59692.4344 | 9000 | 13926.6207 | 1834 | 25.5414 | 246.0211 | 21.9763 | 19.2416 | 0 | 100.0779 |  |  | 2032 | 0 | 2032 |  | 2226 | 1834 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
TRUE | 2035 | 0 | 1.6048 | 0.657 | 0 | 2.5002 | 1.1832 | 0 | 2.5002 | 1.1832 | 0 | 0 | 0 | 0 | 0 | 3.6834 | 230.4629 | 59692.4344 | 9000 | 13926.6207 | 2051 | 28.5635 | 274.5846 | 24.8801 | 44.1217 | 0 | 213.9827 |  |  | 2033 | 0 | 2033 |  | 2463 | 2051 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
TRUE | 2036 | 0 | 1.6048 | 0.657 | 0 | 2.5752 | 1.2305 | 0 | 2.5752 | 1.2305 | 0 | 0 | 0 | 0 | 0 | 3.8057 | 234.2687 | 59692.4344 | 9000 | 13926.6207 | 2109 | 29.3712 | 303.9559 | 25.5655 | 69.6872 | 0 | 316.5881 |  |  | 2034 | 0 | 2034 |  | 2542 | 2109 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
TRUE | 2037 | 0 | 1.6048 | 0.657 | 0 | 2.6524 | 1.2798 | 0 | 2.6524 | 1.2798 | 0 | 0 | 0 | 0 | 0 | 3.9322 | 238.2009 | 59692.4344 | 9000 | 13926.6207 | 2100 | 29.2459 | 333.2018 | 25.3137 | 95.0009 | 0 | 405.9068 |  |  | 2035 | 0 | 2035 |  | 2554 | 2100 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
TRUE | 2038 | 0 | 1.6048 | 0.657 | 0 | 2.732 | 1.331 | 0 | 2.732 | 1.331 | 0 | 0 | 0 | 0 | 0 | 4.063 | 242.2639 | 59692.4344 | 9000 | 13926.6207 | 2236 | 31.1399 | 364.3417 | 27.0769 | 122.0778 | 0 | 492.3035 |  |  | 2036 | 0 | 2036 |  | 2714 | 2236 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
TRUE | 2039 | 0 | 1.6048 | 0.657 | 0 | 2.814 | 1.3842 | 0 | 2.814 | 1.3842 | 0 | 0 | 0 | 0 | 0 | 4.1982 | 246.462 | 59692.4344 | 9000 | 13926.6207 | 2305 | 32.1009 | 396.4425 | 27.9027 | 149.9805 | 0 | 572.6648 |  |  | 2037 | 0 | 2037 |  | 2807 | 2305 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
TRUE | 2040 | 0 | 1.6048 | 0.657 | 0 | 2.8984 | 1.4396 | 0 | 2.8984 | 1.4396 | 0 | 0 | 0 | 0 | 0 | 4.338 | 250.8 | 59692.4344 | 9000 | 13926.6207 | 2308 | 32.1426 | 428.5852 | 27.8047 | 177.7852 | 0 | 644.5557 |  |  | 2038 | 0 | 2038 |  | 2835 | 2308 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
TRUE | 2041 | 0 | 1.6048 | 0.657 | 0 | 2.9854 | 1.4972 | 0 | 2.9854 | 1.4972 | 0 | 0 | 0 | 0 | 0 | 4.4825 | 255.2825 | 59692.4344 | 9000 | 13926.6207 | 2423.4 | 33.7498 | 462.335 | 29.2673 | 207.0524 | 0 | 714.5837 |  |  | 2039 | 0 | 2039 | 5% | 2976.75 | 2423.4 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
TRUE | 2042 | 0 | 1.6048 | 0.657 | 0 | 3.0749 | 1.557 | 0 | 3.0749 | 1.557 | 0 | 0 | 0 | 0 | 0 | 4.6319 | 259.9145 | 59692.4344 | 9000 | 13926.6207 | 2544.57 | 35.4373 | 497.7722 | 30.8053 | 237.8578 | 0 | 783.2534 |  |  | 2040 | 0 | 2040 | 5% | 3125.5875 | 2544.57 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
TRUE | 2043 | 0 | 1.6048 | 0.657 | 0 | 3.1672 | 1.6193 | 0 | 3.1672 | 1.6193 | 0 | 0 | 0 | 0 | 0 | 4.7865 | 264.7009 | 59692.4344 | 9000 | 13926.6207 | 2671.7985 | 37.2091 | 534.9813 | 32.4226 | 270.2804 | 0 | 850.9933 |  |  | 2041 | 0 | 2041 | 5% | 3281.8669 | 2671.7985 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
TRUE | 2044 | 0 | 1.6048 | 0.657 | 0 | 3.2622 | 1.6841 | 0 | 3.2622 | 1.6841 | 0 | 0 | 0 | 0 | 0 | 4.9463 | 269.6472 | 59692.4344 | 9000 | 13926.6207 | 2805.3884 | 39.0696 | 574.0509 | 34.1233 | 304.4037 | 0 | 918.1718 |  |  | 2042 | 0 | 2042 | 5% | 3445.9602 | 2805.3884 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
TRUE | 2045 | 0 | 1.6048 | 0.657 | 0 | 3.36 | 1.7515 | 0 | 3.36 | 1.7515 | 0 | 0 | 0 | 0 | 0 | 5.1115 | 274.7587 | 59692.4344 | 9000 | 13926.6207 | 2945.6578 | 41.0231 | 615.074 | 35.9116 | 340.3153 | 0 | 985.1104 |  |  | 2043 | 0 | 2043 | 5% | 3618.2582 | 2945.6578 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
TRUE | 2046 | 0 | 1.6048 | 0.657 | 0 | 3.4608 | 1.8215 | 0 | 3.4608 | 1.8215 | 0 | 0 | 0 | 0 | 0 | 5.2824 | 280.041 | 59692.4344 | 9000 | 13926.6207 | 3092.9407 | 43.0742 | 658.1482 | 37.7919 | 378.1071 | 0 | 1052.093 |  |  | 2044 | 0 | 2044 | 5% | 3799.1711 | 3092.9407 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
TRUE | 2047 | 0 | 1.6048 | 0.657 | 0 | 3.5647 | 1.8944 | 0 | 3.5647 | 1.8944 | 0 | 0 | 0 | 0 | 0 | 5.459 | 285.5001 | 59692.4344 | 9000 | 13926.6207 | 3247.5878 | 45.2279 | 703.3761 | 39.7689 | 417.876 | 0 | 1119.3739 |  |  | 2045 | 0 | 2045 | 5% | 3989.1297 | 3247.5878 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
TRUE | 2048 | 0 | 1.6048 | 0.657 | 0 | 3.6716 | 1.9701 | 0 | 3.6716 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 5.6418 | 291.1418 | 59692.4344 | 9000 | 13926.6207 | 3409.9672 | 47.4893 | 750.8654 | 41.8476 | 459.7236 | 0 | 1187.1834 |  |  | 2046 | 0 | 2046 | 5% | 4188.5862 | 3409.9672 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
TRUE | 2049 | 0 | 1.6048 | 0.657 | 0 | 3.7818 | 2.049 | 0 | 3.7818 | 2.049 | 0 | 0 | 0 | 0 | 0 | 5.8307 | 296.9725 | 59692.4344 | 9000 | 13926.6207 | 3580.4655 | 49.8638 | 800.7292 | 44.0331 | 503.7567 | 0 | 1255.7327 |  |  | 2047 | 0 | 2047 | 5% | 4398.0155 | 3580.4655 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
TRUE | 2050 | 0 | 1.6048 | 0.657 | 0 | 3.8952 | 2.1309 | 0 | 3.8952 | 2.1309 | 0 | 0 | 0 | 0 | 0 | 6.0261 | 302.9987 | 59692.4344 | 9000 | 13926.6207 | 3759.4888 | 52.357 | 853.0862 | 46.3309 | 550.0875 | 0 | 1325.2179 |  |  | 2048 | 0 | 2048 | 5% | 4617.9163 | 3759.4888 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
TRUE | 2051 | 0 | 1.6048 | 0.657 | 0 | 4.0121 | 2.2161 | 0 | 4.0121 | 2.2161 | 0 | 0 | 0 | 0 | 0 | 6.2282 | 309.2269 | 59692.4344 | 9000 | 13926.6207 | 3947.4632 | 54.9748 | 908.061 | 48.7466 | 598.8341 | 0 | 1395.8227 |  |  | 2049 | 0 | 2049 | 5% | 4848.8121 | 3947.4632 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
TRUE | 2052 | 0 | 1.6048 | 0.657 | 0 | 4.1324 | 2.3048 | 0 | 4.1324 | 2.3048 | 0 | 0 | 0 | 0 | 0 | 6.4372 | 315.6641 | 59692.4344 | 9000 | 13926.6207 | 4144.8364 | 57.7236 | 965.7846 | 51.2863 | 650.1205 | 0 | 1467.7215 |  |  | 2050 | 0 | 2050 | 5% | 5091.2527 | 4144.8364 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
TRUE | 2053 | 0 | 1.6048 | 0.657 | 0 | 4.2564 | 2.397 | 0 | 4.2564 | 2.397 | 0 | 0 | 0 | 0 | 0 | 6.6534 | 322.3175 | 59692.4344 | 9000 | 13926.6207 | 4352.0782 | 60.6097 | 1026.3943 | 53.9564 | 704.0768 | 0 | 1541.0812 |  |  | 2051 | 0 | 2051 | 5% | 5345.8153 | 4352.0782 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
TRUE | 2054 | 0 | 1.6048 | 0.657 | 0 | 4.3841 | 2.4929 | 0 | 4.3841 | 2.4929 | 0 | 0 | 0 | 0 | 0 | 6.877 | 329.1944 | 59692.4344 | 9000 | 13926.6207 | 4569.6821 | 63.6402 | 1090.0346 | 56.7633 | 760.8401 | 0 | 1616.0627 |  |  | 2052 | 0 | 2052 | 5% | 5613.1061 | 4569.6821 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
TRUE | 2055 | 0 | 1.6048 | 0.657 | 0 | 4.5156 | 2.5926 | 0 | 4.5156 | 2.5926 | 0 | 0 | 0 | 0 | 0 | 7.1082 | 336.3026 | 59692.4344 | 9000 | 13926.6207 | 4798.1662 | 66.8222 | 1156.8568 | 59.714 | 820.5542 | 0 | 1692.8232 |  |  | 2053 | 0 | 2053 | 5% | 5893.7614 | 4798.1662 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
TRUE | 2056 | 0 | 1.6048 | 0.657 | 0 | 4.6511 | 2.6963 | 0 | 4.6511 | 2.6963 | 0 | 0 | 0 | 0 | 0 | 7.3474 | 343.65 | 59692.4344 | 9000 | 13926.6207 | 5038.0745 | 70.1634 | 1227.0201 | 62.816 | 883.3701 | 0 | 1771.5168 |  |  | 2054 | 0 | 2054 | 5% | 6188.4495 | 5038.0745 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
TRUE | 2057 | 0 | 1.6048 | 0.657 | 0 | 4.7906 | 2.8041 | 0 | 4.7906 | 2.8041 | 0 | 0 | 0 | 0 | 0 | 7.5947 | 351.2448 | 59692.4344 | 9000 | 13926.6207 | 5289.9783 | 73.6715 | 1300.6917 | 66.0768 | 949.4469 | 0 | 1852.2957 |  |  | 2055 | 0 | 2055 | 5% | 6497.8719 | 5289.9783 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
TRUE | 2058 | 0 | 1.6048 | 0.657 | 0 | 4.9343 | 2.9163 | 0 | 4.9343 | 2.9163 | 0 | 0 | 0 | 0 | 0 | 7.8506 | 359.0954 | 59692.4344 | 9000 | 13926.6207 | 5554.4772 | 77.3551 | 1378.0468 | 69.5045 | 1018.9514 | 0 | 1935.3115 |  |  | 2056 | 0 | 2056 | 5% | 6822.7655 | 5554.4772 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
TRUE | 2059 | 0 | 1.6048 | 0.657 | 0 | 5.0824 | 3.033 | 0 | 5.0824 | 3.033 | 0 | 0 | 0 | 0 | 0 | 8.1153 | 367.2107 | 59692.4344 | 9000 | 13926.6207 | 5832.2011 | 81.2229 | 1459.2696 | 73.1075 | 1092.0589 | 0 | 2020.7158 |  |  | 2057 | 0 | 2057 | 5% | 7163.9038 | 5832.2011 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
TRUE | 2060 | 0 | 1.6048 | 0.657 | 0 | 5.2348 | 3.1543 | 0 | 5.2348 | 3.1543 | 0 | 0 | 0 | 0 | 0 | 8.3891 | 375.5998 | 59692.4344 | 9000 | 13926.6207 | 6123.8111 | 85.284 | 1544.5536 | 76.8949 | 1168.9538 | 0 | 2108.661 |  |  | 2058 | 0 | 2058 | 5% | 7522.099 | 6123.8111 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
TRUE | 2061 | 0 | 1.6048 | 0.657 | 0 | 5.3919 | 3.2804 | 0 | 5.3919 | 3.2804 | 0 | 0 | 0 | 0 | 0 | 8.6723 | 384.2721 | 59692.4344 | 9000 | 13926.6207 | 6430.0017 | 89.5482 | 1634.1018 | 80.8759 | 1249.8297 | 0 | 2199.301 |  |  | 2059 | 0 | 2059 | 5% | 7898.2039 | 6430.0017 | 2061 | 0 | 2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061 | 0 | 2061 | 0 | 0
TRUE | 2062 | 0 | 1.6048 | 0.657 | 0 | 5.5536 | 3.4117 | 0 | 5.5536 | 3.4117 | 0 | 0 | 0 | 0 | 0 | 8.9653 | 393.2374 | 59692.4344 | 9000 | 13926.6207 | 6751.5017 | 94.0256 | 1728.1274 | 85.0603 | 1334.89 | 0 | 2292.7919 |  |  | 2060 | 0 | 2060 | 5% | 8293.1141 | 6751.5017
[15 empty] | Total Cost (NPV, $Millions) | 242.422 |  |  | Total Water Saved (acre-ft) | 582211.5874 |  |  | Total Revenue (NPV) | 596.7307 | IRR | 12.51% |  | $/AF at Life of Project | 675.4201
[28 empty] | 2018 NPV Benefit | 354.3087
Note on F8: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L8: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT8: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S11: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.