## 10 YEAR PROJECTION
| Project |  |  | Project Phase | COST PER YEAR
|  |  | CE |  | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | Total
| OL Phase 7a | [21 empty] | 0
| Total Cost: | 244361824 | 30 | Construction | COST PER YEAR 15/16: 61090456 | 61090456
| Sq. Miles: | 6.03 | 37 | Design | COST PER YEAR 15/16: 6109045.6 | 6109045.6
|  |  | 37 | Construction Management | COST PER YEAR 15/16: 3054522.8 | 3054522.8
0
| SUBTOTAL BY FISCAL YEAR |  |  |  | 70254024.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 70254024.4
| OL Phase 9/10 |  | 10 |  | COST PER YEAR 17/18: 408700 | 408700
| Total Cost: | 266654276.31 | 30 | Construction | COST PER YEAR 15/16: 72580747; COST PER YEAR 16/17: 108695109; COST PER YEAR 17/18: 60000000 | 241275856
| Sq. Miles: | 5.395 | 37 | Design | COST PER YEAR 16/17: 3619215 | 3619215
| Comment: |  | 37 | Construction Management | COST PER YEAR 15/16: 1889354.31; COST PER YEAR 16/17: 11561151; COST PER YEAR 17/18: 6000000 | 19450505.31
|  |  | 41 | Materials | COST PER YEAR 16/17: 1700000; COST PER YEAR 17/18: 200000 | 1900000
| SUBTOTAL BY FISCAL YEAR |  |  |  | 74470101.31 | 125575475 | 66608700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 266654276.31
| OL Emergency Project |  | 10 |  | COST PER YEAR 17/18: 200000; COST PER YEAR 18/19: 500000 | 700000
| Total Cost: | 35270000 | 30 | Construction | COST PER YEAR 17/18: 15000000; COST PER YEAR 18/19: 8000000 | 23000000
| Sq. Miles: |  | 37 | Design | COST PER YEAR 17/18: 1400000; COST PER YEAR 18/19: 1770000 | 3170000
| Comment: |  | 37 | Construction Management | COST PER YEAR 17/18: 2800000; COST PER YEAR 18/19: 2200000 | 5000000
|  |  | 37 | Science | COST PER YEAR 17/18: 1050000; COST PER YEAR 18/19: 2350000 | 3400000
| SUBTOTAL BY FISCAL YEAR |  |  |  | 0 | 0 | 20450000 | 14820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 35270000
MASTER PROJECT
| Master Project 1 |  | 10 | Labor | COST PER YEAR 17/18: 500000; COST PER YEAR 18/19: 1000000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 500000 | 3500000
| Estimated Construction Cost: | 0 | 37 | Planning | COST PER YEAR 17/18: 1000000; COST PER YEAR 18/19: 1000000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 500000 | 3500000
| Sq. Miles: | 0 | 30 | Construction | COST PER YEAR 19/20: 0; COST PER YEAR 20/21: 0; COST PER YEAR 21/22: 0 | 0
| Comment: |  | 37 | Design | COST PER YEAR 18/19: 0; COST PER YEAR 19/20: 0; COST PER YEAR 20/21: 0; COST PER YEAR 21/22: 0 | 0
|  |  | 37 | Construction Management | COST PER YEAR 19/20: 0; COST PER YEAR 20/21: 0; COST PER YEAR 21/22: 0 | 0
|  |  | 41 | Materials/ Misc | COST PER YEAR 18/19: 300000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 1000000; COST PER YEAR 21/22: 1000000 | 3300000 | 10300000
Sub_Total
| Master Project 2 |  | 10 | Labor | COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 1000000; COST PER YEAR 22/23: 1000000; COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 500000 | 3500000
| Estimated Construction Cost: | 0 | 37 | Planning | COST PER YEAR 20/21: 1000000; COST PER YEAR 21/22: 1000000; COST PER YEAR 22/23: 1000000; COST PER YEAR 23/24: 500000 | 3500000
| Sq. Miles: | 0 | 30 | Construction | COST PER YEAR 22/23: 0; COST PER YEAR 23/24: 0; COST PER YEAR 24/25: 0 | 0
| Comment: |  | 37 | Design | COST PER YEAR 21/22: 0; COST PER YEAR 22/23: 0; COST PER YEAR 23/24: 0; COST PER YEAR 24/25: 0 | 0
|  |  | 37 | Construction Management | COST PER YEAR 22/23: 0; COST PER YEAR 23/24: 0; COST PER YEAR 24/25: 0 | 0
|  |  | 41 | Materials | COST PER YEAR 21/22: 300000; COST PER YEAR 22/23: 1000000; COST PER YEAR 23/24: 1000000; COST PER YEAR 24/25: 1000000 | 3300000 | 10300000
| Master Project 3 |  | 10 | Labor | COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 1000000; COST PER YEAR 25/26: 1000000; COST PER YEAR 26/27: 500000; COST PER YEAR 27/28: 500000 | 3500000
| Estimated Construction Cost: | 0 | 37 | Planning | COST PER YEAR 23/24: 1000000; COST PER YEAR 24/25: 1000000; COST PER YEAR 25/26: 1000000; COST PER YEAR 26/27: 500000 | 3500000
| Sq. Miles: | 0 | 30 | Construction | COST PER YEAR 25/26: 0; COST PER YEAR 26/27: 0; COST PER YEAR 27/28: 0 | 0
| Comment: |  | 37 | Design | COST PER YEAR 24/25: 0; COST PER YEAR 25/26: 0; COST PER YEAR 26/27: 0; COST PER YEAR 27/28: 0 | 0
|  |  | 37 | Construction Management | COST PER YEAR 25/26: 0; COST PER YEAR 26/27: 0; COST PER YEAR 27/28: 0 | 0
|  |  | 41 | Materials | COST PER YEAR 24/25: 300000; COST PER YEAR 25/26: 1000000; COST PER YEAR 26/27: 1000000; COST PER YEAR 27/28: 1000000 | 3300000 | 10300000
| Master Project 4 |  | 10 | Labor | COST PER YEAR 26/27: 500000; COST PER YEAR 27/28: 1000000; COST PER YEAR 28/29: 1000000; COST PER YEAR 29/30: 500000; COST PER YEAR 30/31: 500000 | 3500000
| Estimated Construction Cost: | 0 | 37 | Planning | COST PER YEAR 26/27: 1000000; COST PER YEAR 27/28: 1000000; COST PER YEAR 28/29: 1000000; COST PER YEAR 29/30: 500000 | 3500000
| Sq. Miles: | 0 | 30 | Construction | COST PER YEAR 28/29: 0; COST PER YEAR 29/30: 0; COST PER YEAR 30/31: 0 | 0
| Comment: |  | 37 | Design | COST PER YEAR 27/28: 0; COST PER YEAR 28/29: 0; COST PER YEAR 29/30: 0; COST PER YEAR 30/31: 0 | 0
|  |  | 37 | Construction Management | COST PER YEAR 28/29: 0; COST PER YEAR 29/30: 0; COST PER YEAR 30/31: 0 | 0
|  |  | 41 | Materials | COST PER YEAR 27/28: 300000; COST PER YEAR 28/29: 1000000; COST PER YEAR 29/30: 1000000; COST PER YEAR 30/31: 1000000 | 3300000 | 10300000
| Master Project 5 |  | 10 | Labor | COST PER YEAR 28/29: 500000; COST PER YEAR 29/30: 1000000; COST PER YEAR 30/31: 1000000; COST PER YEAR 31/32: 500000; COST PER YEAR 32/33: 500000 | 3500000
| Estimated Construction Cost: | 0 | 37 | Planning | COST PER YEAR 28/29: 1000000; COST PER YEAR 29/30: 1000000; COST PER YEAR 30/31: 1000000; COST PER YEAR 31/32: 500000 | 3500000
| Sq. Miles: | 0 | 30 | Construction | COST PER YEAR 30/31: 0; COST PER YEAR 31/32: 0; COST PER YEAR 32/33: 0 | 0
| Comment: |  | 37 | Design | COST PER YEAR 29/30: 0; COST PER YEAR 30/31: 0; COST PER YEAR 31/32: 0; COST PER YEAR 32/33: 0 | 0
|  |  | 37 | Construction Management | COST PER YEAR 30/31: 0; COST PER YEAR 31/32: 0; COST PER YEAR 32/33: 0 | 0
|  |  | 41 | Materials | COST PER YEAR 29/30: 300000; COST PER YEAR 30/31: 1000000; COST PER YEAR 31/32: 1000000; COST PER YEAR 32/33: 1000000 | 3300000 | 10300000
| SUBTOTAL BY FISCAL YEAR |  |  |  | 0 | 0 | 1500000 | 2300000 | 3000000 | 3500000 | 3800000 | 3000000 | 3500000 | 3800000 | 3000000 | 3500000 | 3800000 | 4500000 | 4300000 | 4500000 | 2000000 | 1500000 | 51500000
| Cumulative Capital Cost Total |  |  |  |  | 0 | 1500000 | 3800000 | 6800000 | 10300000 | 14100000 | 17100000 | 20600000 | 24400000 | 27400000 | 30900000 | 34700000 | 39200000 | 43500000 | 48000000 | 50000000 | 51500000 |  | 51500000
[6 empty] | 10 | 500000 | 1000000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1500000 | 1500000 | 1500000 | 500000 | 500000
[6 empty] | 37 | 1000000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1000000 | 1000000 | 1500000 | 1000000 | 2000000 | 1500000 | 1000000 | 500000 | 0
[6 empty] | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 41 | 0 | 300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1000000 | 1300000 | 1000000 | 1300000 | 2000000 | 1000000 | 1000000
OWENS LAKE EFFECIENCY MEASURES
Jaime | ADDITIONS AND BETTERMENTS |  | 10 | Labor | [18 empty] | 0
|  |  | 30 | Construction | COST PER YEAR 18/19: 5300000; COST PER YEAR 19/20: 9666000; COST PER YEAR 20/21: 9864000; COST PER YEAR 21/22: 10062000; COST PER YEAR 22/23: 5695000; COST PER YEAR 23/24: 9666000 | 50253000
|  |  | 37 | Professional Services
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Jaime | OLSAP |  | 10 | Labor | COST PER YEAR 17/18: 150000; COST PER YEAR 18/19: 150000; COST PER YEAR 19/20: 150000; COST PER YEAR 20/21: 150000; COST PER YEAR 21/22: 150000; COST PER YEAR 22/23: 150000; COST PER YEAR 23/24: 150000; COST PER YEAR 24/25: 150000; COST PER YEAR 25/26: 150000; COST PER YEAR 26/27: 150000 | 1500000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | [18 empty] | 0
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Saeed | Groundwater Well Drilling & Data Gathering |  | 10 | Labor | COST PER YEAR 17/18: 243000; COST PER YEAR 18/19: 248000; COST PER YEAR 19/20: 253000; COST PER YEAR 20/21: 258000 | 1002000
|  |  | 30 | Construction | COST PER YEAR 17/18: 2640000; COST PER YEAR 19/20: 2255000; COST PER YEAR 20/21: 767000 | 5662000
|  |  | 37 | Professional Services | COST PER YEAR 17/18: 400000; COST PER YEAR 18/19: 400000; COST PER YEAR 19/20: 400000; COST PER YEAR 20/21: 400000 | 1600000
| Comment: |  | 41 | Materials | COST PER YEAR 18/19: 200000; COST PER YEAR 19/20: 100000; COST PER YEAR 20/21: 100000 | 400000
0
Adam | SFWCRFT |  | 10 | Labor | COST PER YEAR 17/18: 200000; COST PER YEAR 18/19: 206000; COST PER YEAR 19/20: 212000; COST PER YEAR 20/21: 218000 | 836000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | COST PER YEAR 17/18: 1100000; COST PER YEAR 18/19: 1100000; COST PER YEAR 19/20: 1100000; COST PER YEAR 20/21: 1100000 | 4400000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Sarah | Regulatory Fines |  | 10 | Labor | COST PER YEAR 17/18: 207000; COST PER YEAR 18/19: 215000; COST PER YEAR 19/20: 222000; COST PER YEAR 20/21: 230000; COST PER YEAR 21/22: 238000; COST PER YEAR 22/23: 246000; COST PER YEAR 23/24: 255000; COST PER YEAR 24/25: 264000; COST PER YEAR 25/26: 273000; COST PER YEAR 26/27: 283000 | 2433000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | COST PER YEAR 17/18: 780000; COST PER YEAR 18/19: 808000; COST PER YEAR 19/20: 836000; COST PER YEAR 20/21: 864000; COST PER YEAR 21/22: 896000; COST PER YEAR 22/23: 927000; COST PER YEAR 23/24: 959000; COST PER YEAR 24/25: 993000; COST PER YEAR 25/26: 1028000; COST PER YEAR 26/27: 1063000 | 9154000
| Comment: |  | 41 | Materials | [18 empty] | 0
|  |  | 99 | Other Direct - Fines | COST PER YEAR 17/18: 6500000; COST PER YEAR 18/19: 6728000; COST PER YEAR 19/20: 6963000; COST PER YEAR 20/21: 7207000; COST PER YEAR 21/22: 7459000; COST PER YEAR 22/23: 7720000; COST PER YEAR 23/24: 7990000; COST PER YEAR 24/25: 8270000; COST PER YEAR 25/26: 8560000; COST PER YEAR 26/27: 8860000 | 76257000
Sarah | T13 |  | 10 | Labor | COST PER YEAR 17/18: 160000; COST PER YEAR 18/19: 166000 | 326000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services-Design | COST PER YEAR 17/18: 130000; COST PER YEAR 18/19: 135000 | 265000
| Comment: |  | 41 | Materials | COST PER YEAR 17/18: 871000 | 871000
0
Adam | T5-1 Add |  | 10 | Labor | COST PER YEAR 17/18: 280000; COST PER YEAR 18/19: 290000 | 570000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services - Design | COST PER YEAR 17/18: 130000; COST PER YEAR 18/19: 135000 | 265000
| Comment: |  | 41 | Materials | COST PER YEAR 17/18: 850000 | 850000
0
Sarah | T17-2 |  | 10 | Labor | COST PER YEAR 17/18: 160000; COST PER YEAR 18/19: 166000 | 326000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services - Design | COST PER YEAR 17/18: 130000; COST PER YEAR 18/19: 135000 | 265000
| Comment: |  | 41 | Materials | COST PER YEAR 17/18: 533000 | 533000
0
Adam/ | Subcommittees |  | 10 | Labor | COST PER YEAR 17/18: 527000; COST PER YEAR 18/19: 545000; COST PER YEAR 19/20: 564000; COST PER YEAR 20/21: 584000; COST PER YEAR 21/22: 604000; COST PER YEAR 22/23: 626000; COST PER YEAR 23/24: 647000; COST PER YEAR 24/25: 670000; COST PER YEAR 25/26: 693000; COST PER YEAR 26/27: 718000 | 6178000
Sarah |  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Profession Srvcs-Science | COST PER YEAR 17/18: 975000; COST PER YEAR 18/19: 1010000; COST PER YEAR 19/20: 1045000; COST PER YEAR 20/21: 1081000; COST PER YEAR 21/22: 1119000; COST PER YEAR 22/23: 1158000; COST PER YEAR 23/24: 1200000; COST PER YEAR 24/25: 1240000; COST PER YEAR 25/26: 1284000; COST PER YEAR 26/27: 1330000 | 11442000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Sarah | Soil Binder Study |  | 10 | Labor | COST PER YEAR 17/18: 162000; COST PER YEAR 18/19: 118000; COST PER YEAR 19/20: 122000; COST PER YEAR 20/21: 126000; COST PER YEAR 21/22: 130000; COST PER YEAR 22/23: 135000 | 793000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Srvcs - Science | COST PER YEAR 17/18: 520000; COST PER YEAR 18/19: 539000; COST PER YEAR 19/20: 558000; COST PER YEAR 20/21: 577000; COST PER YEAR 21/22: 597000; COST PER YEAR 22/23: 618000 | 3409000
| Comment: |  | 41 | Materials | COST PER YEAR 17/18: 208000; COST PER YEAR 19/20: 223000; COST PER YEAR 21/22: 239000 | 670000
0
Paul | GIS and As-Builts |  | 10 | Labor | COST PER YEAR 17/18: 2000000; COST PER YEAR 18/19: 1000000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 500000; COST PER YEAR 22/23: 500000; COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 500000; COST PER YEAR 25/26: 500000; COST PER YEAR 26/27: 500000 | 7500000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | COST PER YEAR 17/18: 2000000; COST PER YEAR 18/19: 1000000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 500000; COST PER YEAR 22/23: 500000; COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 500000; COST PER YEAR 25/26: 500000; COST PER YEAR 26/27: 500000 | 7500000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Sarah | Science Contract |  | 10 | Labor | COST PER YEAR 17/18: 329000; COST PER YEAR 18/19: 341000; COST PER YEAR 19/20: 353000; COST PER YEAR 20/21: 365000; COST PER YEAR 21/22: 378000; COST PER YEAR 22/23: 391000; COST PER YEAR 23/24: 405000; COST PER YEAR 24/25: 419000; COST PER YEAR 25/26: 431000; COST PER YEAR 26/27: 449000 | 3861000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Srvcs - Science | COST PER YEAR 17/18: 6500000; COST PER YEAR 18/19: 6728000; COST PER YEAR 19/20: 6963000; COST PER YEAR 20/21: 7207000; COST PER YEAR 21/22: 7459000; COST PER YEAR 22/23: 7720000; COST PER YEAR 23/24: 7991000; COST PER YEAR 24/25: 8270000; COST PER YEAR 25/26: 8560000; COST PER YEAR 26/27: 8860000 | 76258000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Jaime | Tribal Consultations and Monitoring |  | 10 | Labor | [18 empty] | 0
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | [18 empty] | 0
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Rod | SCADA |  | 10 | Labor | COST PER YEAR 17/18: 500000; COST PER YEAR 18/19: 500000; COST PER YEAR 19/20: 500000; COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 500000; COST PER YEAR 22/23: 500000; COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 500000; COST PER YEAR 25/26: 500000; COST PER YEAR 26/27: 500000 | 5000000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services - Design | COST PER YEAR 17/18: 400000; COST PER YEAR 18/19: 400000; COST PER YEAR 19/20: 400000; COST PER YEAR 20/21: 400000; COST PER YEAR 21/22: 400000; COST PER YEAR 22/23: 400000; COST PER YEAR 23/24: 400000; COST PER YEAR 24/25: 400000; COST PER YEAR 25/26: 400000; COST PER YEAR 26/27: 400000 | 4000000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Rod | Brine Study |  | 10 | Labor | COST PER YEAR 17/18: 400000; COST PER YEAR 18/19: 400000; COST PER YEAR 19/20: 400000; COST PER YEAR 20/21: 400000; COST PER YEAR 21/22: 400000; COST PER YEAR 22/23: 400000; COST PER YEAR 23/24: 400000; COST PER YEAR 24/25: 400000; COST PER YEAR 25/26: 400000; COST PER YEAR 26/27: 400000 | 4000000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services - Design | COST PER YEAR 17/18: 500000; COST PER YEAR 18/19: 500000; COST PER YEAR 19/20: 1000000; COST PER YEAR 20/21: 1000000; COST PER YEAR 21/22: 1000000; COST PER YEAR 22/23: 2000000; COST PER YEAR 23/24: 2000000; COST PER YEAR 24/25: 1000000; COST PER YEAR 25/26: 1000000; COST PER YEAR 26/27: 1000000 | 11000000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Rod | TWB2 Infrastructure |  | 10 | Labor | COST PER YEAR 17/18: 500000; COST PER YEAR 18/19: 500000; COST PER YEAR 19/20: 500000; COST PER YEAR 20/21: 500000; COST PER YEAR 21/22: 500000; COST PER YEAR 22/23: 500000; COST PER YEAR 23/24: 500000; COST PER YEAR 24/25: 500000; COST PER YEAR 25/26: 500000; COST PER YEAR 26/27: 500000 | 5000000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services - Design | COST PER YEAR 17/18: 300000; COST PER YEAR 18/19: 300000; COST PER YEAR 19/20: 300000; COST PER YEAR 20/21: 300000; COST PER YEAR 21/22: 300000; COST PER YEAR 22/23: 300000; COST PER YEAR 23/24: 300000; COST PER YEAR 24/25: 300000; COST PER YEAR 25/26: 300000; COST PER YEAR 26/27: 300000 | 3000000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Rod | Satellite Imagery |  | 10 | Labor | COST PER YEAR 17/18: 200000; COST PER YEAR 18/19: 200000; COST PER YEAR 19/20: 200000; COST PER YEAR 20/21: 200000; COST PER YEAR 21/22: 200000; COST PER YEAR 22/23: 200000; COST PER YEAR 23/24: 200000; COST PER YEAR 24/25: 200000; COST PER YEAR 25/26: 200000; COST PER YEAR 26/27: 200000 | 2000000
|  |  | 30 | Construction | [18 empty] | 0
|  |  | 37 | Professional Services | COST PER YEAR 17/18: 300000; COST PER YEAR 18/19: 300000; COST PER YEAR 19/20: 300000; COST PER YEAR 20/21: 300000; COST PER YEAR 21/22: 300000; COST PER YEAR 22/23: 300000; COST PER YEAR 23/24: 300000; COST PER YEAR 24/25: 300000; COST PER YEAR 25/26: 300000; COST PER YEAR 26/27: 300000 | 3000000
| Comment: |  | 41 | Materials | [18 empty] | 0
0
Jaime | Agency Payments |  | 10 | Labor | [18 empty] | 0
|  |  | 30 | Construction | [18 empty] | 0
| Comment: | State Lands | 39 | Other Outside Services | COST PER YEAR 17/18: 100000; COST PER YEAR 18/19: 200000; COST PER YEAR 19/20: 800000; COST PER YEAR 20/21: 800000; COST PER YEAR 21/22: 200000; COST PER YEAR 22/23: 100000; COST PER YEAR 23/24: 100000; COST PER YEAR 24/25: 100000; COST PER YEAR 25/26: 100000; COST PER YEAR 26/27: 100000 | 2600000
|  | GBUAPCD | 39 | Other Outside Services | COST PER YEAR 17/18: 6000000; COST PER YEAR 18/19: 6000000; COST PER YEAR 19/20: 6000000; COST PER YEAR 20/21: 6000000; COST PER YEAR 21/22: 6000000; COST PER YEAR 22/23: 6000000; COST PER YEAR 23/24: 600000; COST PER YEAR 24/25: 600000; COST PER YEAR 25/26: 600000; COST PER YEAR 26/27: 600000 | 38400000
|  |  | 41 | Materials | [18 empty] | 0
| Gravel Contract |  | 10 | Labor | COST PER YEAR 17/18: 150000; COST PER YEAR 18/19: 150000; COST PER YEAR 19/20: 150000; COST PER YEAR 20/21: 150000; COST PER YEAR 21/22: 150000; COST PER YEAR 22/23: 150000; COST PER YEAR 23/24: 150000; COST PER YEAR 24/25: 150000; COST PER YEAR 25/26: 150000; COST PER YEAR 26/27: 150000 | 1500000
| Total Cost: |  | 41 | Materials | COST PER YEAR 16/17: 5000000; COST PER YEAR 17/18: 6000000; COST PER YEAR 18/19: 6000000 | 17000000
| Owens Lake Spare Parts (IFB 693) |  | 10 | Labor | [18 empty] | 0
| Total Cost: |  | 41 | Materials | COST PER YEAR 16/17: 5000000; COST PER YEAR 17/18: 6000000; COST PER YEAR 18/19: 6000000 | 17000000
M. Grahek | Irrigation System Materials (IFB 661) |  | 10 | Labor | COST PER YEAR 17/18: 200000; COST PER YEAR 18/19: 200000; COST PER YEAR 19/20: 200000; COST PER YEAR 20/21: 200000; COST PER YEAR 21/22: 200000; COST PER YEAR 22/23: 200000; COST PER YEAR 23/24: 200000; COST PER YEAR 24/25: 200000; COST PER YEAR 25/26: 200000; COST PER YEAR 26/27: 200000 | 2000000
| Total Cost: |  | 41 | Materials | COST PER YEAR 15/16: 5075324; COST PER YEAR 16/17: 32608; COST PER YEAR 17/18: 6400000; COST PER YEAR 18/19: 5000000; COST PER YEAR 19/20: 4000000 | 20507932
| Seeding Materials (IFB 761) |  | 10 | Labor | COST PER YEAR 17/18: 150000; COST PER YEAR 18/19: 150000; COST PER YEAR 19/20: 150000; COST PER YEAR 20/21: 150000; COST PER YEAR 21/22: 150000; COST PER YEAR 22/23: 150000; COST PER YEAR 23/24: 150000; COST PER YEAR 24/25: 150000; COST PER YEAR 25/26: 150000; COST PER YEAR 26/27: 150000 | 1500000
| Total Cost: |  | 41 | Materials | COST PER YEAR 16/17: 938000; COST PER YEAR 17/18: 1000000; COST PER YEAR 18/19: 1100000 | 3038000
0
| SUBTOTAL BY FISCAL YEAR |  |  |  | 5075324 | 10970608 | 57785000 | 55563000 | 48885000 | 42998000 | 40631000 | 37586000 | 36063000 | 26076000 | 26779000 | 27513000 | 0 | 0 | 0 | 0 |  | 0 | 415924932
[6 empty] | 10 | 6518000 | 5545000 | 4976000 | 4531000 | 4100000 | 4148000 | 4057000 | 4103000 | 4147000 | 4200000 | 0 | 0 | 0 | 0 |  | 0 |  | 46325000
[6 empty] | 37 | 14165000 | 13490000 | 13902000 | 13729000 | 12571000 | 13923000 | 13650000 | 13003000 | 13372000 | 13753000 | 0 | 0 | 0 | 0 |  | 0 |  | 135558000
[6 empty] | 30 | 2640000 | 5300000 | 11921000 | 10631000 | 10062000 | 5695000 | 9666000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 55915000
[6 empty] | 41 | 21862000 | 18300000 | 4323000 | 100000 | 239000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 44824000
[6 empty] | 39 | 6100000 | 6200000 | 6800000 | 6800000 | 6200000 | 6100000 | 700000 | 700000 | 700000 | 700000 | 0 | 0 | 0 | 0 |  | 0 |  | 41000000
[6 empty] | 99 | 6500000 | 6728000 | 6963000 | 7207000 | 7459000 | 7720000 | 7990000 | 8270000 | 8560000 | 8860000 | 0 | 0 | 0 | 0 |  | 0 |  | 76257000
399879000
Assumptions: Hybrid: $35M/(SQ-MILE), Gravel: $30M/(SQ-MILE), TwB2: $500K/(SQ-MILE), Each Square Mile is 50% Hybrid, 25% Gravel, 25% TwB2
| Facilities replacement without Master Project. | [21 empty] | 415924932
| Capital |  |  |  | 289448251.42 | 252088950 | 176617400 | 33040000 | 3000000 | 3500000 | 3800000 | 3000000 | 3500000 | 3800000 | [7 empty] | 1500000
| O&M |  |  |  | 5075324 | 5032608 | 12600000 | 11200000 | 4200000 | 200000 | 200000 | 200000 | 200000 | 200000 | [7 empty] | 0
| Captial without MP through 2016 |  |  |  | COST PER YEAR 15/16: 214978150.11; COST PER YEAR 16/17: 126513475
Phase 7a Monthly Expense Rate
[5 empty] | February | March | April | May | June | July | August | September | October | November | [7 empty] | December | January | February | March | April | May | June | July
[5 empty] | 3.47% | 4.405% | 9.052% | 7.472% | 8.939% | 9.183% | 9.272% | 8.992% | 8.531% | 6.729% | [7 empty] | 6.081% | 5.581% | 2.412% | 1.45% | 1.13% | 0.365% | 0.000859% | 0.6791%
[22 empty] | 82.13% | [6 empty] | 18.62% | 100.7%
ü Cost of Hybrid / Mile2 = $31M
ü Cost of Gravel/ Mile2 = $37M
ü Cost of Sprinkler SF/ Mile2 = $32M
ü Cost of MV/ Mile2 = $36M
ü Cost of Tillage/ Mile2 = $500K
ü Cost per turnout = $2M

## MP_new
Scenario | BWF | MWF | Plover | MSB | Meadow | Water Used (a-f/y) | Hard Transition Area (sq mi) | Soft Transition Area (sq mi) | Groundwater Pumped (a-f/y) |  | * Step 0 DCM assignments from "Anticipated 2017-2018 Dust Season Operation Designations" (letter to P. Kiddoo, 09/29/17)
Base | [6 empty] | - | - | 0 |  | User input (analysis script must be run to update calculations)
0 | [6 empty] | - | - | 0 |  | User input (workbook will update automatically)
1 | [6 empty] | 0 | 0 | 5000 |  | Analysis script output
2 | [6 empty] | 0 | 0 | 9000 |  | Workbook formula calculation
3 | [6 empty] | 0 | 0 | 9000
4 | [6 empty] | 0 | 0 | 9000
5 | [6 empty] | 0 | 0 | 9000
Scenario | BWF | MWF | Plover | MSB | Meadow | Water | Water Savings in Step (a-f/y) w/o GW | Total Water Savings (a-f/y) w/o GW | Water Saved in Step (a-f/y) with GW | Total Water Saved (a-f/y) with GW
Base | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0
1 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 5000 | 5000
2 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 9000 | 9000
3 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 9000 | 9000
4 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 9000 | 9000
5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 9000 | 9000
DCA | Area (ac) | Area (sq mi) | Base | DWM | Step 0* | MP | Step | Transition Type
Channel Area North | 133 | 0.20781 | ENV | ENV | ENV |  |  | hard
Channel Area South | 197 | 0.30781 | ENV | ENV | ENV |  |  | hard
Corridor 1 | 87.9 | 0.13734 | Gravel | Gravel | Gravel |  |  | hard
Phase 8 | 1291.7 | 2.0183 | Gravel | Gravel | Gravel |  |  | hard
T10-1 | 447.9 | 0.69984 | SFP | DWM_Dec | DWM_Dec |  |  | hard
T10-1a | 41.074 | 0.064178 | None | DWM_Jan | DWM_Dec |  |  | hard
T10-2N | 201 | 0.31406 | SFP | DWM_Jan | DWM_Jan |  |  | hard
T10-2S | 698 | 1.0906 | SFL | DWM_Jan | DWM_Jan |  |  | hard
T10-3a | 315.033 | 0.49224 | None | None | Gravel |  |  | hard
T10-3E | 177.8 | 0.27781 | SFP | DWM_Jan | DWM_Jan |  |  | hard
T10-3W | 102.8 | 0.16063 | Brine | Brine | Brine |  |  | hard
T11 | 431 | 0.67344 | SFP | SFP | Brine |  |  | hard
T1-1 | 152.4 | 0.23813 | SFP | DWM_Dec | DWM_Dec |  |  | hard
T12-1 | 215.7 | 0.33703 | None | None | Tillage |  |  | hard
T13-1 Addition | 79.7 | 0.12453 | SFL | DWM_Jan | SFL |  |  | hard
T13-1N | 425.9 | 0.66547 | SFL | SFL | SFL |  |  | hard
T13-1S | 319.2 | 0.49875 | SFL | SFL | SFL |  |  | hard
T13-2N | 251.6 | 0.39313 | SFP | SFP | SFP |  |  | hard
T13-2S | 136.9 | 0.21391 | SFL | SFL | SFL |  |  | hard
T13-3 | 436.6 | 0.68219 | SFP | SFP | SFP |  |  | hard
T15 | 76.1151 | 0.11893 | None | None | Gravel |  |  | hard
T16 | 1082.5 | 1.6914 | SFP | DWM_Jan | MWF and MSB |  |  | hard
T17-1 | 523.9 | 0.81859 | SFP | DWM_Plovers | DWM_Plovers |  |  | hard
T17-2 | 600.8 | 0.93875 | SFP | DWM_Plovers | DWM_Plovers |  |  | hard
T18-0 | 341.5 | 0.53359 | SFP | DWM_Jan | DWM_Jan |  |  | hard
T18N | 544.7 | 0.85109 | SFP | SFP | SFP |  |  | hard
T18N Addition | 21.3 | 0.033281 | SFP | SFP | SFP |  |  | hard
T18S | 1161.7 | 1.8152 | SFP | SFP | SFP |  |  | hard
T1A-1 | 248.4 | 0.38813 | Sand Fences | Sand Fences | Sand Fences |  |  | hard
T1A-2 | 701 | 1.0953 | SFL | SFL | BWF |  |  | hard
T1A-3 | 506.2 | 0.79094 | None | None | Gravel |  |  | hard
T1A-4 | 615.1 | 0.96109 | None | None | SFLS |  |  | hard
T20 | 138.4525 | 0.21633 | None | None | Gravel |  |  | hard
T2-1 | 332.6 | 0.51969 | SFL | SFL | DWM_Oct |  |  | hard
T2-1 Addition | 183.4 | 0.28656 | SFL | SFL | SFL |  |  | hard
T21-1 | 103.8253 | 0.16223 | None | None | Gravel |  |  | hard
T21-2 | 55.5791 | 0.086842 | None | None | Gravel |  |  | hard
T2-1b | 50.1712 | 0.078392 | None | None | Veg 11 |  |  | hard
T2-1c | 110.435 | 0.17255 | None | None | Veg 11 |  |  | hard
T21E | 275.4 | 0.43031 | SFP | SFP | DWM_Oct |  |  | hard
T21W | 43.2 | 0.0675 | SFL | DWM_Jan | DWM_Jan |  |  | hard
T22 | 366.0488 | 0.57195 | None | None | Gravel |  |  | hard
T2-2 | 133.3 | 0.20828 | SFP | SFP | DWM_Oct |  |  | hard
T2-3 | 74.7 | 0.11672 | SFL | SFL | Tillage |  |  | hard
T23-5 | 199.2 | 0.31125 | SFP | SFP | DWM_Dec |  |  | hard
T23NE | 251.4 | 0.39281 | SFL | SFL | Brine |  |  | hard
T23NW | 220.1 | 0.34391 | SFL | SFL | SFL |  |  | hard
T23SE | 475.8 | 0.74344 | SFL | SFL | SFL |  |  | hard
T23SW | 225.4 | 0.35219 | SFL | SFL | SFL |  |  | hard
T24 | 1099.7 | 1.7183 | SFL | SFL | SFL |  |  | hard
T2-4 | 180.3 | 0.28172 | SFL | SFL | Tillage |  |  | hard
T24 Addition | 42.3 | 0.066094 | SFL | SFL | Tillage |  |  | hard
T2-5 | 65.2 | 0.10188 | Brine | Brine | Brine |  |  | hard
T25-3 | 170.2 | 0.26594 | SFL | DWM_Jan | DWM_Jan |  |  | hard
T25N | 257.3 | 0.40203 | SFL | SFL | SFL |  |  | hard
T25S | 818.3 | 1.2786 | SFL | SFL | SFL |  |  | hard
T26 | 851.2 | 1.33 | SFL | SFL | SFL |  |  | hard
T27 Addition | 50.4 | 0.07875 | SFL | SFL | Brine |  |  | hard
T27N | 547.6 | 0.85563 | SFL | SFL | SFL |  |  | hard
T27S | 545.3 | 0.85203 | SFL | SFL | SFL |  |  | hard
T28N | 453 | 0.70781 | SFL | SFL | Meadow |  |  | hard
T28S | 300 | 0.46875 | SFL | SFL | Meadow |  |  | hard
T29-1 | 219.8 | 0.34344 | SFP | SFP | SFP |  |  | hard
T29-2 | 479.5 | 0.74922 | SFP | SFP | SFP |  |  | hard
T29-3 | 258.1 | 0.40328 | SFP | SFP | Brine |  |  | hard
T29-4 | 163.3 | 0.25516 | SFL | SFL | Brine |  |  | hard
T30-1 | 689.3 | 1.077 | SFL | SFL | Breeding Waterfowl & Meadow |  |  | hard
T30-2 | 316.9 | 0.49516 | SFP | SFP | SFP |  |  | hard
T30-3 | 172.8 | 0.27 | SFP | SFP | SFP |  |  | hard
T32-1 | 112.2 | 0.17531 | None | None | Meadow |  |  | hard
T32-2 | 601.1627 | 0.93932 | None | None | Gravel |  |  | hard
T35-1 | 67.3 | 0.10516 | SFP | SFP | Gravel |  |  | hard
T35-2 | 91.6 | 0.14313 | SFP | SFP | Gravel |  |  | hard
T35-3 | 30.9815 | 0.048409 | None | None | Gravel |  |  | hard
T36-1E | 288.4 | 0.45062 | SFL | SFL | Meadow |  |  | hard
T36-1W | 357.2 | 0.55812 | SFL | SFL | Meadow |  |  | hard
T36-2E | 275.8 | 0.43094 | SFP | SFP | SFP |  |  | hard
T36-2W | 391.6 | 0.61188 | SFP | SFP | SFP |  |  | hard
T36-3 Addition | 21.4 | 0.033438 | Brine | Brine | Brine |  |  | hard
T36-3E | 143.1 | 0.22359 | Brine | Brine | Brine |  |  | hard
T36-3W | 82.6 | 0.12906 | Brine | Brine | Brine |  |  | hard
T37-1a | 115.6 | 0.18063 | None | None | Gravel |  |  | hard
T37-2 | 377.8 | 0.59031 | None | None | DWM_Jan |  |  | hard
T37-2a | 116.2517 | 0.18164 | None | None | DWM_Oct |  |  | hard
T37-2b | 41.5666 | 0.064948 | None | None | DWM_Jan |  |  | hard
T37-2c | 31.2677 | 0.048856 | None | None | DWM_Jan |  |  | hard
T37-2d | 120.0515 | 0.18758 | None | None | DWM_Jan |  |  | hard
T3NE | 149.2 | 0.23312 | SFL | SFL | Tillage |  |  | hard
T3SE | 318.7 | 0.49797 | SFL | SFL | Tillage |  |  | hard
T3SE Addition | 77.5 | 0.12109 | SFL | SFL | SFL |  |  | hard
T3SW | 386.5 | 0.60391 | SFL | SFL | Tillage |  |  | hard
T4-3 | 149.4 | 0.23344 | SFL | SFL | SFL |  |  | hard
T4-3 Addition | 87.4 | 0.13656 | SFL | SFL | SFL |  |  | hard
T4-4 | 161.5 | 0.25234 | SFP | SFP | SFP |  |  | hard
T4-5 | 67.2 | 0.105 | SFP | SFP | SFP |  |  | hard
T5-1 | 86.4 | 0.135 | SFL | SFL | SFL |  |  | hard
T5-1 Addition | 19.9 | 0.031094 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-2 | 19.8 | 0.030938 | SFL | SFL | SFL |  |  | hard
T5-3 | 139.2 | 0.2175 | SFL | SFL | DWM_Jan |  |  | hard
T5-3 Addition | 80.6 | 0.12594 | SFP | SFP | DWM_Jan |  |  | hard
T5-3B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-3C | 19.7 | 0.030781 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-4 | 43.4 | 0.067812 | SFP | SFP | SFL |  |  | hard
T5-4B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-4C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-4D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-5A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-5D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-6A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-6B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-6C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-6D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-7A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-7B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T5-7D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-4C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-4D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-5A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-5B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-5C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-5D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-6A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-6B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-6C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-6D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-7A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-7B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-7C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T6-7D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-4A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-4C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-4D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-5A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-5B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-5C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-5D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-6A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-6B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-6C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-6D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-7A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-7B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-7C | 39.9 | 0.062344 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T7-7D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-3A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-3B | 39.7 | 0.062031 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-4A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-4B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-4C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-4D | 40.4 | 0.063125 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-5A | 39.7 | 0.062031 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-5B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-5C | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-5D | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-6A | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-6B | 40 | 0.0625 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-6C | 41.5 | 0.064844 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8-6D | 43 | 0.067187 | Veg 08 | Veg 08 | Veg 08 |  |  | hard
T8W | 124.6 | 0.19469 | Brine | Brine | Brine |  |  | hard
T9 | 292.8 | 0.4575 | SFP | DWM_Dec | DWM_Dec |  |  | hard

## NPV Summary
Net Present Value Summary For Optimzed Master Project, by Project Step
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 4.25% | 2.9% | 3% | 4% | 0% | 30 | 5% | No | 475 | 15 | Treated | 3.6% | Yes | 73
| Net Present Value Summary Table | [8 empty] | Cell Color-Coding
| Step |  | 2018 NPV Benefit ($Million) | [7 empty] | User Input
| Thru Step 1 Only |  | 176.8501 | [7 empty] | Spreadsheet Calculations
| Thru Step 2 Only |  | #REF!
| Thru Step 3 Only |  | #REF!
| Thru Step 4 Only |  | #REF!
| Thru Step 5 |  | #REF!
| 0 | Step 0 water usage (acre-feet/year)

## Area Summary
Total Area under SIP DCM and MP Habitat, in acres.
| FY | 21/22 | 24/25 | 27/28 | 30/31 | 32/33
SIP DCM | Thru Step 0 (acres) | Thru Step 1 (acres) | Thru Step 2 (acres) | Thru Step 3 (acres) | Thru Step 4 (acres) | Full Master Project (acres) | Master Project Habitat | Thru Step 0 (acres) | Thru Step 1 (acres) | Thru Step 2 (acres) | Thru Step 3 (acres) | Thru Step 4 (acres) | Full Master Project (acres) | User input (analysis script must be run to update calculations)
Workbook formula calculation
Traditional Shallow Flood | [6 empty] | Breeding Waterfowl & Meadow | [6 empty] | Analysis script output
Sprinkler Shallow Flood | [6 empty] | Brine
Managed Vegetation Farm | [6 empty] | BWF
Managed Vegetation Phase 7a, 9 and 10 | [6 empty] | DWM_Dec
Gravel | [6 empty] | DWM_Dust Control
Brine with BACM Backup | [6 empty] | DWM_Jan
Tillage with BACM Backup | [6 empty] | DWM_Oct
Channel Areas Reduced MDCE BACM | [6 empty] | DWM_Plovers
Sand Fences | [6 empty] | DWM_Spring_only
Habitat DCM | [6 empty] | ENV
Total | [6 empty] | Gravel
Construction Cost Per Step ($Millions) | [6 empty] | Meadow
| $M/Sq-Mile | Step 1 ($M) | Step 2 ($M) | Step 3 ($M) | Step 4 ($M) | Step 5 ($M) | MSB
Traditional Shallow Flood | 25 | 0 | 0 | 0 | 0 | 0 | MSB and SNPL
Sprinkler Shallow Flood | 32 | 0 | 0 | 0 | 0 | 0 | MSB and SNPL_gravel
Managed Vegetation Farm | 36 | 0 | 0 | 0 | 0 | 0 | MSB and SNPL_gravel_MWF
Managed Vegetation Phase 7a, 9 and 10 | 36 | 0 | 0 | 0 | 0 | 0 | MWF
Gravel | 37 | 0 | 0 | 0 | 0 | 0 | MWF and MSB
Brine with BACM Backup | 22 | 0 | 0 | 0 | 0 | 0 | MWF and SNPL
Tillage with BACM Backup | 1 | 0 | 0 | 0 | 0 | 0 | MWF and SNPL_with gravel
Channel Areas Reduced MDCE BACM | 10 | 0 | 0 | 0 | 0 | 0 | Sand Fences
Sand Fences | 15 | 0 | 0 | 0 | 0 | 0 | SFL
Habitat DCM | 35 | 0 | 0 | 0 | 0 | 0 | SFLS
Construction Cost Per Step ($Millions) |  | 0 | 0 | 0 | 0 | 0 | SFP
O&M Breakdown by Step | [6 empty] | SNPL_realistic
| Step 0 | Step 1 ($M) | Step 2 ($M) | Step 3 ($M) | Step 4 ($M) | Step 5 ($M) | SNPL_with gravel
MP Owned | 0.25224 | 0 | 0 | 0 | 0 | 0 | Tillage
Outside MP | 0.32829 | 0 | 0 | 0 | 0 | 0 | Till-Brine
Veg 08
Veg 11
Total

## MP Analysis Input
User input (analysis script must be run to update calculations)
Analysis Variables
Hard Transition Limit | 3 | square miles (per step)
Soft Transition Limit | 3 | square miles (per step)
Habitat Area Targets |  | decimal % of Base case area
BWF | 0.9 | bw
MWF | 0.9 | mw
Plover | 0.9 | pl
MSB | 0.9 | ms
Meadow | 0.9 | md
Soft Transition DCMS
Tillage
-
-
-
-
-
-
Waterless DCM Preference List |  | Notes:
Tillage | 1st choice | Lowest capital cost, highest maintenance cost.
Gravel | 2nd choice | Limited by soil capacity (not viable close to brine pool).
Brine | 3rd choice | More durable, long-term control measure. Supply limited.
Till-Brine | 4th choice | Dummy DCM, already accounted for as separate Tillage and Brine DCMs. Kept in this list for consistency with Step 0 assignments.

## Constraints
Hardwired Contrainst (written into code): | [10 empty] | DCM List
Channel areas locked to ENV - not in TDCA | [10 empty] | SFP
Nothing ENV except for Channel Areas | [10 empty] | Veg 08
No additional sand fences allowed (besides existing T1A-1) | [10 empty] | Veg 11
Current areas defined as habitat should reamin unchanged. | [10 empty] | ENV
All DCAs under waterless DCM in Step 0 should be kept as-is. | [10 empty] | SFL
All DCAs must be under dust control - no "None" DCMs allowed | [10 empty] | DWM_Jan
Meadow is hard to establish, don't add Meadow, only remove | [10 empty] | DWM_Oct
DWM_Dec
BWF
MWF
DCM Constraints | (DCMs NOT allowed) | [7 empty] | Ops Comments |  | SNPL_realistic
T10-1 | Gravel | Tillage | Veg 08 | Veg 11 | SFL |  |  |  | T10-1SF | tillage,gravel,veg,S.F lats | SNPL_with gravel
T10-1a | Veg 08 | Veg 11 | Gravel | SFL | Tillage | Brine |  |  | T10-1A | veg,gravel,S.F lats, tillage,brine | MSB
T10-2N | Veg 08 | Veg 11 | [6 empty] | T10-2 Pond Post DWM | veg | Meadow
T10-2S | Veg 08 | Veg 11 | [8 empty] | MWF and MSB
T10-3E | Veg 08 | Veg 11 | [6 empty] | T10-3 Pond (East) | veg | MSB and SNPL
T10-3W | Veg 08 | Veg 11 | [6 empty] | T10-3 Brine (West) | veg | MSB and SNPL_gravel
T11 | Veg 08 | Veg 11 | [6 empty] | T11 | veg | MSB and SNPL_gravel_MWF
T13-1 Addition | Gravel | Tillage | SFL | Brine |  |  |  |  | T13-1 Add. | tillage,gravel,veg,S.F lats,brine | MWF and SNPL
T13-1N | Gravel | Tillage | [6 empty] | T13-1SF | tillage,gravel | MWF and SNPL_with gravel
T13-1S | Gravel | Tillage | [6 empty] | T13-1 POND | tillage,gravel | DWM_Dust Control
T16 | Veg 08 | Veg 11 | [6 empty] | T16 Original Large Pond | veg | DWM_Plovers
T17-1 | SFL | Gravel | Tillage | Brine | Veg 08 | Veg 11 |  |  | T17-1&-2SF | S.F lats,gravel,tillage,brine, veg | DWM_Spring_only
T17-2 | SFL | Gravel | Tillage | Brine | Veg 08 | Veg 11 |  |  |  |  | SFLS
T18S | Veg 08 | Veg 11 | Gravel | [5 empty] | T18S - Brine | veg,gravel | Gravel
T1A-4 | Veg 08 | Veg 11 | [6 empty] | T1A-4 | Veg | Tillage
T23-5 | Veg 08 | Veg 11 | Tillage | [5 empty] | T23-5 | veg | Till-Brine
T23NE | Veg 08 | Veg 11 | [6 empty] | T23E | veg | Sand Fences
T23NW | Veg 08 | Veg 11 | [6 empty] | T23W | veg | Brine
T23SE | Veg 08 | Veg 11 | [8 empty] | Breeding Waterfowl & Meadow
T23SW | Veg 08 | Veg 11 | [8 empty] | None
T2-4 | Veg 08 | Veg 11 | [6 empty] | T2-4 POND | Veg
T2-5 | Veg 08 | Veg 11 | Tillage | [5 empty] | T2-5 | veg, tillage
T25-3 | Veg 08 | Veg 11 | [6 empty] | T25-3 | veg
T25N | Veg 08 | Veg 11 | [6 empty] | T25 | veg
T25S | Veg 08 | Veg 11
T26 | Tillage | [7 empty] | T26 | tillage
T27 Addition | Veg 08 | Veg 11 | SFL | Tillage | Gravel | SFLS |  |  | T27Add | veg,tillage,gravel,S.F lats,S.F sprinklers
T27N | Veg 08 | Veg 11 | [6 empty] | T27 only | veg
T27S | Veg 08 | Veg 11
T28N | Tillage | [7 empty] | T28-1 | tillage
T28S | Tillage | [7 empty] | T28-2 | tillage
T29-1 | Tillage | [7 empty] | T29-1 | tillage
T29-2 | Tillage | [7 empty] | T29-2 | tillage
T29-3 | Tillage | Veg 08 | Veg 11 | [5 empty] | T29-3 | tillage,veg
T29-4 | Tillage | Veg 08 | Veg 11 | [5 empty] | T29-4 | Already brine - no tillage,veg
T30-1 | Tillage | [7 empty] | T30-1SF | tillage
T30-2 | Tillage | [7 empty] | T30-2 | tillage
T30-3 | Tillage | [7 empty] | T30-3 | tillage
T36-1E | Tillage | [7 empty] | T36-1 MV/SF SPRINKLER | tillage
T36-1W | Tillage | [7 empty] | T36-1 POND | tillage
T36-2E | Tillage | Veg 08 | Veg 11 | [5 empty] | T36-2 Brine | Already Brine - tillage,veg
T36-2W | Tillage | Veg 08 | Veg 11 | [5 empty] | T36-2 POND | tillage,veg
T36-3E | Tillage | Veg 08 | Veg 11 | [5 empty] | T36-3 Post Brine&Addition | tillage,veg
T36-3 Addition | Tillage | Veg 08 | Veg 11
T36-3W | Tillage | Veg 08 | Veg 11
T37-2 | Veg 08 | Veg 11 | SFL | Tillage |  |  |  |  | T37-2 Laterals inc MV trans | veg,S.F lats
T37-2a | Veg 08 | Veg 11 | SFL | Tillage |  |  |  |  | T37-2A Laterals | veg,S.F lats,tillage
T37-2b | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2B Pond | veg,S.F lats,tillage,gravel
T37-2c | Veg 08 | Veg 11 | SFL | Tillage | Gravel |  |  |  | T37-2C Pond | veg,S.F lats,tillage,gravel
T37-2d | Veg 08 | Veg 11 | SFL | Tillage |  |  |  |  | T37-2D Laterals | veg,S.F lats,tillage
T3SE Addition | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T3SE ADD (inc all SF) | Tillage, Gravel, Veg, Brine
T4-3 | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-3 | Tillage, Gravel, Veg, Brine
T4-3 Addition | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-3 Addition | Tillage, Gravel, Veg, Brine
T4-4 | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-4 | Tillage, Gravel, Veg, Brine
T4-5 | Gravel | Tillage | Veg 08 | Veg 11 | Brine |  |  |  | T4-5 | Tillage, Gravel, Veg, Brine
T5-1 | Gravel | Tillage | Brine | [5 empty] | T5-1SF | Gravel, Tillage, Brine
T5-1 Addition | Gravel | Tillage | Brine | SFP | SFLS | Brine | Veg 08 | Veg 11 | T5-1SF Addition | Ponds, SF Lats, Sprinklers, Brine, Traditional MV
T5-2 | Veg 08 | Veg 11 | [6 empty] | T5-2SF | Veg
T5-3 | Veg 08 | Veg 11 | Tillage | [5 empty] | T5-3SF | Veg, Tillage
T5-3 Addition | Veg 08 | Veg 11 | Tillage
T5-3B | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T5-3-2 | Gravel, Tillage, Veg
T5-3C | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T5-3-3 | Gravel, Tillage, Veg
T5-4 | Veg 08 | Veg 11 | [6 empty] | T5-4 | Veg
T8W | Veg 08 | Veg 11 | [6 empty] | T8W | veg
T9 | Gravel | Tillage | Veg 08 | Veg 11 |  |  |  |  | T9 | gravel,tillage,veg
Step Constraints | (Steps where change NOT allowed)
Corridor 1 | 1 | 2 | 3
T10-1a | 1 | 2 | 3 | [5 empty] | Phase 7a, 9/10 areas: only allow change in steps 4 or 5
T10-3a | 1 | 2 | 3
T12-1 | 1 | 2 | 3
T15 | 1 | 2 | 3
T18S | 2 | 3 | 4 | 5 |  |  |  |  | T18S: only allow change in step 1
T1A-2 | 1 | 2 | 3
T1A-3 | 1 | 2 | 3
T1A-4 | 1 | 2 | 3
T20 | 1 | 2 | 3
T21-1 | 1 | 2 | 3
T21-2 | 1 | 2 | 3
T2-1b | 1 | 2 | 3
T2-1c | 1 | 2 | 3
T22 | 1 | 2 | 3
T28N | 1 | 2 | 3
T28S | 1 | 2 | 3
T30-1 | 1 | 2 | 3
T32-1 | 1 | 2 | 3
T32-2 | 1 | 2 | 3
T35-3 | 1 | 2 | 3
T36-1E | 1 | 2 | 3
T36-1W | 1 | 2 | 3
T36-3W | 1 | 2 | 3
T37-1a | 1 | 2 | 3
T37-2 | 1 | 2 | 3
T37-2a | 1 | 2 | 3
T37-2c | 1 | 2 | 3
T37-2d | 1 | 2 | 3

## Custom HV & WD
DCA | DCM | Step | BW | MW | Pl | MS | Md | Water (f/y) | Habitat value and water demand exceptions from Generic Values, for DCA/DCM/Step0 combinations. The source data for these exceptions was taken from JD workbook, sheets 'Base_20171129', 'DWM', and 'SiteHSV'. #N/A values indicate that there is no exception assignment for that column (i.e. Water) for that combination, and will cause the formulas in MP_new to revert to the generic values for those columns.
Channel Area North | ENV | base | 0.16195 | 0.064286 | 0 | 0.067594 | 0.00090226 | #N/A
Channel Area South | ENV | base | 0.24036 | 0.055076 | 0 | 0.055025 | 0.0031472 | #N/A
Corridor 1 | Gravel | base | 0 | 0.020819 | 0 | 0.053015 | 0 | #N/A
Phase 8 | Gravel | base | 0 | 0.020833 | 0 | 0.053031 | 0 | #N/A
T10-1 | SFP | base | 0 | 0.36048 | 0.28614 | 0.57886 | 0 | #N/A
T10-1a | None | base | 0 | 0.044067 | 0.038467 | 0.28558 | 0.0060866 | #N/A
T10-2N | SFP | base | 0 | 0.2909 | 0.35 | 0.61413 | 0 | #N/A
T10-2S | SFL | base | 0 | 0.44059 | 0.22291 | 0.64274 | 2.8653e-05 | #N/A
T10-3a | None | base | 0 | 0.002095 | 0 | 0.038885 | 0 | #N/A
T10-3E | SFP | base | 0 | 0.07784 | 0.24809 | 0.48498 | 0 | #N/A
T10-3W | Brine | base | 0 | 0 | 0 | 0.048735 | 0 | #N/A
T11 | SFP | base | 0 | 0.14385 | 0.20775 | 0.64847 | 0 | #N/A
T1-1 | SFP | base | 0 | 0.27021 | 0.10984 | 0.62146 | 0 | #N/A
T12-1 | None | base | 0 | 0.0020399 | 0 | 0.025916 | 0 | #N/A
T13-1 Addition | SFL | base | 0 | 0.0043915 | 0.046801 | 0.16462 | 0.0040151 | #N/A
T13-1N | SFL | base | 0 | 0.49977 | 0.1942 | 0.47774 | 0.013102 | #N/A
T13-1S | SFL | base | 0 | 0.4844 | 0.1943 | 0.44919 | 0.017481 | #N/A
T13-2N | SFP | base | 0 | 0.52095 | 0.24452 | 0.54181 | 0 | #N/A
T13-2S | SFL | base | 0 | 0.40782 | 0.29854 | 0.58802 | 0 | #N/A
T13-3 | SFP | base | 0 | 0.16473 | 0.11766 | 0.54647 | 0 | #N/A
T15 | None | base | 0 | 0.0021021 | 0 | 0.038888 | 0 | #N/A
T16 | SFP | base | 0 | 0.17453 | 0.085533 | 0.49992 | 0 | #N/A
T17-1 | SFP | base | 0 | 0.41573 | 0.19139 | 0.53254 | 0.00013361 | #N/A
T17-2 | SFP | base | 0 | 0.54504 | 0.15909 | 0.43034 | 0.00043276 | #N/A
T18-0 | SFP | base | 0 | 0.64266 | 0.1012 | 0.72369 | 0 | #N/A
T18N | SFP | base | 0 | 0.40857 | 0.048339 | 0.47854 | 0 | #N/A
T18N Addition | SFP | base | 0 | 0.18169 | 0.077934 | 0.58263 | 0 | #N/A
T18S | SFP | base | 0 | 0.39128 | 0.16361 | 0.54432 | 8.6081e-06 | #N/A
T1A-1 | Sand Fences | base | 0 | 0.049155 | 0.15378 | 0.33056 | 0.01723 | #N/A
T1A-2 | SFL | base | 0 | 0.4669 | 0.13645 | 0.47136 | 0.001669 | #N/A
T1A-3 | None | base | 0 | 0.002094 | 0 | 0.039075 | 0 | #N/A
T1A-4 | None | base | 0 | 0.0020972 | 0 | 0.038937 | 0 | #N/A
T20 | None | base | 0 | 0.0020946 | 0 | 0.038858 | 0.0007945 | #N/A
T2-1 | SFL | base | 0 | 0.43157 | 0.28854 | 0.56621 | 0.0028863 | #N/A
T2-1 Addition | SFL | base | 0 | 0.2452 | 0.33233 | 0.57181 | 0.0055616 | #N/A
T21-1 | None | base | 0 | 0.0053937 | 0.041127 | 0.24002 | 0 | #N/A
T21-2 | None | base | 0 | 0.0021591 | 0 | 0.038864 | 0 | #N/A
T2-1b | None | base | 0.17261 | 0.04684 | 0.094477 | 0.24217 | 0.10205 | #N/A
T2-1c | None | base | 0.14497 | 0.029972 | 0.019378 | 0.20256 | 0.019106 | #N/A
T21E | SFP | base | 0 | 0.58696 | 0.064924 | 0.54361 | 0.0011619 | #N/A
T21W | SFL | base | 0 | 0.050694 | 0.28287 | 0.40833 | 0 | #N/A
T22 | None | base | 0 | 0.0089332 | 0.065073 | 0.28455 | 0 | #N/A
T2-2 | SFP | base | 0 | 0.43736 | 0.20998 | 0.63968 | 0 | #N/A
T2-3 | SFL | base | 0 | 0.2755 | 0.24926 | 0.55904 | 0 | #N/A
T23-5 | SFP | base | 0 | 0.061546 | 0.099498 | 0.32545 | 0 | #N/A
T23NE | SFL | base | 0 | 0.036317 | 0.078282 | 0.3037 | 0.00019889 | #N/A
T23NW | SFL | base | 0 | 0.058019 | 0.095593 | 0.33617 | 9.0868e-05 | #N/A
T23SE | SFL | base | 0 | 0.20544 | 0.36786 | 0.52268 | 0.00031526 | #N/A
T23SW | SFL | base | 0 | 0.32498 | 0.26229 | 0.53403 | 0 | #N/A
T24 | SFL | base | 0 | 0.16625 | 0.45057 | 0.53616 | 0.0018369 | #N/A
T2-4 | SFL | base | 0 | 0.073045 | 0.11542 | 0.39834 | 0.00061009 | #N/A
T24 Addition | SFL | base | 0 | 0 | 0.076596 | 0.15059 | 0.00094563 | #N/A
T2-5 | Brine | base | 0 | 0 | 0.012117 | 0.091718 | 0 | #N/A
T25-3 | SFL | base | 0 | 0.012808 | 0.091774 | 0.25106 | 0 | #N/A
T25N | SFL | base | 0 | 0.30315 | 0.22013 | 0.56424 | 0.0015935 | #N/A
T25S | SFL | base | 0 | 0.2674 | 0.34968 | 0.58755 | 0.00046438 | #N/A
T26 | SFL | base | 0 | 0.10497 | 0.35856 | 0.43736 | 0.0027373 | #N/A
T27 Addition | SFL | base | 0 | 0 | 0.080952 | 0.15913 | 0 | #N/A
T27N | SFL | base | 0 | 0.18734 | 0.39907 | 0.49622 | 0.00056611 | #N/A
T27S | SFL | base | 0 | 0.16263 | 0.43534 | 0.49043 | 0 | #N/A
T28N | SFL | base | 0.16832 | 0.20645 | 0.24934 | 0.44715 | 0.073488 | #N/A
T28S | SFL | base | 0.16577 | 0.19373 | 0.2385 | 0.43723 | 0.0963 | #N/A
T29-1 | SFP | base | 0 | 0.55214 | 0.021338 | 0.2848 | 0 | #N/A
T29-2 | SFP | base | 0 | 0.18252 | 0.10761 | 0.48586 | 0.015996 | #N/A
T29-3 | SFP | base | 0 | 0.13568 | 0.036691 | 0.36722 | 0 | #N/A
T29-4 | SFL | base | 0 | 0.13258 | 0.13337 | 0.39412 | 0 | #N/A
T30-1 | SFL | base | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | #N/A
T30-2 | SFP | base | 0 | 0.48725 | 0.042537 | 0.40893 | 0.001136 | #N/A
T30-3 | SFP | base | 0 | 0.37749 | 0.077083 | 0.47257 | 0.00011574 | #N/A
T32-1 | None | base | 0.057665 | 0.020856 | 0 | 0.037166 | 0 | #N/A
T32-2 | None | base | 0.029393 | 0.0020793 | 0 | 0.030058 | 0.07755 | #N/A
T35-1 | SFP | base | 0 | 0.28514 | 0.060921 | 0.35542 | 0 | #N/A
T35-2 | SFP | base | 0 | 0.019214 | 0.047162 | 0.32686 | 0 | #N/A
T35-3 | None | base | 0 | 0.0061327 | 0.062295 | 0.24369 | 0 | #N/A
T36-1E | SFL | base | 0.34112 | 0.43232 | 0.1069 | 0.34802 | 0.079369 | #N/A
T36-1W | SFL | base | 0 | 0.43217 | 0.16652 | 0.48653 | 0.041349 | #N/A
T36-2E | SFP | base | 0 | 0.35914 | 0.070631 | 0.52908 | 0.00097897 | #N/A
T36-2W | SFP | base | 0 | 0.020735 | 0.057099 | 0.27873 | 0.00079162 | #N/A
T36-3 Addition | Brine | base | 0 | 0 | 0.035047 | 0.16916 | 0.014486 | #N/A
T36-3E | Brine | base | 0 | 0 | 0.04689 | 0.19804 | 0 | #N/A
T36-3W | Brine | base | 0 | 0 | 0.094794 | 0.19782 | 0 | #N/A
T37-1a | None | base | 0.067301 | 0.020848 | 0 | 0.037111 | 0.098443 | #N/A
T37-2 | None | base | 0 | 0.0020911 | 0 | 0.038936 | 0.00052938 | #N/A
T37-2a | None | base | 0.029419 | 0.0023225 | 0 | 0.095224 | 0.014623 | #N/A
T37-2b | None | base | 0 | 0.0028869 | 0.0069768 | 0.14026 | 0 | #N/A
T37-2c | None | base | 0 | 0.0028784 | 0.014712 | 0.17814 | 0 | #N/A
T37-2d | None | base | 0 | 0.0033319 | 0.027572 | 0.18717 | 0 | #N/A
T3NE | SFL | base | 0 | 0.026743 | 0.14471 | 0.32587 | 0 | #N/A
T3SE | SFL | base | 0 | 0.0060245 | 0.12432 | 0.23649 | 0 | #N/A
T3SE Addition | SFL | base | 0 | 0.0034839 | 0.16426 | 0.22994 | 0 | #N/A
T3SW | SFL | base | 0 | 0.020517 | 0.15777 | 0.27534 | 0 | #N/A
T4-3 | SFL | base | 0 | 0.01834 | 0.31981 | 0.38916 | 0.00093708 | #N/A
T4-3 Addition | SFL | base | 0 | 0.020938 | 0.37471 | 0.40034 | 0.001373 | #N/A
T4-4 | SFP | base | 0 | 0.13839 | 0.12687 | 0.56 | 0.001548 | #N/A
T4-5 | SFP | base | 0 | 0 | 0.026042 | 0.16771 | 0 | #N/A
T5-1 | SFL | base | 0.33218 | 0.16424 | 0.19387 | 0.39062 | 0.17743 | #N/A
T5-1 Addition | Veg 11 | base | 0 | 0.043719 | 0.090955 | 0.29799 | 0 | #N/A
T5-2 | SFL | base | 0 | 0.19697 | 0.31768 | 0.51465 | 0.0040404 | #N/A
T5-3 | SFL | base | 0.36257 | 0.25474 | 0.32091 | 0.50093 | 0.01681 | #N/A
T5-3 Addition | SFP | base | 0.36811 | 0.40447 | 0.14417 | 0.40881 | 0.053598 | #N/A
T5-3B | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.4545 | #N/A
T5-3C | Veg 08 | base | 0.20609 | 0.053299 | 0.036548 | 0.25178 | 0.31827 | #N/A
T5-4 | SFP | base | 0 | 0.14839 | 0.34055 | 0.59332 | 0.0041475 | #N/A
T5-4B | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.4245 | #N/A
T5-4C | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3535 | #N/A
T5-4D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.518 | #N/A
T5-5A | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.34675 | #N/A
T5-5D | Veg 08 | base | 0.22175 | 0.05325 | 0.041 | 0.2515 | 0.20025 | #N/A
T5-6A | Veg 08 | base | 0.1635 | 0.05325 | 0.0325 | 0.23475 | 0.306 | #N/A
T5-6B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.446 | #N/A
T5-6C | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.443 | #N/A
T5-6D | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3605 | #N/A
T5-7A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.353 | #N/A
T5-7B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.44525 | #N/A
T5-7D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35175 | #N/A
T6-4C | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.48825 | #N/A
T6-4D | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.36375 | #N/A
T6-5A | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3885 | #N/A
T6-5B | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.41325 | #N/A
T6-5C | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.2855 | #N/A
T6-5D | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.2615 | #N/A
T6-6A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.4405 | #N/A
T6-6B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.4365 | #N/A
T6-6C | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.271 | #N/A
T6-6D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36875 | #N/A
T6-7A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.358 | #N/A
T6-7B | Veg 08 | base | 0.22175 | 0.05325 | 0.0325 | 0.23475 | 0.23525 | #N/A
T6-7C | Veg 08 | base | 0.22175 | 0.05325 | 0.041 | 0.2515 | 0.176 | #N/A
T6-7D | Veg 08 | base | 0.22175 | 0.05325 | 0.0325 | 0.23475 | 0.188 | #N/A
T7-4A | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.43825 | #N/A
T7-4C | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3925 | #N/A
T7-4D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.436 | #N/A
T7-5A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.343 | #N/A
T7-5B | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.31725 | #N/A
T7-5C | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.45525 | #N/A
T7-5D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36525 | #N/A
T7-6A | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.329 | #N/A
T7-6B | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.336 | #N/A
T7-6C | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.363 | #N/A
T7-6D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35125 | #N/A
T7-7A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35275 | #N/A
T7-7B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36075 | #N/A
T7-7C | Veg 08 | base | 0.16341 | 0.053383 | 0.021805 | 0.23484 | 0.31429 | #N/A
T7-7D | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.3255 | #N/A
T8-3A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.506 | #N/A
T8-3B | Veg 08 | base | 0.16348 | 0.053401 | 0.027456 | 0.23476 | 0.37935 | #N/A
T8-4A | Veg 08 | base | 0.1635 | 0.05325 | 0.0275 | 0.23475 | 0.3605 | #N/A
T8-4B | Veg 08 | base | 0.1635 | 0.05325 | 0.0325 | 0.23475 | 0.352 | #N/A
T8-4C | Veg 08 | base | 0.1635 | 0.05325 | 0.02175 | 0.23475 | 0.40125 | #N/A
T8-4D | Veg 08 | base | 0.16337 | 0.053218 | 0.015099 | 0.2349 | 0.35124 | #N/A
T8-5A | Veg 08 | base | 0.16348 | 0.053401 | 0.015113 | 0.23476 | 0.36322 | #N/A
T8-5B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.35525 | #N/A
T8-5C | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36125 | #N/A
T8-5D | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36675 | #N/A
T8-6A | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.36625 | #N/A
T8-6B | Veg 08 | base | 0.1635 | 0.05325 | 0.015 | 0.23475 | 0.349 | #N/A
T8-6C | Veg 08 | base | 0.16337 | 0.053253 | 0.021928 | 0.2347 | 0.29952 | #N/A
T8-6D | Veg 08 | base | 0.16349 | 0.053256 | 0.015116 | 0.23488 | 0.34093 | #N/A
T8W | Brine | base | 0 | 0 | 0.040289 | 0.17576 | 0 | #N/A
T9 | SFP | base | 0 | 0.12155 | 0.25929 | 0.52223 | 0.0019126 | #N/A
T10-1 | DWM_Dec | dwm | 0 | 0.19033 | 0.35454 | 0.57333 | 9.4567e-06 | 1.5475 | Notes on DWM: Same DCAs in the DWM step (T25S, T26, etc) use MORE water in the DWM step than the generic water use value for the associated DCM. This is because it was agreed that those DCAs would use more water to maintain habitat that was lost when other DCAs wer converted to DWM. (per John Dickey, meeting in PDX on 04/04/18)
T10-2N | DWM_Jan | dwm | 0 | 0.12347 | 0.20259 | 0.44935 | 1.5357e-06 | 0.98
T10-2S | DWM_Jan | dwm | 0 | 0.25342 | 0.14004 | 0.45679 | 3.3626e-05 | 0.98
T10-3E | DWM_Jan | dwm | 0 | 0.017723 | 0.1089 | 0.30536 | 0 | 0.98
T10-3W | Brine | dwm | 0 | 0 | 0 | 0.028681 | 0 | 0
T1-1 | DWM_Dec | dwm | 0 | 0.060567 | 0.098273 | 0.41548 | 2.3538e-05 | 1.07
T13-1 Addition | DWM_Jan | dwm | 0 | 0.0031573 | 0.029317 | 0.18868 | 0.0039635 | 0.98
T13-1N | SFL | dwm | 0 | 0.5471 | 0.23965 | 0.37891 | 0.0074933 | 3.9275
T13-1S | SFL | dwm | 0 | 0.5471 | 0.23965 | 0.37891 | 0.0074933 | 3.9275
T16 | DWM_Jan | dwm | 0 | 0.22155 | 0.18368 | 0.57782 | 0 | 0.98
T17-1 | DWM_Plovers | dwm | 0 | 0.52499 | 0.24903 | 0.54358 | 0.00014091 | 4.0675
T17-2 | DWM_Plovers | dwm | 0 | 0.48845 | 0.22657 | 0.40288 | 0.00044054 | 4.0675
T18-0 | DWM_Jan | dwm | 0 | 0.26634 | 0.089231 | 0.46826 | 0 | 0.98
T21W | DWM_Jan | dwm | 0 | 0.018261 | 0.012997 | 0.19203 | 0 | 0.98
T23-5 | SFP | dwm | 0 | 0.030434 | 0.13872 | 0.28501 | 0 | 4.36
T25-3 | DWM_Jan | dwm | 0 | 0.010657 | 0 | 0.16245 | 0 | 0.98
T25S | SFL | dwm | 0 | 0.26893 | 0.43623 | 0.6019 | 0.00046115 | 3.9275
T26 | SFL | dwm | 0 | 0.30609 | 0.41117 | 0.54295 | 0.0027297 | 3.9275
T29-1 | SFP | dwm | 0 | 0.58799 | 0.073502 | 0.30122 | 0 | 4.8375
T29-2 | SFP | dwm | 0 | 0.2126 | 0.2114 | 0.5437 | 0.015986 | 4.8375
T30-2 | SFP | dwm | 0 | 0.66577 | 0.082649 | 0.38977 | 0.0011511 | 4.8375
T36-2E | SFP | dwm | 0 | 0.21697 | 0.1352 | 0.49463 | 0.00098888 | 4.8375
T37-2 | None | dwm | 0 | 0.013333 | 0.078132 | 0.26089 | 0.00054074 | 0
T5-3 | SFL | dwm | 0.25624 | 0.12353 | 0.21793 | 0.37232 | 0.016612 | 3.9275
T5-3 Addition | SFP | dwm | 0.30727 | 0.21172 | 0.27806 | 0.43337 | 0.031523 | 4.8375
T9 | DWM_Dec | dwm | 0 | 0.093123 | 0.25077 | 0.48157 | 0.001906 | 1.07
T10-1a | DWM_Dec | step0 | 0 | 0.018077 | 0.37029 | 0.29215 | 0 | 1.07
T10-3a | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T12-1 | Tillage | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T15 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T1A-2 | DWM_Oct | step0 | 0.61349 | 0.48103 | 0.13134 | 0.45312 | 0.040482 | 2.6755
T1A-3 | Gravel | step0 | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T1A-4 | SFL | step0 | 0 | 0.22988 | 0.44433 | 0.70522 | 0 | 2.9248
T20 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T21-1 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T21-2 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-1b | Veg 11 | step0 | 0.22579 | 0.05244 | 0.03434 | 0.21506 | 0.56533 | 1.49
T2-1c | Veg 11 | step0 | 0.27713 | 0.072657 | 0.067099 | 0.27404 | 0.55788 | 1.49
T22 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-3 | Tillage | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T2-4 | Tillage | step0 | 0 | 0.03741 | 0.042449 | 0.26195 | 0 | 0
T24 Addition | Tillage | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0.0047833 | 0
T28N | Meadow | step0 | 0.59386 | 0.22325 | 0.16462 | 0.38773 | 0.16761 | 1.3633
T28S | Meadow | step0 | 0.42809 | 0.31381 | 0.29568 | 0.5454 | 0.30164 | 1.0048
T29-4 | Brine | step0 | 0 | 0 | 0.0081639 | 0.089233 | 0 | 0
T30-1 | Veg 11 | step0 | 0.70312 | 0.3476 | 0.029161 | 0.35826 | 0.55611 | 1.7426
T32-2 | Gravel | step0 | 0.029398 | 0.0020833 | 0 | 0.030052 | 0.044908 | 0
T35-1 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.035469 | 0 | 0
T35-2 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.033473 | 0 | 0
T35-3 | Gravel | step0 | 0 | 0.0020833 | 0 | 0.038891 | 0 | 0
T36-1E | Meadow | step0 | 0.58 | 0.24977 | 0.025694 | 0.13738 | 0.22433 | 1.49
T36-1W | Meadow | step0 | 0.53474 | 0.18055 | 0.052914 | 0.1577 | 0.17722 | 1.49
T37-1a | Gravel | step0 | 0.067305 | 0.020833 | 0 | 0.037123 | 0.098457 | 0
T37-2 | SFLS | step0 | 0 | 0.013333 | 0.078132 | 0.26089 | 0.00054074 | 3
T37-2a | DWM_Jan | step0 | 0 | 0.036309 | 0.38728 | 0.45553 | 0.0037659 | 0.98
T37-2b | DWM_Jan | step0 | 0 | 0 | 0.068719 | 0.13973 | 0 | 0.98
T37-2c | DWM_Jan | step0 | 0 | 0 | 0.072063 | 0.14037 | 0 | 0.98
T37-2d | DWM_Jan | step0 | 0 | 0.022986 | 0.37026 | 0.28644 | 0 | 0.98
T3NE | Tillage | step0 | 0 | 0.06483 | 0.18275 | 0.42103 | 0 | 0
T3SE | Tillage | step0 | 0 | 0.06483 | 0.18275 | 0.42103 | 0 | 0
T3SE Add | Tillage | step0 | 0 | 0.09866 | 0.43115 | 0.53577 | 0 | 0
T3SW | Tillage | step0 | 0 | 0.00225 | 0 | 0.086963 | 0 | 0
T5-4 | Brine | step0 | 0 | 0.0125 | 0 | 0.053033 | 0 | 0
T16 | BWF | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673 | Custom water duties for T16 habitat ponds from Jason Olin email 04/05/2018
T16 | MWF | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673 | Note on T16: T16 pond water duties from Jason Olin are for pond acreage only, not aggregate over entire DCA
T16 | SNPL_realistic | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673 | Factor T16 water duties to reflect pond portion of approximately 300 acres ponds / 1100 acres dry.
T16 | SNPL_with gravel | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673 | T16 factor = | 0.27273
T16 | MSB | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and MSB | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL_gravel | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL_gravel_MWF | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and SNPL | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and SNPL_with gravel | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | Breeding Waterfowl & Meadow | mp | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | BWF | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | SNPL_realistic | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | SNPL_with gravel | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and MSB | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL_gravel | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MSB and SNPL_gravel_MWF | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and SNPL | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | MWF and SNPL_with gravel | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673
T16 | Breeding Waterfowl & Meadow | step0 | #N/A | #N/A | #N/A | #N/A | #N/A | 1.4673

## Generic HV & WD
Generic habitat value and water demand by MP DCM designation.
|  | Habitat factors (% of area) generated as average of Base Case habitat values for each DCM | [5 empty] | Habitat factors and Water values Copied from John Dickey workbook sheet 'WD_HV_gen'. | [5 empty] | Water duties from Jason Olin (email 04/05/18)
MP_id | Desc | BW | MW | Pl | MS | Md | Water (f/y) | BW | MW | Pl | MS | Md | Water (f/y) |  | Water (f/y)
SFP | Shallow Flood Pond | 0.011875 | 0.2873 | 0.13495 | 0.48705 | 0.0026439 | 3.13 | 0.021492 | 0.28007 | 0.12329 | 0.44243 | 0.0068052 | 4.36 | Shallow Flood Lateral | 2.73 |  | yes
Veg 08 | Managed Vegetation (2008) | 0.16833 | 0.053258 | 0.02126 | 0.23564 | 0.3619 | 1.01 | 0.16833 | 0.053258 | 0.02126 | 0.23564 | 0.3619 | 1.35 | Sprinkler Shallow Flood | 2.68 |  | no
Veg 11 | Managed Vegetation (2011) | 0 | 0.043719 | 0.090955 | 0.29799 | 0 | 3.18 | 0.019222 | 0.022222 | 0.030318 | 0.1247 | 0.00017646 | 1.49 | Drip Tube Managed Veg | 1.01
ENV | Enhanced Native Vegetation | 0.20116 | 0.059681 | 0 | 0.06131 | 0.0020247 | 0.72 | 0.20116 | 0.059681 | 0 | 0.06131 | 0.0020247 | 0.72 | Sprinkler Managed Veg | 2.65 | normal operating conditions, estblishment is higher water use
SFL | Shallow Flood Lateral | 0.043992 | 0.19212 | 0.22296 | 0.41747 | 0.023833 | 2.73 | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 3.51 | Ponds | 3.13 | Note: "Ponds" and "Habitat Ponds" water duties are considered to be aggregate values for entire DCA.
DWM_Jan | Dynamic Water Management, January start | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 0.98 | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 0.98 | Habitat Ponds | 3.86
DWM_Oct | Dynamic Water Management, October start | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | T16 Habitat Ponds | 5.38 | Note: "T16 Habitat Pond" water duties are considered to be specific to actual pond acreage (and will be adjusted for each HDCM). These will go into the custom sheet for MP steps
DWM_Dec | Dynamic Water Management, December start | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 1.07 | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 1.07
BWF | Breeding Waterfowl | 0.53251 | 0.61029 | 0.1152 | 0.47706 | 0 | 3.86 | 0.53251 | 0.61029 | 0.1152 | 0.47706 | 0 | 4.1
MWF | Migrating Waterfowl | 0 | 0.755 | 0.14514 | 0.5702 | 0 | 3.86 | 0 | 0.755 | 0.14514 | 0.5702 | 0 | 4.71
SNPL_realistic | Snowy Plover | 0 | 0.27 | 0.53908 | 0.56125 | 0 | 3.86 | 0 | 0.27 | 0.53908 | 0.56125 | 0 | 3.46
SNPL_with gravel | Snowy Plover w/ Gravel | 0 | 0.077355 | 0.52288 | 0.54848 | 0 | 3.86 | 0 | 0.077355 | 0.52288 | 0.54848 | 0 | 3.46
MSB | Migrating Shorebirds | 0 | 0.3525 | 0.39217 | 0.89443 | 0 | 3.86 | 0 | 0.3525 | 0.39217 | 0.89443 | 0 | 4.71
Meadow | Meadow | 0.15384 | 0.02 | 0 | 0 | 0.9725 | 1.49 | 0.15384 | 0.02 | 0 | 0 | 0.9725 | 1.49
MWF and MSB | Migrating Waterfowl & Migrating Shorebirds | 0 | 0.755 | 0.15839 | 0.73202 | 0 | 3.86 | 0 | 0.755 | 0.15839 | 0.73202 | 0 | 4.71
MSB and SNPL | Migrating Shorebirds & Snowy Plover | 0 | 0.12 | 0.53908 | 0.89443 | 0 | 3.86 | 0 | 0.12 | 0.53908 | 0.89443 | 0 | 4.71
MSB and SNPL_gravel | Migrating Shorebirds & Snowy Plover w/ Gravel | 0 | 0.1146 | 0.52288 | 0.87407 | 0 | 3.86 | 0 | 0.1146 | 0.52288 | 0.87407 | 0 | 4.71
MSB and SNPL_gravel_MWF | Migrating Shorebirds & Snowy Plover w/ Gravel & Migrating Waterfowl | 0 | 0.382 | 0.52288 | 0.87407 | 0 | 3.86 | 0 | 0.382 | 0.52288 | 0.87407 | 0 | 4.71
MWF and SNPL | Migrating Waterfowl & Snowy Plover | 0 | 0.37267 | 0.50391 | 0.63196 | 0 | 3.86 | 0 | 0.37267 | 0.50391 | 0.63196 | 0 | 4.71
MWF and SNPL_with gravel | Migrating Waterfowl & Snowy Plover w/ Gravel | 0 | 0.35187 | 0.56982 | 0.61023 | 0 | 3.86 | 0 | 0.35187 | 0.56982 | 0.61023 | 0 | 4.71
DWM_Dust Control | Dynamic Water Management, January start | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 0.98 | 0 | 0.041542 | 0.12906 | 0.30121 | 0 | 0.98
DWM_Plovers | Dynamic Water Management, January start & Snowy Plover | 0 | 0.047273 | 0.36071 | 0.3909 | 0 | 3.59 | 0 | 0.047273 | 0.36071 | 0.3909 | 0 | 3.59
DWM_Spring_only | Dynamic Water Management, October start | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51 | 0 | 0.04775 | 0.23384 | 0.3314 | 0 | 1.51
SFLS | Shallow Flood Sprinklers | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 2.68 | 0.024812 | 0.18416 | 0.23831 | 0.43012 | 0.008628 | 3
Gravel | Gravel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tillage | Tillage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Till-Brine | Till-Brine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sand Fences | Sand Fences | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.049155 | 0.15378 | 0.33056 | 0.01723 | 0
Brine | Brine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.048735 | 0 | 0
Breeding Waterfowl & Meadow | Breeding Waterfowl & Meadow | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | 3.51 | 0.34571 | 0.17413 | 0.054301 | 0.23824 | 0.38427 | 3.51
None | None | 0.023874 | 0.010158 | 0.017623 | 0.11915 | 0.015199 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: in general case, waterless DCMs have no habitat value. In a few specific instances in Base case, some DCAs under waterless DCMs had habitat (see "Custom HV and WD" sheet).

## Cost Analysis Input
step | year |  | dust_dcm | capital/SM | om/SM-Y |  | mp_name | desc | hab_id | dust_dcm | O&M Estimates fopr 2017/2018(from email from J. Valenzuela, 05/01/18)
step0 | 2018 | 0 | Traditional Shallow Flood | 25 | 0.25224 |  | Breeding Waterfowl & Meadow | Breeding Waterfowl & Meadow | BWF&MDW | Habitat DCM | SIP DCM | Step 0 (acres) | Step 0 (sq mi) | % of O&M | O&M Cost ($ million) | O&M Cost ($ million / sq. mi.)
step1 | 2021 | 1 | Sprinkler Shallow Flood | 32 | 0.32829 |  | Brine | Brine | Brine | Brine with BACM Backup | Traditional Shallow Flood | 11037 | 17.2453 | 0.15 | 4.35 | 0.25224
step2 | 2024 | 2 | Managed Vegetation Farm | 36 | 1.6396 |  | BWF | Breeding Waterfowl | BWF | Traditional Shallow Flood | Sprinkler Shallow Flood | 7915 | 12.3672 | 0.14 | 4.06 | 0.32829
step3 | 2027 | 3 | Managed Vegetation Phase 7a, 9 and 10 | 36 | 2.0204 |  | DWM_Dec | Dynamic Water Management - DEC | DWM_Dec | Traditional Shallow Flood | Managed Vegetation Farm | 2264 | 3.5375 | 0.2 | 5.8 | 1.6396
step4 | 2030 | 4 | Gravel | 37 | 0.24123 |  | DWM_Dust Control | Dynamic Water Management - Dust Control | DWM_Dust Control | Traditional Shallow Flood | Managed Vegetation Phase 7a, 9 and 10 | 2021 | 3.1578 | 0.22 | 6.38 | 2.0204
step5 | 2033 | 5 | Brine with BACM Backup | 22 | 1.9903 |  | DWM_Jan | Dynamic Water Management - JAN | DWM_Jan | Traditional Shallow Flood | Gravel | 3847 | 6.0109 | 0.05 | 1.45 | 0.24123
|  |  | Tillage with BACM Backup | 1 | 1.3577 |  | DWM_Oct | Dynamic Water Management - OCT | DWM_Oct | Traditional Shallow Flood | Brine with BACM Backup | 746 | 1.1656 | 0.08 | 2.32 | 1.9903
|  |  | Channel Areas Reduced MDCE BACM | 10 | 0.11248 |  | DWM_Plovers | Dynamic Water Management - Plovers | DWM_Plovers | Traditional Shallow Flood | Tillage with BACM Backup | 1367 | 2.1359 | 0.1 | 2.9 | 1.3577
|  |  | Sand Fences | 15 | 0.59871 |  | DWM_Spring_only | Dynamic Water Management - Spring Plovers | DWM_Spring_only | Traditional Shallow Flood | Channel Areas Reduced MDCE BACM | 330 | 0.51562 | 0.002 | 0.058 | 0.11248
|  |  | None | 0 | 0 |  | ENV | Enhanced native vegetation | ENV | Channel Areas Reduced MDCE BACM | Sand Fences | 248 | 0.3875 | 0.008 | 0.232 | 0.59871
|  |  | Habitat DCM | 35 | 0.5237 |  | Gravel | Gravel | GR | Gravel | None | 0 | 0 | 0 | 0 | 0
|  |  | see O&M calculations at end of sheet ------> |  |  |  | Meadow | Meadow | Meadow | Managed Vegetation Phase 7a, 9 and 10 | Habitat DCM | 1772 | 2.7688 | 0.05 | 1.45 | 0.5237
|  |  | capital, om and replacement costs in $ million / square mile |  |  |  | MSB | Shorebirds | MSB | Habitat DCM | Total | 31219 | 48.7797 | 1 | 29
|  |  | lifespan in years |  |  |  | MSB and SNPL | Shorebirds Plus | MSB and SNPL | Habitat DCM
[7 empty] | MSB and SNPL_gravel | Shorebirds Plus | MSB and SNPL_gravel | Habitat DCM
|  |  | Cell Color-Coding |  |  |  | MSB and SNPL_gravel_MWF | Shorebirds Plus | MSB and SNPL_gravel_MWF | Habitat DCM
|  |  |  | User Input |  |  | MWF | Migratory Waterfowl | MWF | Habitat DCM
|  |  |  | Workbook Calculation |  |  | MWF and MSB | Migratory Waterfowl Plus | MWF and MSB | Habitat DCM
|  |  | Changes to user input cells will automatically update spreadsheet calculations. |  |  |  | MWF and SNPL | Migratory Waterfowl Plus | MWF and SNPL | Habitat DCM
[7 empty] | MWF and SNPL_with gravel | Migratory Waterfowl Plus | MWF and SNPL_with gravel | Habitat DCM
[7 empty] | None | No DCM | None | None
[7 empty] | Sand Fences | Sand Fences | SAF | Sand Fences
[7 empty] | SFL | Shallow Flood Lateral | SFL | Sprinkler Shallow Flood
[7 empty] | SFLS | Shallow Flood Lateral with shoulder | SFLS | Sprinkler Shallow Flood
[7 empty] | SFP | Shallow Flood Pond | SFP | Traditional Shallow Flood
[7 empty] | SNPL_realistic | Snowy Plover | SNPL_realistic | Habitat DCM
[7 empty] | SNPL_with gravel | Snowy Plover w/ Gravel | SNPL_with gravel | Habitat DCM
[7 empty] | Tillage | Tillage | TL | Tillage with BACM Backup
[7 empty] | Till-Brine | Till-Brine | TB | Tillage with BACM Backup
[7 empty] | Veg 08 | Managed Vegetation (2008) | MV | Managed Vegetation Farm
[7 empty] | Veg 11 | Managed Vegetation (2011) | MVN | Managed Vegetation Phase 7a, 9 and 10
Water duties from Jason Olin (email 04/05/18)
Water (f/y)
|  |  |  | Shallow Flood Lateral | 2.73 |  | 5241.6
|  |  |  | Sprinkler Shallow Flood | 2.68
|  |  |  | Drip Tube Managed Veg | 1.01
|  |  |  | Sprinkler Managed Veg | 3.18
|  |  |  | Ponds | 3.13 | Note: "Ponds" and "Habitat Ponds" water duties are considered to be aggregate values for entire DCA.
|  |  |  | Habitat Ponds | 3.86
|  |  |  | T16 Habitat Ponds | 5.38 | Note: "T16 Habitat Pond" water duties are considered to be specific to actual pond acreage (and will be adjusted for each HDCM). These will go into the custom sheet for MP steps

## Rates
MWD Water Rates, as provided by LADWP
Rate Used in Analysis |  | MWD Water Rates
Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft)
2007 | 478 | 2007 | - | 478 | 331 | User input (analysis script must be run to update calculations)
2008 | 508 | 2008 | - | 508 | 351 | Workbook formula calculation
2009 | 579 | 2009 | - | 579 | 412
2010 | 701 | 2010 | - | 701 | 484
2011 | 744 | 2011 | - | 744 | 527
2012 | 794 | 2012 | - | 794 | 560
2013 | 847 | 2013 | - | 847 | 593
2014 | 890 | 2014 | - | 890 | 593
2015 | 923 | 2015 | - | 923 | 582
2016 | 942 | 2016 | - | 942 | 594
2017 | 979 | 2017 | - | 979 | 666
2018 | 1015 | 2018 | - | 1015 | 695
2019 | 1053 | 2019 | - | 1053 | 738
2020 | 1092 | 2020 | - | 1092 | 783
2021 | 1123 | 2021 | - | 1123 | 835
2022 | 1164 | 2022 | - | 1164 | 876
2023 | 1205 | 2023 | - | 1205 | 917
2024 | 1249 | 2024 | - | 1249 | 961
2025 | 1296 | 2025 | - | 1296 | 1008
2026 | 1344 | 2026 | - | 1344 | 1056
2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016
2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006
2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203
2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743
2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674
2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637
2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399
2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335
2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783
2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472
2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929
2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879
2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022
2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087
2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826
2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602
2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477
2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034
2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559
2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951
2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141
2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095
2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981
2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F7: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on F13: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.

## Step 1
Projected Costs and Revenues Through Step | [7 empty] | 1
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 0.0425 | 0.029 | 0.03 | 0.04 | 0 | 30 | 0.05 | No | 475 | 15 | Treated | 0.036 | Yes | 73
CHANGE THESE VALUES ONLY ON 'NPV SUMMARY' SHEET
ONLY CHANGE WATER RATES IN 'Rates' SHEET. CHANGES WILL BE REFLECTED HERE.
Base
|  | Projected Annual Cost 2018 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$24.624) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$201.474) | [5 empty] | LADWP Rate of Return |  |  |  |  | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Step | FYE | Capital | O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  | Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
0 | 2018 | 1.5 |  | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1015 | 0 | 0 | - | - | - | - |  | 2007 | 478 | 2007 | - | 478 | 331 | 2018 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2018 | 0 | 0
1 | 2019 | 2.3 |  | 0.365 | 2.3667 | 0 | 0.3796 | 2.3667 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 2.7463 | 4.2463 | -5000 | 5000 | 10000 | 1053 | 10.53 | 10.53 | 7.7837 | 6.2837 | 2019 | 628.37 |  | 2008 | 508 | 2008 | - | 508 | 351 | 2019 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 2019 | 0 | 0
1 | 2020 | 3 | 0 | 0.365 | 3.1765 | 0 | 0.39478 | 3.1765 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 3.5713 | 7.8176 | -5000 | 5000 | 10000 | 1092 | 10.92 | 21.45 | 7.3487 | 13.6324 | 0 | 681.6196 |  | 2009 | 579 | 2009 | - | 579 | 412 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
1 | 2021 | 3.5 | 0 | 0.365 | 3.8134 | 0 | 0.41058 | 3.8134 | 0 | 0.41058 | 0 | 0 | 0 | 0 | 0 | 4.224 | 12.0416 | -5000 | 5000 | 10000 | 1123 | 11.23 | 32.68 | 7.006 | 20.6384 | 0 | 687.9467 |  | 2010 | 701 | 2010 | - | 701 | 484 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
MP Complete | 2022 | 0 | 0 | 0.365 | 0 | 0 | 0.427 | 0 | 0 | 0.427 | 0 | 0 | 0 | 0 | 0 | 0.427 | 12.4686 | 0 | 5000 | 5000 | 1164 | 5.82 | 38.5 | 5.393 | 26.0314 | 0 | 743.7544 |  | 2011 | 744 | 2011 | - | 744 | 527 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
MP Complete | 2023 | 0 | 0 | 0.365 | 0 | 0 | 0.44408 | 0 | 0 | 0.44408 | 0 | 0 | 0 | 0 | 0 | 0.44408 | 12.9127 | 0 | 5000 | 5000 | 1205 | 6.025 | 44.525 | 5.5809 | 31.6123 | 0 | 790.3081 |  | 2012 | 794 | 2012 | - | 794 | 560 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
MP Complete | 2024 | 0 | 0 | 0.365 | 0 | 0 | 0.46184 | 0 | 0 | 0.46184 | 0 | 0 | 0 | 0 | 0 | 0.46184 | 13.3745 | 0 | 5000 | 5000 | 1249 | 6.245 | 50.77 | 5.7832 | 37.3955 | 0 | 831.0107 |  | 2013 | 847 | 2013 | - | 847 | 593 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
MP Complete | 2025 | 0 | 0 | 0.365 | 0 | 0 | 0.48032 | 0 | 0 | 0.48032 | 0 | 0 | 0 | 0 | 0 | 0.48032 | 13.8548 | 0 | 5000 | 5000 | 1296 | 6.48 | 57.25 | 5.9997 | 43.3952 | 0 | 867.9034 |  | 2014 | 890 | 2014 | - | 890 | 593 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
MP Complete | 2026 | 0 | 0 | 0.365 | 0 | 0 | 0.49953 | 0 | 0 | 0.49953 | 0 | 0 | 0 | 0 | 0 | 0.49953 | 14.3544 | 0 | 5000 | 5000 | 1344 | 6.72 | 63.97 | 6.2205 | 49.6156 | 0 | 902.1026 |  | 2015 | 923 | 2015 | - | 923 | 582 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
MP Complete | 2027 | 0 | 0 | 0.365 | 0 | 0 | 0.51951 | 0 | 0 | 0.51951 | 0 | 0 | 0 | 0 | 0 | 0.51951 | 14.8739 | 0 | 5000 | 5000 | 1392.384 | 6.9619 | 70.9319 | 6.4424 | 56.0581 | 0 | 934.3009 |  | 2016 | 942 | 2016 | - | 942 | 594 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
MP Complete | 2028 | 0 | 0 | 0.365 | 0 | 0 | 0.54029 | 0 | 0 | 0.54029 | 0 | 0 | 0 | 0 | 0 | 0.54029 | 15.4142 | 0 | 5000 | 5000 | 1442.5098 | 7.2125 | 78.1445 | 6.6723 | 62.7303 | 0 | 965.0817 |  | 2017 | 979 | 2017 | - | 979 | 666 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
MP Complete | 2029 | 0 | 0 | 0.365 | 0 | 0 | 0.5619 | 0 | 0 | 0.5619 | 0 | 0 | 0 | 0 | 0 | 0.5619 | 15.9761 | 0 | 5000 | 5000 | 1494.4402 | 7.4722 | 85.6167 | 6.9103 | 69.6406 | 0 | 994.8659 |  | 2018 | 1015 | 2018 | - | 1015 | 695 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
MP Complete | 2030 | 0 | 0 | 0.365 | 0 | 0 | 0.58438 | 0 | 0 | 0.58438 | 0 | 0 | 0 | 0 | 0 | 0.58438 | 16.5604 | 0 | 5000 | 5000 | 1548.24 | 7.7412 | 93.3579 | 7.1568 | 76.7974 | 0 | 1023.9658 |  | 2019 | 1053 | 2019 | - | 1053 | 738 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
MP Complete | 2031 | 0 | 0 | 0.365 | 0 | 0 | 0.60775 | 0 | 0 | 0.60775 | 0 | 0 | 0 | 0 | 0 | 0.60775 | 17.1682 | 0 | 5000 | 5000 | 1603.9767 | 8.0199 | 101.3778 | 7.4121 | 84.2096 | 0 | 1052.6196 |  | 2020 | 1092 | 2020 | - | 1092 | 783 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
MP Complete | 2032 | 0 | 0 | 0.365 | 0 | 0 | 0.63206 | 0 | 0 | 0.63206 | 0 | 0 | 0 | 0 | 0 | 0.63206 | 17.8002 | 0 | 5000 | 5000 | 1661.7198 | 8.3086 | 109.6864 | 7.6765 | 91.8861 | 0 | 1081.013 |  | 2021 | 1123 | 2021 | - | 1123 | 835 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
MP Complete | 2033 | 0 | 0 | 0.365 | 0 | 0 | 0.65734 | 0 | 0 | 0.65734 | 0 | 0 | 0 | 0 | 0 | 0.65734 | 18.4576 | 0 | 5000 | 5000 | 1721.5417 | 8.6077 | 118.2941 | 7.9504 | 99.8365 | 0 | 1109.2941 |  | 2022 | 1164 | 2022 | - | 1164 | 876 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
MP Complete | 2034 | 0 | 0 | 0.365 | 0 | 0 | 0.68364 | 0 | 0 | 0.68364 | 0 | 0 | 0 | 0 | 0 | 0.68364 | 19.1412 | 0 | 5000 | 5000 | 1783.5172 | 8.9176 | 127.2116 | 8.2339 | 108.0704 | 0 | 1137.5833 |  | 2023 | 1205 | 2023 | - | 1205 | 917 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
MP Complete | 2035 | 0 | 0 | 0.365 | 0 | 0 | 0.71098 | 0 | 0 | 0.71098 | 0 | 0 | 0 | 0 | 0 | 0.71098 | 19.8522 | 0 | 5000 | 5000 | 1847.7239 | 9.2386 | 136.4503 | 8.5276 | 116.5981 | 0 | 1165.9805 |  | 2024 | 1249 | 2024 | - | 1249 | 961 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
MP Complete | 2036 | 0 | 0 | 0.365 | 0 | 0 | 0.73942 | 0 | 0 | 0.73942 | 0 | 0 | 0 | 0 | 0 | 0.73942 | 20.5916 | 0 | 5000 | 5000 | 1914.2419 | 9.5712 | 146.0215 | 8.8318 | 125.4298 | 0 | 1194.5699 |  | 2025 | 1296 | 2025 | - | 1296 | 1008 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
MP Complete | 2037 | 0 | 0 | 0.365 | 0 | 0 | 0.769 | 0 | 0 | 0.769 | 0 | 0 | 0 | 0 | 0 | 0.769 | 21.3606 | 0 | 5000 | 5000 | 1983.1546 | 9.9158 | 155.9372 | 9.1468 | 134.5766 | 0 | 1223.4237 |  | 2026 | 1344 | 2026 | - | 1344 | 1056 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
MP Complete | 2038 | 0 | 0 | 0.365 | 0 | 0 | 0.79976 | 0 | 0 | 0.79976 | 0 | 0 | 0 | 0 | 0 | 0.79976 | 22.1604 | 0 | 5000 | 5000 | 2054.5482 | 10.2727 | 166.21 | 9.473 | 144.0496 | 0 | 1252.6052 |  | 2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
MP Complete | 2039 | 0 | 0 | 0.365 | 0 | 0 | 0.83175 | 0 | 0 | 0.83175 | 0 | 0 | 0 | 0 | 0 | 0.83175 | 22.9921 | 0 | 5000 | 5000 | 2128.5119 | 10.6426 | 176.8526 | 9.8108 | 153.8604 | 0 | 1282.17 |  | 2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
MP Complete | 2040 | 0 | 0 | 0.365 | 0 | 0 | 0.86502 | 0 | 0 | 0.86502 | 0 | 0 | 0 | 0 | 0 | 0.86502 | 23.8572 | 0 | 5000 | 5000 | 2205.1384 | 11.0257 | 187.8782 | 10.1607 | 164.0211 | 0 | 1312.1686 |  | 2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
MP Complete | 2041 | 0 | 0 | 0.365 | 0 | 0 | 0.89962 | 0 | 0 | 0.89962 | 0 | 0 | 0 | 0 | 0 | 0.89962 | 24.7568 | 0 | 5000 | 5000 | 2284.5233 | 11.4226 | 199.3009 | 10.523 | 174.5441 | 0 | 1342.6467 |  | 2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
MP Complete | 2042 | 0 | 0 | 0.365 | 0 | 0 | 0.93561 | 0 | 0 | 0.93561 | 0 | 0 | 0 | 0 | 0 | 0.93561 | 25.6924 | 0 | 5000 | 5000 | 2366.7662 | 11.8338 | 211.1347 | 10.8982 | 185.4423 | 0 | 1373.6466 |  | 2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
MP Complete | 2043 | 0 | 0 | 0.365 | 0 | 0 | 0.97303 | 0 | 0 | 0.97303 | 0 | 0 | 0 | 0 | 0 | 0.97303 | 26.6654 | 0 | 5000 | 5000 | 2451.9698 | 12.2598 | 223.3945 | 11.2868 | 196.7291 | 0 | 1405.2079 |  | 2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
MP Complete | 2044 | 0 | 0 | 0.365 | 0 | 0 | 1.012 | 0 | 0 | 1.012 | 0 | 0 | 0 | 0 | 0 | 1.012 | 27.6774 | 0 | 5000 | 5000 | 2540.2407 | 12.7012 | 236.0957 | 11.6893 | 208.4184 | 0 | 1437.368 |  | 2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
MP Complete | 2045 | 0 | 0 | 0.365 | 0 | 0 | 1.0524 | 0 | 0 | 1.0524 | 0 | 0 | 0 | 0 | 0 | 1.0524 | 28.7298 | 0 | 5000 | 5000 | 2631.6893 | 13.1584 | 249.2542 | 12.106 | 220.5244 | 0 | 1470.1625 |  | 2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
MP Complete | 2046 | 0 | 0 | 0.365 | 0 | 0 | 1.0945 | 0 | 0 | 1.0945 | 0 | 0 | 0 | 0 | 0 | 1.0945 | 29.8243 | 0 | 5000 | 5000 | 2726.4302 | 13.6322 | 262.8863 | 12.5376 | 233.062 | 0 | 1503.6258 |  | 2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
MP Complete | 2047 | 0 | 0 | 0.365 | 0 | 0 | 1.1383 | 0 | 0 | 1.1383 | 0 | 0 | 0 | 0 | 0 | 1.1383 | 30.9626 | 0 | 5000 | 5000 | 2824.5816 | 14.1229 | 277.0092 | 12.9846 | 246.0466 | 0 | 1537.7913 |  | 2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
MP Complete | 2048 | 0 | 0 | 0.365 | 0 | 0 | 1.1838 | 0 | 0 | 1.1838 | 0 | 0 | 0 | 0 | 0 | 1.1838 | 32.1465 | 0 | 5000 | 5000 | 2926.2666 | 14.6313 | 291.6406 | 13.4475 | 259.4941 | 0 | 1572.6915 |  | 2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
MP Complete | 2049 | 0 | 0 | 0.365 | 0 | 0 | 1.2312 | 0 | 0 | 1.2312 | 0 | 0 | 0 | 0 | 0 | 1.2312 | 33.3777 | 0 | 5000 | 5000 | 3031.6122 | 15.1581 | 306.7986 | 13.9269 | 273.421 | 0 | 1608.3586 |  | 2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
MP Complete | 2050 | 0 | 0 | 0.365 | 0 | 0 | 1.2804 | 0 | 0 | 1.2804 | 0 | 0 | 0 | 0 | 0 | 1.2804 | 34.6581 | 0 | 5000 | 5000 | 3140.7502 | 15.7038 | 322.5024 | 14.4233 | 287.8443 | 0 | 1644.8244 |  | 2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
MP Complete | 2051 | 0 | 0 | 0.365 | 0 | 0 | 1.3317 | 0 | 0 | 1.3317 | 0 | 0 | 0 | 0 | 0 | 1.3317 | 35.9898 | 0 | 5000 | 5000 | 3253.8172 | 16.2691 | 338.7715 | 14.9374 | 302.7817 | 0 | 1682.1206 |  | 2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
MP Complete | 2052 | 0 | 0 | 0.365 | 0 | 0 | 1.3849 | 0 | 0 | 1.3849 | 0 | 0 | 0 | 0 | 0 | 1.3849 | 37.3747 | 0 | 5000 | 5000 | 3370.9546 | 16.8548 | 355.6263 | 15.4698 | 318.2516 | 0 | 1720.2787 |  | 2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
MP Complete | 2053 | 0 | 0 | 0.365 | 0 | 0 | 1.4403 | 0 | 0 | 1.4403 | 0 | 0 | 0 | 0 | 0 | 1.4403 | 38.815 | 0 | 5000 | 5000 | 3492.309 | 17.4615 | 373.0878 | 16.0212 | 334.2728 | 0 | 1759.3304 | 204.2896 | 2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
MP Complete | 2054 | 0 | 0 | 0.365 | 0 | 0 | 1.4979 | 0 | 0 | 1.4979 | 0 | 0 | 0 | 0 | 0 | 1.4979 | 40.313 | 0 | 5000 | 5000 | 3618.0321 | 18.0902 | 391.178 | 16.5922 | 350.865 | 0 | 1799.3077 |  | 2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
MP Complete | 2055 | 0 | 0 | 0.365 | 0 | 0 | 1.5579 | 0 | 0 | 1.5579 | 0 | 0 | 0 | 0 | 0 | 1.5579 | 41.8708 | 0 | 5000 | 5000 | 3748.2813 | 18.7414 | 409.9194 | 17.1836 | 368.0486 | 0 | 1840.2428 |  | 2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
MP Complete | 2056 | 0 | 0 | 0.365 | 0 | 0 | 1.6202 | 0 | 0 | 1.6202 | 0 | 0 | 0 | 0 | 0 | 1.6202 | 43.491 | 0 | 5000 | 5000 | 3883.2194 | 19.4161 | 429.3355 | 17.7959 | 385.8445 | 0 | 1882.1682 |  | 2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
MP Complete | 2057 | 0 | 0 | 0.365 | 0 | 0 | 1.685 | 0 | 0 | 1.685 | 0 | 0 | 0 | 0 | 0 | 1.685 | 45.176 | 0 | 5000 | 5000 | 4023.0153 | 20.1151 | 449.4505 | 18.4301 | 404.2746 | 0 | 1925.1171 |  | 2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
MP Complete | 2058 | 0 | 0 | 0.365 | 0 | 0 | 1.7524 | 0 | 0 | 1.7524 | 0 | 0 | 0 | 0 | 0 | 1.7524 | 46.9283 | 0 | 5000 | 5000 | 4167.8439 | 20.8392 | 470.2898 | 19.0868 | 423.3614 | 0 | 1969.1229 |  | 2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
MP Complete | 2059 | 0 | 0 | 0.365 | 0 | 0 | 1.8225 | 0 | 0 | 1.8225 | 0 | 0 | 0 | 0 | 0 | 1.8225 | 48.7508 | 0 | 5000 | 5000 | 4317.8863 | 21.5894 | 491.8792 | 19.767 | 443.1284 | 0 | 2014.22 |  | 2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
MP Complete | 2060 | 0 | 0 | 0.365 | 0 | 0 | 1.8954 | 0 | 0 | 1.8954 | 0 | 0 | 0 | 0 | 0 | 1.8954 | 50.6462 | 0 | 5000 | 5000 | 4473.3302 | 22.3667 | 514.2458 | 20.4713 | 463.5997 | 0 | 2060.443 |  | 2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
[15 empty] | Total Cost (NPV) | 24.6237 |  |  |  |  | Total Revenue (NPV) | 201.4738 | IRR | 0% |  | $/AF at Life of Project (Year 2060) | 225.094 |  | 2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
1 - If LRP Subsidies are applicable, an Increase in supplies occuring after 2125 will require a modification to the current analysis. | [28 empty] | 2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
[29 empty] | 2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
[29 empty] | 2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
[29 empty] | 2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
[29 empty] | 2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
[29 empty] | 2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
[29 empty] | 2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
[29 empty] | 2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
[29 empty] | 2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
[29 empty] | 2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F10: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L10: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT10: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S12: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.
Note on AM13: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on AM19: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.

## Steps 1 thru 2
Projected Costs and Revenues Through Step | [7 empty] | 2
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 0.0425 | 0.029 | 0.03 | 0.04 | 0 | 30 | 0.05 | No | 475 | 15 | Treated | 0.036 | Yes | 73
CHANGE THESE VALUES ONLY ON 'NPV SUMMARY' SHEET
ONLY CHANGE WATER RATES IN 'Rates' SHEET. CHANGES WILL BE REFLECTED HERE.
Base
|  | Projected Annual Cost 2018 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$35.404) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$353.29) | [5 empty] | LADWP Rate of Return |  |  |  |  | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Step | FYE | Capital | O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  | Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
0 | 2018 | 1.5 |  | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1015 | 0 | 0 | - | - | - | - |  | 2007 | 478 | 2007 | - | 478 | 331 | 2018 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2018 | 0 | 0
1 | 2019 | 2.3 |  | 0.365 | 2.3667 | 0 | 0.3796 | 2.3667 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 2.7463 | 4.2463 | -5000 | 5000 | 10000 | 1053 | 10.53 | 10.53 | 7.7837 | 6.2837 | 2019 | 628.37 |  | 2008 | 508 | 2008 | - | 508 | 351 | 2019 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 2019 | 0 | 0
1 | 2020 | 3 | 0 | 0.365 | 3.1765 | 0 | 0.39478 | 3.1765 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 3.5713 | 7.8176 | -5000 | 5000 | 10000 | 1092 | 10.92 | 21.45 | 7.3487 | 13.6324 | 0 | 681.6196 |  | 2009 | 579 | 2009 | - | 579 | 412 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
1 | 2021 | 3.5 | 0 | 0.365 | 3.8134 | 0 | 0.41058 | 3.8134 | 0 | 0.41058 | 0 | 0 | 0 | 0 | 0 | 4.224 | 12.0416 | -5000 | 5000 | 10000 | 1123 | 11.23 | 32.68 | 7.006 | 20.6384 | 0 | 687.9467 |  | 2010 | 701 | 2010 | - | 701 | 484 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
2 | 2022 | 0 | 0 | 0.657 | 0 | 0 | 0.7686 | 0 | 0 | 0.7686 | 0 | 0 | 0 | 0 | 0 | 0.7686 | 12.8102 | -5000 | 9000 | 14000 | 1164 | 16.296 | 48.976 | 15.5274 | 36.1658 | 0 | 821.9501 |  | 2011 | 744 | 2011 | - | 744 | 527 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
2 | 2023 | 0 | 0 | 0.657 | 0 | 0 | 0.79934 | 0 | 0 | 0.79934 | 0 | 0 | 0 | 0 | 0 | 0.79934 | 13.6095 | -5000 | 9000 | 14000 | 1205 | 16.87 | 65.846 | 16.0707 | 52.2365 | 0 | 900.6287 |  | 2012 | 794 | 2012 | - | 794 | 560 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
2 | 2024 | 0 | 0 | 0.657 | 0 | 0 | 0.83131 | 0 | 0 | 0.83131 | 0 | 0 | 0 | 0 | 0 | 0.83131 | 14.4409 | -5000 | 9000 | 14000 | 1249 | 17.486 | 83.332 | 16.6547 | 68.8911 | 0 | 956.8215 |  | 2013 | 847 | 2013 | - | 847 | 593 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
MP Complete | 2025 | 0 | 0 | 0.657 | 0 | 0 | 0.86457 | 0 | 0 | 0.86457 | 0 | 0 | 0 | 0 | 0 | 0.86457 | 15.3054 | 0 | 9000 | 9000 | 1296 | 11.664 | 94.996 | 10.7994 | 79.6906 | 0 | 983.8343 |  | 2014 | 890 | 2014 | - | 890 | 593 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
MP Complete | 2026 | 0 | 0 | 0.657 | 0 | 0 | 0.89915 | 0 | 0 | 0.89915 | 0 | 0 | 0 | 0 | 0 | 0.89915 | 16.2046 | 0 | 9000 | 9000 | 1344 | 12.096 | 107.092 | 11.1969 | 90.8874 | 0 | 1009.8604 |  | 2015 | 923 | 2015 | - | 923 | 582 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
MP Complete | 2027 | 0 | 0 | 0.657 | 0 | 0 | 0.93512 | 0 | 0 | 0.93512 | 0 | 0 | 0 | 0 | 0 | 0.93512 | 17.1397 | 0 | 9000 | 9000 | 1392.384 | 12.5315 | 119.6235 | 11.5963 | 102.4838 | 0 | 1035.1896 |  | 2016 | 942 | 2016 | - | 942 | 594 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
MP Complete | 2028 | 0 | 0 | 0.657 | 0 | 0 | 0.97252 | 0 | 0 | 0.97252 | 0 | 0 | 0 | 0 | 0 | 0.97252 | 18.1122 | 0 | 9000 | 9000 | 1442.5098 | 12.9826 | 132.606 | 12.0101 | 114.4938 | 0 | 1060.1281 |  | 2017 | 979 | 2017 | - | 979 | 666 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
MP Complete | 2029 | 0 | 0 | 0.657 | 0 | 0 | 1.0114 | 0 | 0 | 1.0114 | 0 | 0 | 0 | 0 | 0 | 1.0114 | 19.1236 | 0 | 9000 | 9000 | 1494.4402 | 13.45 | 146.056 | 12.4385 | 126.9324 | 0 | 1084.8921 |  | 2018 | 1015 | 2018 | - | 1015 | 695 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
MP Complete | 2030 | 0 | 0 | 0.657 | 0 | 0 | 1.0519 | 0 | 0 | 1.0519 | 0 | 0 | 0 | 0 | 0 | 1.0519 | 20.1755 | 0 | 9000 | 9000 | 1548.24 | 13.9342 | 159.9902 | 12.8823 | 139.8147 | 0 | 1109.6402 |  | 2019 | 1053 | 2019 | - | 1053 | 738 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
MP Complete | 2031 | 0 | 0 | 0.657 | 0 | 0 | 1.094 | 0 | 0 | 1.094 | 0 | 0 | 0 | 0 | 0 | 1.094 | 21.2695 | 0 | 9000 | 9000 | 1603.9767 | 14.4358 | 174.426 | 13.3418 | 153.1565 | 0 | 1134.4926 |  | 2020 | 1092 | 2020 | - | 1092 | 783 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
MP Complete | 2032 | 0 | 0 | 0.657 | 0 | 0 | 1.1377 | 0 | 0 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 1.1377 | 22.4072 | 0 | 9000 | 9000 | 1661.7198 | 14.9555 | 189.3814 | 13.8178 | 166.9743 | 0 | 1159.5435 |  | 2021 | 1123 | 2021 | - | 1123 | 835 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
MP Complete | 2033 | 0 | 0 | 0.657 | 0 | 0 | 1.1832 | 0 | 0 | 1.1832 | 0 | 0 | 0 | 0 | 0 | 1.1832 | 23.5904 | 0 | 9000 | 9000 | 1721.5417 | 15.4939 | 204.8753 | 14.3107 | 181.2849 | 0 | 1184.8688 |  | 2022 | 1164 | 2022 | - | 1164 | 876 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
MP Complete | 2034 | 0 | 0 | 0.657 | 0 | 0 | 1.2305 | 0 | 0 | 1.2305 | 0 | 0 | 0 | 0 | 0 | 1.2305 | 24.8209 | 0 | 9000 | 9000 | 1783.5172 | 16.0517 | 220.927 | 14.8211 | 196.106 | 0 | 1210.531 |  | 2023 | 1205 | 2023 | - | 1205 | 917 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
MP Complete | 2035 | 0 | 0 | 0.657 | 0 | 0 | 1.2798 | 0 | 0 | 1.2798 | 0 | 0 | 0 | 0 | 0 | 1.2798 | 26.1007 | 0 | 9000 | 9000 | 1847.7239 | 16.6295 | 237.5565 | 15.3497 | 211.4558 | 0 | 1236.5835 |  | 2024 | 1249 | 2024 | - | 1249 | 961 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
MP Complete | 2036 | 0 | 0 | 0.657 | 0 | 0 | 1.331 | 0 | 0 | 1.331 | 0 | 0 | 0 | 0 | 0 | 1.331 | 27.4317 | 0 | 9000 | 9000 | 1914.2419 | 17.2282 | 254.7847 | 15.8972 | 227.353 | 0 | 1263.0722 |  | 2025 | 1296 | 2025 | - | 1296 | 1008 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
MP Complete | 2037 | 0 | 0 | 0.657 | 0 | 0 | 1.3842 | 0 | 0 | 1.3842 | 0 | 0 | 0 | 0 | 0 | 1.3842 | 28.8159 | 0 | 9000 | 9000 | 1983.1546 | 17.8484 | 272.633 | 16.4642 | 243.8172 | 0 | 1290.038 |  | 2026 | 1344 | 2026 | - | 1344 | 1056 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
MP Complete | 2038 | 0 | 0 | 0.657 | 0 | 0 | 1.4396 | 0 | 0 | 1.4396 | 0 | 0 | 0 | 0 | 0 | 1.4396 | 30.2554 | 0 | 9000 | 9000 | 2054.5482 | 18.4909 | 291.124 | 17.0514 | 260.8685 | 0 | 1317.5179 |  | 2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
MP Complete | 2039 | 0 | 0 | 0.657 | 0 | 0 | 1.4972 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 0 | 1.4972 | 31.7526 | 0 | 9000 | 9000 | 2128.5119 | 19.1566 | 310.2806 | 17.6595 | 278.528 | 0 | 1345.5459 |  | 2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
MP Complete | 2040 | 0 | 0 | 0.657 | 0 | 0 | 1.557 | 0 | 0 | 1.557 | 0 | 0 | 0 | 0 | 0 | 1.557 | 33.3096 | 0 | 9000 | 9000 | 2205.1384 | 19.8462 | 330.1268 | 18.2892 | 296.8172 | 0 | 1374.1538 |  | 2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
MP Complete | 2041 | 0 | 0 | 0.657 | 0 | 0 | 1.6193 | 0 | 0 | 1.6193 | 0 | 0 | 0 | 0 | 0 | 1.6193 | 34.9289 | 0 | 9000 | 9000 | 2284.5233 | 20.5607 | 350.6875 | 18.9414 | 315.7586 | 0 | 1403.3716 |  | 2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
MP Complete | 2042 | 0 | 0 | 0.657 | 0 | 0 | 1.6841 | 0 | 0 | 1.6841 | 0 | 0 | 0 | 0 | 0 | 1.6841 | 36.613 | 0 | 9000 | 9000 | 2366.7662 | 21.3009 | 371.9884 | 19.6168 | 335.3754 | 0 | 1433.2282 |  | 2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
MP Complete | 2043 | 0 | 0 | 0.657 | 0 | 0 | 1.7515 | 0 | 0 | 1.7515 | 0 | 0 | 0 | 0 | 0 | 1.7515 | 38.3645 | 0 | 9000 | 9000 | 2451.9698 | 22.0677 | 394.0562 | 20.3163 | 355.6917 | 0 | 1463.7518 |  | 2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
MP Complete | 2044 | 0 | 0 | 0.657 | 0 | 0 | 1.8215 | 0 | 0 | 1.8215 | 0 | 0 | 0 | 0 | 0 | 1.8215 | 40.186 | 0 | 9000 | 9000 | 2540.2407 | 22.8622 | 416.9183 | 21.0407 | 376.7323 | 0 | 1494.9696 |  | 2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
MP Complete | 2045 | 0 | 0 | 0.657 | 0 | 0 | 1.8944 | 0 | 0 | 1.8944 | 0 | 0 | 0 | 0 | 0 | 1.8944 | 42.0804 | 0 | 9000 | 9000 | 2631.6893 | 23.6852 | 440.6035 | 21.7908 | 398.5232 | 0 | 1526.9087 |  | 2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
MP Complete | 2046 | 0 | 0 | 0.657 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 44.0505 | 0 | 9000 | 9000 | 2726.4302 | 24.5379 | 465.1414 | 22.5677 | 421.0909 | 0 | 1559.5959 |  | 2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
MP Complete | 2047 | 0 | 0 | 0.657 | 0 | 0 | 2.049 | 0 | 0 | 2.049 | 0 | 0 | 0 | 0 | 0 | 2.049 | 46.0995 | 0 | 9000 | 9000 | 2824.5816 | 25.4212 | 490.5626 | 23.3723 | 444.4632 | 0 | 1593.058 |  | 2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
MP Complete | 2048 | 0 | 0 | 0.657 | 0 | 0 | 2.1309 | 0 | 0 | 2.1309 | 0 | 0 | 0 | 0 | 0 | 2.1309 | 48.2304 | 0 | 9000 | 9000 | 2926.2666 | 26.3364 | 516.899 | 24.2055 | 468.6687 | 0 | 1627.3217 |  | 2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
MP Complete | 2049 | 0 | 0 | 0.657 | 0 | 0 | 2.2161 | 0 | 0 | 2.2161 | 0 | 0 | 0 | 0 | 0 | 2.2161 | 50.4465 | 0 | 9000 | 9000 | 3031.6122 | 27.2845 | 544.1836 | 25.0684 | 493.737 | 0 | 1662.4142 |  | 2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
MP Complete | 2050 | 0 | 0 | 0.657 | 0 | 0 | 2.3048 | 0 | 0 | 2.3048 | 0 | 0 | 0 | 0 | 0 | 2.3048 | 52.7513 | 0 | 9000 | 9000 | 3140.7502 | 28.2668 | 572.4503 | 25.962 | 519.699 | 0 | 1698.3627 |  | 2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
MP Complete | 2051 | 0 | 0 | 0.657 | 0 | 0 | 2.397 | 0 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 2.397 | 55.1483 | 0 | 9000 | 9000 | 3253.8172 | 29.2844 | 601.7347 | 26.8874 | 546.5863 | 0 | 1735.1947 |  | 2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
MP Complete | 2052 | 0 | 0 | 0.657 | 0 | 0 | 2.4929 | 0 | 0 | 2.4929 | 0 | 0 | 0 | 0 | 0 | 2.4929 | 57.6412 | 0 | 9000 | 9000 | 3370.9546 | 30.3386 | 632.0733 | 27.8457 | 574.4321 | 0 | 1772.9385 |  | 2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
MP Complete | 2053 | 0 | 0 | 0.657 | 0 | 0 | 2.5926 | 0 | 0 | 2.5926 | 0 | 0 | 0 | 0 | 0 | 2.5926 | 60.2338 | 0 | 9000 | 9000 | 3492.309 | 31.4308 | 663.504 | 28.8382 | 603.2703 | 0 | 1811.6224 | 180.8822 | 2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
MP Complete | 2054 | 0 | 0 | 0.657 | 0 | 0 | 2.6963 | 0 | 0 | 2.6963 | 0 | 0 | 0 | 0 | 0 | 2.6963 | 62.93 | 0 | 9000 | 9000 | 3618.0321 | 32.5623 | 696.0663 | 29.866 | 633.1363 | 0 | 1851.2757 |  | 2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
MP Complete | 2055 | 0 | 0 | 0.657 | 0 | 0 | 2.8041 | 0 | 0 | 2.8041 | 0 | 0 | 0 | 0 | 0 | 2.8041 | 65.7342 | 0 | 9000 | 9000 | 3748.2813 | 33.7345 | 729.8009 | 30.9304 | 664.0667 | 0 | 1891.9278 |  | 2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
MP Complete | 2056 | 0 | 0 | 0.657 | 0 | 0 | 2.9163 | 0 | 0 | 2.9163 | 0 | 0 | 0 | 0 | 0 | 2.9163 | 68.6505 | 0 | 9000 | 9000 | 3883.2194 | 34.949 | 764.7498 | 32.0327 | 696.0993 | 0 | 1933.6093 |  | 2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
MP Complete | 2057 | 0 | 0 | 0.657 | 0 | 0 | 3.033 | 0 | 0 | 3.033 | 0 | 0 | 0 | 0 | 0 | 3.033 | 71.6834 | 0 | 9000 | 9000 | 4023.0153 | 36.2071 | 800.957 | 33.1742 | 729.2735 | 0 | 1976.351 |  | 2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
MP Complete | 2058 | 0 | 0 | 0.657 | 0 | 0 | 3.1543 | 0 | 0 | 3.1543 | 0 | 0 | 0 | 0 | 0 | 3.1543 | 74.8377 | 0 | 9000 | 9000 | 4167.8439 | 37.5106 | 838.4676 | 34.3563 | 763.6299 | 0 | 2020.1848 |  | 2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
MP Complete | 2059 | 0 | 0 | 0.657 | 0 | 0 | 3.2804 | 0 | 0 | 3.2804 | 0 | 0 | 0 | 0 | 0 | 3.2804 | 78.1181 | 0 | 9000 | 9000 | 4317.8863 | 38.861 | 877.3285 | 35.5805 | 799.2104 | 0 | 2065.1431 |  | 2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
MP Complete | 2060 | 0 | 0 | 0.657 | 0 | 0 | 3.4117 | 0 | 0 | 3.4117 | 0 | 0 | 0 | 0 | 0 | 3.4117 | 81.5298 | 0 | 9000 | 9000 | 4473.3302 | 40.26 | 917.5885 | 36.8483 | 836.0587 | 0 | 2111.2594 |  | 2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
[15 empty] | Total Cost (NPV) | 35.4038 |  |  |  |  | Total Revenue (NPV) | 353.29 | IRR | 0% |  | $/AF at Life of Project (Year 2060) | 205.8833 |  | 2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
1 - If LRP Subsidies are applicable, an Increase in supplies occuring after 2125 will require a modification to the current analysis. | [28 empty] | 2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
[29 empty] | 2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
[29 empty] | 2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
[29 empty] | 2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
[29 empty] | 2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
[29 empty] | 2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
[29 empty] | 2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
[29 empty] | 2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
[29 empty] | 2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
[29 empty] | 2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F10: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L10: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT10: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S12: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.
Note on AM13: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on AM19: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.

## Steps 1 thru 3
Projected Costs and Revenues Through Step | [7 empty] | 3
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 0.0425 | 0.029 | 0.03 | 0.04 | 0 | 30 | 0.05 | No | 475 | 15 | Treated | 0.036 | Yes | 73
CHANGE THESE VALUES ONLY ON 'NPV SUMMARY' SHEET
ONLY CHANGE WATER RATES IN 'Rates' SHEET. CHANGES WILL BE REFLECTED HERE.
Base
|  | Projected Annual Cost 2018 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$35.404) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$367.736) | [5 empty] | LADWP Rate of Return |  |  |  |  | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Step | FYE | Capital | O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  | Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
0 | 2018 | 1.5 |  | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1015 | 0 | 0 | - | - | - | - |  | 2007 | 478 | 2007 | - | 478 | 331 | 2018 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2018 | 0 | 0
1 | 2019 | 2.3 |  | 0.365 | 2.3667 | 0 | 0.3796 | 2.3667 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 2.7463 | 4.2463 | -5000 | 5000 | 10000 | 1053 | 10.53 | 10.53 | 7.7837 | 6.2837 | 2019 | 628.37 |  | 2008 | 508 | 2008 | - | 508 | 351 | 2019 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 2019 | 0 | 0
1 | 2020 | 3 | 0 | 0.365 | 3.1765 | 0 | 0.39478 | 3.1765 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 3.5713 | 7.8176 | -5000 | 5000 | 10000 | 1092 | 10.92 | 21.45 | 7.3487 | 13.6324 | 0 | 681.6196 |  | 2009 | 579 | 2009 | - | 579 | 412 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
1 | 2021 | 3.5 | 0 | 0.365 | 3.8134 | 0 | 0.41058 | 3.8134 | 0 | 0.41058 | 0 | 0 | 0 | 0 | 0 | 4.224 | 12.0416 | -5000 | 5000 | 10000 | 1123 | 11.23 | 32.68 | 7.006 | 20.6384 | 0 | 687.9467 |  | 2010 | 701 | 2010 | - | 701 | 484 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
2 | 2022 | 0 | 0 | 0.657 | 0 | 0 | 0.7686 | 0 | 0 | 0.7686 | 0 | 0 | 0 | 0 | 0 | 0.7686 | 12.8102 | -5000 | 9000 | 14000 | 1164 | 16.296 | 48.976 | 15.5274 | 36.1658 | 0 | 821.9501 |  | 2011 | 744 | 2011 | - | 744 | 527 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
2 | 2023 | 0 | 0 | 0.657 | 0 | 0 | 0.79934 | 0 | 0 | 0.79934 | 0 | 0 | 0 | 0 | 0 | 0.79934 | 13.6095 | -5000 | 9000 | 14000 | 1205 | 16.87 | 65.846 | 16.0707 | 52.2365 | 0 | 900.6287 |  | 2012 | 794 | 2012 | - | 794 | 560 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
2 | 2024 | 0 | 0 | 0.657 | 0 | 0 | 0.83131 | 0 | 0 | 0.83131 | 0 | 0 | 0 | 0 | 0 | 0.83131 | 14.4409 | -5000 | 9000 | 14000 | 1249 | 17.486 | 83.332 | 16.6547 | 68.8911 | 0 | 956.8215 |  | 2013 | 847 | 2013 | - | 847 | 593 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
3 | 2025 | 0 | 0 | 0.657 | 0 | 0 | 0.86457 | 0 | 0 | 0.86457 | 0 | 0 | 0 | 0 | 0 | 0.86457 | 15.3054 | -5000 | 9000 | 14000 | 1296 | 18.144 | 101.476 | 17.2794 | 86.1706 | 0 | 1001.9835 |  | 2014 | 890 | 2014 | - | 890 | 593 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
3 | 2026 | 0 | 0 | 0.657 | 0 | 0 | 0.89915 | 0 | 0 | 0.89915 | 0 | 0 | 0 | 0 | 0 | 0.89915 | 16.2046 | -5000 | 9000 | 14000 | 1344 | 18.816 | 120.292 | 17.9169 | 104.0874 | 0 | 1040.8743 |  | 2015 | 923 | 2015 | - | 923 | 582 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
3 | 2027 | 0 | 0 | 0.657 | 0 | 0 | 0.93512 | 0 | 0 | 0.93512 | 0 | 0 | 0 | 0 | 0 | 0.93512 | 17.1397 | -5000 | 9000 | 14000 | 1392.384 | 19.4934 | 139.7854 | 18.5583 | 122.6457 | 0 | 1075.8394 |  | 2016 | 942 | 2016 | - | 942 | 594 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
MP Complete | 2028 | 0 | 0 | 0.657 | 0 | 0 | 0.97252 | 0 | 0 | 0.97252 | 0 | 0 | 0 | 0 | 0 | 0.97252 | 18.1122 | 0 | 9000 | 9000 | 1442.5098 | 12.9826 | 152.768 | 12.0101 | 134.6558 | 0 | 1094.7623 |  | 2017 | 979 | 2017 | - | 979 | 666 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
MP Complete | 2029 | 0 | 0 | 0.657 | 0 | 0 | 1.0114 | 0 | 0 | 1.0114 | 0 | 0 | 0 | 0 | 0 | 1.0114 | 19.1236 | 0 | 9000 | 9000 | 1494.4402 | 13.45 | 166.2179 | 12.4385 | 147.0943 | 0 | 1114.3508 |  | 2018 | 1015 | 2018 | - | 1015 | 695 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
MP Complete | 2030 | 0 | 0 | 0.657 | 0 | 0 | 1.0519 | 0 | 0 | 1.0519 | 0 | 0 | 0 | 0 | 0 | 1.0519 | 20.1755 | 0 | 9000 | 9000 | 1548.24 | 13.9342 | 180.1521 | 12.8823 | 159.9766 | 0 | 1134.5857 |  | 2019 | 1053 | 2019 | - | 1053 | 738 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
MP Complete | 2031 | 0 | 0 | 0.657 | 0 | 0 | 1.094 | 0 | 0 | 1.094 | 0 | 0 | 0 | 0 | 0 | 1.094 | 21.2695 | 0 | 9000 | 9000 | 1603.9767 | 14.4358 | 194.5879 | 13.3418 | 173.3184 | 0 | 1155.4561 |  | 2020 | 1092 | 2020 | - | 1092 | 783 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
MP Complete | 2032 | 0 | 0 | 0.657 | 0 | 0 | 1.1377 | 0 | 0 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 1.1377 | 22.4072 | 0 | 9000 | 9000 | 1661.7198 | 14.9555 | 209.5434 | 13.8178 | 187.1362 | 0 | 1176.9571 |  | 2021 | 1123 | 2021 | - | 1123 | 835 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
MP Complete | 2033 | 0 | 0 | 0.657 | 0 | 0 | 1.1832 | 0 | 0 | 1.1832 | 0 | 0 | 0 | 0 | 0 | 1.1832 | 23.5904 | 0 | 9000 | 9000 | 1721.5417 | 15.4939 | 225.0372 | 14.3107 | 201.4468 | 0 | 1199.0883 |  | 2022 | 1164 | 2022 | - | 1164 | 876 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
MP Complete | 2034 | 0 | 0 | 0.657 | 0 | 0 | 1.2305 | 0 | 0 | 1.2305 | 0 | 0 | 0 | 0 | 0 | 1.2305 | 24.8209 | 0 | 9000 | 9000 | 1783.5172 | 16.0517 | 241.0889 | 14.8211 | 216.2679 | 0 | 1221.8528 |  | 2023 | 1205 | 2023 | - | 1205 | 917 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
MP Complete | 2035 | 0 | 0 | 0.657 | 0 | 0 | 1.2798 | 0 | 0 | 1.2798 | 0 | 0 | 0 | 0 | 0 | 1.2798 | 26.1007 | 0 | 9000 | 9000 | 1847.7239 | 16.6295 | 257.7184 | 15.3497 | 231.6177 | 0 | 1245.2564 |  | 2024 | 1249 | 2024 | - | 1249 | 961 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
MP Complete | 2036 | 0 | 0 | 0.657 | 0 | 0 | 1.331 | 0 | 0 | 1.331 | 0 | 0 | 0 | 0 | 0 | 1.331 | 27.4317 | 0 | 9000 | 9000 | 1914.2419 | 17.2282 | 274.9466 | 15.8972 | 247.5149 | 0 | 1269.3072 |  | 2025 | 1296 | 2025 | - | 1296 | 1008 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
MP Complete | 2037 | 0 | 0 | 0.657 | 0 | 0 | 1.3842 | 0 | 0 | 1.3842 | 0 | 0 | 0 | 0 | 0 | 1.3842 | 28.8159 | 0 | 9000 | 9000 | 1983.1546 | 17.8484 | 292.795 | 16.4642 | 263.9791 | 0 | 1294.0152 |  | 2026 | 1344 | 2026 | - | 1344 | 1056 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
MP Complete | 2038 | 0 | 0 | 0.657 | 0 | 0 | 1.4396 | 0 | 0 | 1.4396 | 0 | 0 | 0 | 0 | 0 | 1.4396 | 30.2554 | 0 | 9000 | 9000 | 2054.5482 | 18.4909 | 311.2859 | 17.0514 | 281.0305 | 0 | 1319.3919 |  | 2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
MP Complete | 2039 | 0 | 0 | 0.657 | 0 | 0 | 1.4972 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 0 | 1.4972 | 31.7526 | 0 | 9000 | 9000 | 2128.5119 | 19.1566 | 330.4425 | 17.6595 | 298.6899 | 0 | 1345.4501 |  | 2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
MP Complete | 2040 | 0 | 0 | 0.657 | 0 | 0 | 1.557 | 0 | 0 | 1.557 | 0 | 0 | 0 | 0 | 0 | 1.557 | 33.3096 | 0 | 9000 | 9000 | 2205.1384 | 19.8462 | 350.2888 | 18.2892 | 316.9791 | 0 | 1372.204 |  | 2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
MP Complete | 2041 | 0 | 0 | 0.657 | 0 | 0 | 1.6193 | 0 | 0 | 1.6193 | 0 | 0 | 0 | 0 | 0 | 1.6193 | 34.9289 | 0 | 9000 | 9000 | 2284.5233 | 20.5607 | 370.8495 | 18.9414 | 335.9205 | 0 | 1399.6688 |  | 2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
MP Complete | 2042 | 0 | 0 | 0.657 | 0 | 0 | 1.6841 | 0 | 0 | 1.6841 | 0 | 0 | 0 | 0 | 0 | 1.6841 | 36.613 | 0 | 9000 | 9000 | 2366.7662 | 21.3009 | 392.1504 | 19.6168 | 355.5373 | 0 | 1427.8608 |  | 2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
MP Complete | 2043 | 0 | 0 | 0.657 | 0 | 0 | 1.7515 | 0 | 0 | 1.7515 | 0 | 0 | 0 | 0 | 0 | 1.7515 | 38.3645 | 0 | 9000 | 9000 | 2451.9698 | 22.0677 | 414.2181 | 20.3163 | 375.8536 | 0 | 1456.7969 |  | 2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
MP Complete | 2044 | 0 | 0 | 0.657 | 0 | 0 | 1.8215 | 0 | 0 | 1.8215 | 0 | 0 | 0 | 0 | 0 | 1.8215 | 40.186 | 0 | 9000 | 9000 | 2540.2407 | 22.8622 | 437.0803 | 21.0407 | 396.8943 | 0 | 1486.4953 |  | 2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
MP Complete | 2045 | 0 | 0 | 0.657 | 0 | 0 | 1.8944 | 0 | 0 | 1.8944 | 0 | 0 | 0 | 0 | 0 | 1.8944 | 42.0804 | 0 | 9000 | 9000 | 2631.6893 | 23.6852 | 460.7655 | 21.7908 | 418.6851 | 0 | 1516.9749 |  | 2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
MP Complete | 2046 | 0 | 0 | 0.657 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 44.0505 | 0 | 9000 | 9000 | 2726.4302 | 24.5379 | 485.3033 | 22.5677 | 441.2528 | 0 | 1548.2555 |  | 2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
MP Complete | 2047 | 0 | 0 | 0.657 | 0 | 0 | 2.049 | 0 | 0 | 2.049 | 0 | 0 | 0 | 0 | 0 | 2.049 | 46.0995 | 0 | 9000 | 9000 | 2824.5816 | 25.4212 | 510.7246 | 23.3723 | 464.6251 | 0 | 1580.3574 |  | 2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
MP Complete | 2048 | 0 | 0 | 0.657 | 0 | 0 | 2.1309 | 0 | 0 | 2.1309 | 0 | 0 | 0 | 0 | 0 | 2.1309 | 48.2304 | 0 | 9000 | 9000 | 2926.2666 | 26.3364 | 537.061 | 24.2055 | 488.8306 | 0 | 1613.3022 |  | 2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
MP Complete | 2049 | 0 | 0 | 0.657 | 0 | 0 | 2.2161 | 0 | 0 | 2.2161 | 0 | 0 | 0 | 0 | 0 | 2.2161 | 50.4465 | 0 | 9000 | 9000 | 3031.6122 | 27.2845 | 564.3455 | 25.0684 | 513.8989 | 0 | 1647.112 |  | 2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
MP Complete | 2050 | 0 | 0 | 0.657 | 0 | 0 | 2.3048 | 0 | 0 | 2.3048 | 0 | 0 | 0 | 0 | 0 | 2.3048 | 52.7513 | 0 | 9000 | 9000 | 3140.7502 | 28.2668 | 592.6122 | 25.962 | 539.8609 | 0 | 1681.8096 |  | 2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
MP Complete | 2051 | 0 | 0 | 0.657 | 0 | 0 | 2.397 | 0 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 2.397 | 55.1483 | 0 | 9000 | 9000 | 3253.8172 | 29.2844 | 621.8966 | 26.8874 | 566.7483 | 0 | 1717.419 |  | 2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
MP Complete | 2052 | 0 | 0 | 0.657 | 0 | 0 | 2.4929 | 0 | 0 | 2.4929 | 0 | 0 | 0 | 0 | 0 | 2.4929 | 57.6412 | 0 | 9000 | 9000 | 3370.9546 | 30.3386 | 652.2352 | 27.8457 | 594.594 | 0 | 1753.9646 |  | 2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
MP Complete | 2053 | 0 | 0 | 0.657 | 0 | 0 | 2.5926 | 0 | 0 | 2.5926 | 0 | 0 | 0 | 0 | 0 | 2.5926 | 60.2338 | 0 | 9000 | 9000 | 3492.309 | 31.4308 | 683.666 | 28.8382 | 623.4322 | 0 | 1791.4718 | 173.0855 | 2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
MP Complete | 2054 | 0 | 0 | 0.657 | 0 | 0 | 2.6963 | 0 | 0 | 2.6963 | 0 | 0 | 0 | 0 | 0 | 2.6963 | 62.93 | 0 | 9000 | 9000 | 3618.0321 | 32.5623 | 716.2282 | 29.866 | 653.2982 | 0 | 1829.9669 |  | 2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
MP Complete | 2055 | 0 | 0 | 0.657 | 0 | 0 | 2.8041 | 0 | 0 | 2.8041 | 0 | 0 | 0 | 0 | 0 | 2.8041 | 65.7342 | 0 | 9000 | 9000 | 3748.2813 | 33.7345 | 749.9628 | 30.9304 | 684.2286 | 0 | 1869.477 |  | 2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
MP Complete | 2056 | 0 | 0 | 0.657 | 0 | 0 | 2.9163 | 0 | 0 | 2.9163 | 0 | 0 | 0 | 0 | 0 | 2.9163 | 68.6505 | 0 | 9000 | 9000 | 3883.2194 | 34.949 | 784.9117 | 32.0327 | 716.2613 | 0 | 1910.03 |  | 2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
MP Complete | 2057 | 0 | 0 | 0.657 | 0 | 0 | 3.033 | 0 | 0 | 3.033 | 0 | 0 | 0 | 0 | 0 | 3.033 | 71.6834 | 0 | 9000 | 9000 | 4023.0153 | 36.2071 | 821.1189 | 33.1742 | 749.4355 | 0 | 1951.6548 |  | 2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
MP Complete | 2058 | 0 | 0 | 0.657 | 0 | 0 | 3.1543 | 0 | 0 | 3.1543 | 0 | 0 | 0 | 0 | 0 | 3.1543 | 74.8377 | 0 | 9000 | 9000 | 4167.8439 | 37.5106 | 858.6295 | 34.3563 | 783.7918 | 0 | 1994.3811 |  | 2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
MP Complete | 2059 | 0 | 0 | 0.657 | 0 | 0 | 3.2804 | 0 | 0 | 3.2804 | 0 | 0 | 0 | 0 | 0 | 3.2804 | 78.1181 | 0 | 9000 | 9000 | 4317.8863 | 38.861 | 897.4905 | 35.5805 | 819.3723 | 0 | 2038.2396 |  | 2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
MP Complete | 2060 | 0 | 0 | 0.657 | 0 | 0 | 3.4117 | 0 | 0 | 3.4117 | 0 | 0 | 0 | 0 | 0 | 3.4117 | 81.5298 | 0 | 9000 | 9000 | 4473.3302 | 40.26 | 937.7504 | 36.8483 | 856.2206 | 0 | 2083.2619 |  | 2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
[15 empty] | Total Cost (NPV) | 35.4038 |  |  |  |  | Total Revenue (NPV) | 367.7358 | IRR | 0% |  | $/AF at Life of Project (Year 2060) | 198.3694 |  | 2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
1 - If LRP Subsidies are applicable, an Increase in supplies occuring after 2125 will require a modification to the current analysis. | [28 empty] | 2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
[29 empty] | 2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
[29 empty] | 2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
[29 empty] | 2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
[29 empty] | 2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
[29 empty] | 2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
[29 empty] | 2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
[29 empty] | 2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
[29 empty] | 2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
[29 empty] | 2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F10: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L10: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT10: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S12: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.
Note on AM13: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on AM19: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.

## Steps 1 thru 4
Projected Costs and Revenues Through Step | [7 empty] | 4
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 0.0425 | 0.029 | 0.03 | 0.04 | 0 | 30 | 0.05 | No | 475 | 15 | Treated | 0.036 | Yes | 73
CHANGE THESE VALUES ONLY ON 'NPV SUMMARY' SHEET
ONLY CHANGE WATER RATES IN 'Rates' SHEET. CHANGES WILL BE REFLECTED HERE.
Base
|  | Projected Annual Cost 2018 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$35.404) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$381.918) | [5 empty] | LADWP Rate of Return |  |  |  |  | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Step | FYE | Capital | O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  | Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
0 | 2018 | 1.5 |  | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1015 | 0 | 0 | - | - | - | - |  | 2007 | 478 | 2007 | - | 478 | 331 | 2018 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2018 | 0 | 0
1 | 2019 | 2.3 |  | 0.365 | 2.3667 | 0 | 0.3796 | 2.3667 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 2.7463 | 4.2463 | -5000 | 5000 | 10000 | 1053 | 10.53 | 10.53 | 7.7837 | 6.2837 | 2019 | 628.37 |  | 2008 | 508 | 2008 | - | 508 | 351 | 2019 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 2019 | 0 | 0
1 | 2020 | 3 | 0 | 0.365 | 3.1765 | 0 | 0.39478 | 3.1765 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 3.5713 | 7.8176 | -5000 | 5000 | 10000 | 1092 | 10.92 | 21.45 | 7.3487 | 13.6324 | 0 | 681.6196 |  | 2009 | 579 | 2009 | - | 579 | 412 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
1 | 2021 | 3.5 | 0 | 0.365 | 3.8134 | 0 | 0.41058 | 3.8134 | 0 | 0.41058 | 0 | 0 | 0 | 0 | 0 | 4.224 | 12.0416 | -5000 | 5000 | 10000 | 1123 | 11.23 | 32.68 | 7.006 | 20.6384 | 0 | 687.9467 |  | 2010 | 701 | 2010 | - | 701 | 484 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
2 | 2022 | 0 | 0 | 0.657 | 0 | 0 | 0.7686 | 0 | 0 | 0.7686 | 0 | 0 | 0 | 0 | 0 | 0.7686 | 12.8102 | -5000 | 9000 | 14000 | 1164 | 16.296 | 48.976 | 15.5274 | 36.1658 | 0 | 821.9501 |  | 2011 | 744 | 2011 | - | 744 | 527 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
2 | 2023 | 0 | 0 | 0.657 | 0 | 0 | 0.79934 | 0 | 0 | 0.79934 | 0 | 0 | 0 | 0 | 0 | 0.79934 | 13.6095 | -5000 | 9000 | 14000 | 1205 | 16.87 | 65.846 | 16.0707 | 52.2365 | 0 | 900.6287 |  | 2012 | 794 | 2012 | - | 794 | 560 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
2 | 2024 | 0 | 0 | 0.657 | 0 | 0 | 0.83131 | 0 | 0 | 0.83131 | 0 | 0 | 0 | 0 | 0 | 0.83131 | 14.4409 | -5000 | 9000 | 14000 | 1249 | 17.486 | 83.332 | 16.6547 | 68.8911 | 0 | 956.8215 |  | 2013 | 847 | 2013 | - | 847 | 593 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
3 | 2025 | 0 | 0 | 0.657 | 0 | 0 | 0.86457 | 0 | 0 | 0.86457 | 0 | 0 | 0 | 0 | 0 | 0.86457 | 15.3054 | -5000 | 9000 | 14000 | 1296 | 18.144 | 101.476 | 17.2794 | 86.1706 | 0 | 1001.9835 |  | 2014 | 890 | 2014 | - | 890 | 593 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
3 | 2026 | 0 | 0 | 0.657 | 0 | 0 | 0.89915 | 0 | 0 | 0.89915 | 0 | 0 | 0 | 0 | 0 | 0.89915 | 16.2046 | -5000 | 9000 | 14000 | 1344 | 18.816 | 120.292 | 17.9169 | 104.0874 | 0 | 1040.8743 |  | 2015 | 923 | 2015 | - | 923 | 582 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
3 | 2027 | 0 | 0 | 0.657 | 0 | 0 | 0.93512 | 0 | 0 | 0.93512 | 0 | 0 | 0 | 0 | 0 | 0.93512 | 17.1397 | -5000 | 9000 | 14000 | 1392.384 | 19.4934 | 139.7854 | 18.5583 | 122.6457 | 0 | 1075.8394 |  | 2016 | 942 | 2016 | - | 942 | 594 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
4 | 2028 | 0 | 0 | 0.657 | 0 | 0 | 0.97252 | 0 | 0 | 0.97252 | 0 | 0 | 0 | 0 | 0 | 0.97252 | 18.1122 | -5000 | 9000 | 14000 | 1442.5098 | 20.1951 | 159.9805 | 19.2226 | 141.8683 | 0 | 1108.3462 |  | 2017 | 979 | 2017 | - | 979 | 666 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
4 | 2029 | 0 | 0 | 0.657 | 0 | 0 | 1.0114 | 0 | 0 | 1.0114 | 0 | 0 | 0 | 0 | 0 | 1.0114 | 19.1236 | -5000 | 9000 | 14000 | 1494.4402 | 20.9222 | 180.9027 | 19.9107 | 161.7791 | 0 | 1139.2891 |  | 2018 | 1015 | 2018 | - | 1015 | 695 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
4 | 2030 | 0 | 0 | 0.657 | 0 | 0 | 1.0519 | 0 | 0 | 1.0519 | 0 | 0 | 0 | 0 | 0 | 1.0519 | 20.1755 | -5000 | 9000 | 14000 | 1548.24 | 21.6754 | 202.578 | 20.6235 | 182.4025 | 0 | 1169.247 |  | 2019 | 1053 | 2019 | - | 1053 | 738 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
MP Complete | 2031 | 0 | 0 | 0.657 | 0 | 0 | 1.094 | 0 | 0 | 1.094 | 0 | 0 | 0 | 0 | 0 | 1.094 | 21.2695 | 0 | 9000 | 9000 | 1603.9767 | 14.4358 | 217.0138 | 13.3418 | 195.7444 | 0 | 1186.3295 |  | 2020 | 1092 | 2020 | - | 1092 | 783 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
MP Complete | 2032 | 0 | 0 | 0.657 | 0 | 0 | 1.1377 | 0 | 0 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 1.1377 | 22.4072 | 0 | 9000 | 9000 | 1661.7198 | 14.9555 | 231.9693 | 13.8178 | 209.5621 | 0 | 1204.3801 |  | 2021 | 1123 | 2021 | - | 1123 | 835 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
MP Complete | 2033 | 0 | 0 | 0.657 | 0 | 0 | 1.1832 | 0 | 0 | 1.1832 | 0 | 0 | 0 | 0 | 0 | 1.1832 | 23.5904 | 0 | 9000 | 9000 | 1721.5417 | 15.4939 | 247.4632 | 14.3107 | 223.8728 | 0 | 1223.3486 |  | 2022 | 1164 | 2022 | - | 1164 | 876 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
MP Complete | 2034 | 0 | 0 | 0.657 | 0 | 0 | 1.2305 | 0 | 0 | 1.2305 | 0 | 0 | 0 | 0 | 0 | 1.2305 | 24.8209 | 0 | 9000 | 9000 | 1783.5172 | 16.0517 | 263.5148 | 14.8211 | 238.6939 | 0 | 1243.1974 |  | 2023 | 1205 | 2023 | - | 1205 | 917 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
MP Complete | 2035 | 0 | 0 | 0.657 | 0 | 0 | 1.2798 | 0 | 0 | 1.2798 | 0 | 0 | 0 | 0 | 0 | 1.2798 | 26.1007 | 0 | 9000 | 9000 | 1847.7239 | 16.6295 | 280.1444 | 15.3497 | 254.0436 | 0 | 1263.8987 |  | 2024 | 1249 | 2024 | - | 1249 | 961 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
MP Complete | 2036 | 0 | 0 | 0.657 | 0 | 0 | 1.331 | 0 | 0 | 1.331 | 0 | 0 | 0 | 0 | 0 | 1.331 | 27.4317 | 0 | 9000 | 9000 | 1914.2419 | 17.2282 | 297.3725 | 15.8972 | 269.9409 | 0 | 1285.4327 |  | 2025 | 1296 | 2025 | - | 1296 | 1008 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
MP Complete | 2037 | 0 | 0 | 0.657 | 0 | 0 | 1.3842 | 0 | 0 | 1.3842 | 0 | 0 | 0 | 0 | 0 | 1.3842 | 28.8159 | 0 | 9000 | 9000 | 1983.1546 | 17.8484 | 315.2209 | 16.4642 | 286.4051 | 0 | 1307.7856 |  | 2026 | 1344 | 2026 | - | 1344 | 1056 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
MP Complete | 2038 | 0 | 0 | 0.657 | 0 | 0 | 1.4396 | 0 | 0 | 1.4396 | 0 | 0 | 0 | 0 | 0 | 1.4396 | 30.2554 | 0 | 9000 | 9000 | 2054.5482 | 18.4909 | 333.7119 | 17.0514 | 303.4564 | 0 | 1330.9492 |  | 2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
MP Complete | 2039 | 0 | 0 | 0.657 | 0 | 0 | 1.4972 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 0 | 1.4972 | 31.7526 | 0 | 9000 | 9000 | 2128.5119 | 19.1566 | 352.8685 | 17.6595 | 321.1159 | 0 | 1354.9193 |  | 2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
MP Complete | 2040 | 0 | 0 | 0.657 | 0 | 0 | 1.557 | 0 | 0 | 1.557 | 0 | 0 | 0 | 0 | 0 | 1.557 | 33.3096 | 0 | 9000 | 9000 | 2205.1384 | 19.8462 | 372.7147 | 18.2892 | 339.4051 | 0 | 1379.6955 |  | 2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
MP Complete | 2041 | 0 | 0 | 0.657 | 0 | 0 | 1.6193 | 0 | 0 | 1.6193 | 0 | 0 | 0 | 0 | 0 | 1.6193 | 34.9289 | 0 | 9000 | 9000 | 2284.5233 | 20.5607 | 393.2754 | 18.9414 | 358.3465 | 0 | 1405.2803 |  | 2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
MP Complete | 2042 | 0 | 0 | 0.657 | 0 | 0 | 1.6841 | 0 | 0 | 1.6841 | 0 | 0 | 0 | 0 | 0 | 1.6841 | 36.613 | 0 | 9000 | 9000 | 2366.7662 | 21.3009 | 414.5763 | 19.6168 | 377.9633 | 0 | 1431.6791 |  | 2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
MP Complete | 2043 | 0 | 0 | 0.657 | 0 | 0 | 1.7515 | 0 | 0 | 1.7515 | 0 | 0 | 0 | 0 | 0 | 1.7515 | 38.3645 | 0 | 9000 | 9000 | 2451.9698 | 22.0677 | 436.644 | 20.3163 | 398.2796 | 0 | 1458.8995 |  | 2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
MP Complete | 2044 | 0 | 0 | 0.657 | 0 | 0 | 1.8215 | 0 | 0 | 1.8215 | 0 | 0 | 0 | 0 | 0 | 1.8215 | 40.186 | 0 | 9000 | 9000 | 2540.2407 | 22.8622 | 459.5062 | 21.0407 | 419.3202 | 0 | 1486.9511 |  | 2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
MP Complete | 2045 | 0 | 0 | 0.657 | 0 | 0 | 1.8944 | 0 | 0 | 1.8944 | 0 | 0 | 0 | 0 | 0 | 1.8944 | 42.0804 | 0 | 9000 | 9000 | 2631.6893 | 23.6852 | 483.1914 | 21.7908 | 441.111 | 0 | 1515.8455 |  | 2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
MP Complete | 2046 | 0 | 0 | 0.657 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 44.0505 | 0 | 9000 | 9000 | 2726.4302 | 24.5379 | 507.7293 | 22.5677 | 463.6788 | 0 | 1545.5959 |  | 2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
MP Complete | 2047 | 0 | 0 | 0.657 | 0 | 0 | 2.049 | 0 | 0 | 2.049 | 0 | 0 | 0 | 0 | 0 | 2.049 | 46.0995 | 0 | 9000 | 9000 | 2824.5816 | 25.4212 | 533.1505 | 23.3723 | 487.051 | 0 | 1576.217 |  | 2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
MP Complete | 2048 | 0 | 0 | 0.657 | 0 | 0 | 2.1309 | 0 | 0 | 2.1309 | 0 | 0 | 0 | 0 | 0 | 2.1309 | 48.2304 | 0 | 9000 | 9000 | 2926.2666 | 26.3364 | 559.4869 | 24.2055 | 511.2565 | 0 | 1607.7249 |  | 2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
MP Complete | 2049 | 0 | 0 | 0.657 | 0 | 0 | 2.2161 | 0 | 0 | 2.2161 | 0 | 0 | 0 | 0 | 0 | 2.2161 | 50.4465 | 0 | 9000 | 9000 | 3031.6122 | 27.2845 | 586.7714 | 25.0684 | 536.3249 | 0 | 1640.1373 |  | 2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
MP Complete | 2050 | 0 | 0 | 0.657 | 0 | 0 | 2.3048 | 0 | 0 | 2.3048 | 0 | 0 | 0 | 0 | 0 | 2.3048 | 52.7513 | 0 | 9000 | 9000 | 3140.7502 | 28.2668 | 615.0382 | 25.962 | 562.2868 | 0 | 1673.4728 |  | 2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
MP Complete | 2051 | 0 | 0 | 0.657 | 0 | 0 | 2.397 | 0 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 2.397 | 55.1483 | 0 | 9000 | 9000 | 3253.8172 | 29.2844 | 644.3225 | 26.8874 | 589.1742 | 0 | 1707.7513 |  | 2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
MP Complete | 2052 | 0 | 0 | 0.657 | 0 | 0 | 2.4929 | 0 | 0 | 2.4929 | 0 | 0 | 0 | 0 | 0 | 2.4929 | 57.6412 | 0 | 9000 | 9000 | 3370.9546 | 30.3386 | 674.6611 | 27.8457 | 617.0199 | 0 | 1742.9942 |  | 2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
MP Complete | 2053 | 0 | 0 | 0.657 | 0 | 0 | 2.5926 | 0 | 0 | 2.5926 | 0 | 0 | 0 | 0 | 0 | 2.5926 | 60.2338 | 0 | 9000 | 9000 | 3492.309 | 31.4308 | 706.0919 | 28.8382 | 645.8581 | 0 | 1779.2235 | 165.9332 | 2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
MP Complete | 2054 | 0 | 0 | 0.657 | 0 | 0 | 2.6963 | 0 | 0 | 2.6963 | 0 | 0 | 0 | 0 | 0 | 2.6963 | 62.93 | 0 | 9000 | 9000 | 3618.0321 | 32.5623 | 738.6542 | 29.866 | 675.7241 | 0 | 1816.4628 |  | 2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
MP Complete | 2055 | 0 | 0 | 0.657 | 0 | 0 | 2.8041 | 0 | 0 | 2.8041 | 0 | 0 | 0 | 0 | 0 | 2.8041 | 65.7342 | 0 | 9000 | 9000 | 3748.2813 | 33.7345 | 772.3887 | 30.9304 | 706.6545 | 0 | 1854.7363 |  | 2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
MP Complete | 2056 | 0 | 0 | 0.657 | 0 | 0 | 2.9163 | 0 | 0 | 2.9163 | 0 | 0 | 0 | 0 | 0 | 2.9163 | 68.6505 | 0 | 9000 | 9000 | 3883.2194 | 34.949 | 807.3377 | 32.0327 | 738.6872 | 0 | 1894.0698 |  | 2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
MP Complete | 2057 | 0 | 0 | 0.657 | 0 | 0 | 3.033 | 0 | 0 | 3.033 | 0 | 0 | 0 | 0 | 0 | 3.033 | 71.6834 | 0 | 9000 | 9000 | 4023.0153 | 36.2071 | 843.5448 | 33.1742 | 771.8614 | 0 | 1934.4897 |  | 2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
MP Complete | 2058 | 0 | 0 | 0.657 | 0 | 0 | 3.1543 | 0 | 0 | 3.1543 | 0 | 0 | 0 | 0 | 0 | 3.1543 | 74.8377 | 0 | 9000 | 9000 | 4167.8439 | 37.5106 | 881.0554 | 34.3563 | 806.2177 | 0 | 1976.0238 |  | 2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
MP Complete | 2059 | 0 | 0 | 0.657 | 0 | 0 | 3.2804 | 0 | 0 | 3.2804 | 0 | 0 | 0 | 0 | 0 | 3.2804 | 78.1181 | 0 | 9000 | 9000 | 4317.8863 | 38.861 | 919.9164 | 35.5805 | 841.7983 | 0 | 2018.7009 |  | 2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
MP Complete | 2060 | 0 | 0 | 0.657 | 0 | 0 | 3.4117 | 0 | 0 | 3.4117 | 0 | 0 | 0 | 0 | 0 | 3.4117 | 81.5298 | 0 | 9000 | 9000 | 4473.3302 | 40.26 | 960.1764 | 36.8483 | 878.6466 | 0 | 2062.5506 |  | 2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
[15 empty] | Total Cost (NPV) | 35.4038 |  |  |  |  | Total Revenue (NPV) | 381.9178 | IRR | 0% |  | $/AF at Life of Project (Year 2060) | 191.3845 |  | 2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
1 - If LRP Subsidies are applicable, an Increase in supplies occuring after 2125 will require a modification to the current analysis. | [28 empty] | 2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
[29 empty] | 2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
[29 empty] | 2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
[29 empty] | 2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
[29 empty] | 2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
[29 empty] | 2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
[29 empty] | 2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
[29 empty] | 2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
[29 empty] | 2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
[29 empty] | 2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F10: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L10: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT10: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S12: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.
Note on AM13: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on AM19: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.

## Steps 1 thru 5
Projected Costs and Revenues Through Step | [7 empty] | 5
Scenario Assumptions
|  |  | Net Present Value (NPV) |  | Cost Escalation Rate |  |  | Financing |  |  | LRP Incentive |  |  | Avoided MWD Cost |  | Pumping Cost
| Year of Cost Projection | Project Starting Year | NPV Year | Discount Rate | Capital | O&M | Pumping | % of Capital Financed | Term (Years) | Borrowing Rate | Incentive Qualifying | Incentive ($/Acre-Ft) | Payment Option (Years) | MWD Tier 1 Water Rate | Long Term Rate Increase | Applicable ? | Pumping Cost ($/acre-ft)
| 2018 | 2018 | 2018 | 0.0425 | 0.029 | 0.03 | 0.04 | 0 | 30 | 0.05 | No | 475 | 15 | Treated | 0.036 | Yes | 73
CHANGE THESE VALUES ONLY ON 'NPV SUMMARY' SHEET
ONLY CHANGE WATER RATES IN 'Rates' SHEET. CHANGES WILL BE REFLECTED HERE.
Base
|  | Projected Annual Cost 2018 Dollar Year ($Million) |  |  | Projected Annual Cost Escalated Values ($Million) |  |  | Projected Annual Cost with Financing ($Million; NPV=$35.404) | [9 empty] | Avoided MWD Purchase ($Million; NPV=$395.836) | [5 empty] | LADWP Rate of Return |  |  |  |  | Rate Used in Analysis |  | MWD Water Rates |  |  |  | Financing Costs used in Analysis |  | Financing Costs (Note- only correct column is one with Cell J5 Borrowing Term) | [9 empty] | LRP Incentive used in Analysis |  | LRP Subsidy
Step | FYE | Capital | O&M | Pumping | Escalated Capital | Escalated O&M | Escalated Pumping | CASH Capital | CASH O&M | CASH Pumping | Financed Capital | Annual Payment | Financing Costs | Annual LRP Subsidy | Total LRP Subsidy | Year Cost | Cumulative Cost ($Million) | Water Demand (Acre-Ft) | Pumped Water (Acre-Ft) | 1Avoided Purchase (Acre-Ft) | MWD Water Rate ($/Acre-Ft) | Year Avoided Cost ("Revenue") ($Million) | Cumulative "Revenue" ($Million) | Year Net | Cumulative Net | Payback Year | Water Cost ($/a-f) |  | Year | Tier 1 Treated ($/Acre-Ft) | Year | Rate Increase Projection | Tier 1 - Treated ($/Acre-Ft) | Tier 1 - Untreated ($/Acre-Ft) | Year | 30 Year Borrowing Term | Year | 5 Year Borrowing Term | 10 Year Borrowing Term | 15 Year Borrowing Term | 18 Year Borrowing Term | 20 Year Borrowing Term | 25 Year Borrowing Term | 30 Year Borrowing Term | 35 Year Borrowing Term | 40 Year Borrowing Term | Year | 15 Year Term | Year | 15 Year Term | 25 Year Term
0 | 2018 | 1.5 |  | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1015 | 0 | 0 | - | - | - | - |  | 2007 | 478 | 2007 | - | 478 | 331 | 2018 | 0 | 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2018 | 0 | 0
1 | 2019 | 2.3 |  | 0.365 | 2.3667 | 0 | 0.3796 | 2.3667 | 0 | 0.3796 | 0 | 0 | 0 | 0 | 0 | 2.7463 | 4.2463 | -5000 | 5000 | 10000 | 1053 | 10.53 | 10.53 | 7.7837 | 6.2837 | 2019 | 628.37 |  | 2008 | 508 | 2008 | - | 508 | 351 | 2019 | 0 | 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019 | 0 | 2019 | 0 | 0
1 | 2020 | 3 | 0 | 0.365 | 3.1765 | 0 | 0.39478 | 3.1765 | 0 | 0.39478 | 0 | 0 | 0 | 0 | 0 | 3.5713 | 7.8176 | -5000 | 5000 | 10000 | 1092 | 10.92 | 21.45 | 7.3487 | 13.6324 | 0 | 681.6196 |  | 2009 | 579 | 2009 | - | 579 | 412 | 2020 | 0 | 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020 | 0 | 2020 | 0 | 0
1 | 2021 | 3.5 | 0 | 0.365 | 3.8134 | 0 | 0.41058 | 3.8134 | 0 | 0.41058 | 0 | 0 | 0 | 0 | 0 | 4.224 | 12.0416 | -5000 | 5000 | 10000 | 1123 | 11.23 | 32.68 | 7.006 | 20.6384 | 0 | 687.9467 |  | 2010 | 701 | 2010 | - | 701 | 484 | 2021 | 0 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021 | 0 | 2021 | 0 | 0
2 | 2022 | 0 | 0 | 0.657 | 0 | 0 | 0.7686 | 0 | 0 | 0.7686 | 0 | 0 | 0 | 0 | 0 | 0.7686 | 12.8102 | -5000 | 9000 | 14000 | 1164 | 16.296 | 48.976 | 15.5274 | 36.1658 | 0 | 821.9501 |  | 2011 | 744 | 2011 | - | 744 | 527 | 2022 | 0 | 2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2022 | 0 | 0
2 | 2023 | 0 | 0 | 0.657 | 0 | 0 | 0.79934 | 0 | 0 | 0.79934 | 0 | 0 | 0 | 0 | 0 | 0.79934 | 13.6095 | -5000 | 9000 | 14000 | 1205 | 16.87 | 65.846 | 16.0707 | 52.2365 | 0 | 900.6287 |  | 2012 | 794 | 2012 | - | 794 | 560 | 2023 | 0 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023 | 0 | 2023 | 0 | 0
2 | 2024 | 0 | 0 | 0.657 | 0 | 0 | 0.83131 | 0 | 0 | 0.83131 | 0 | 0 | 0 | 0 | 0 | 0.83131 | 14.4409 | -5000 | 9000 | 14000 | 1249 | 17.486 | 83.332 | 16.6547 | 68.8911 | 0 | 956.8215 |  | 2013 | 847 | 2013 | - | 847 | 593 | 2024 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2024 | 0 | 0
3 | 2025 | 0 | 0 | 0.657 | 0 | 0 | 0.86457 | 0 | 0 | 0.86457 | 0 | 0 | 0 | 0 | 0 | 0.86457 | 15.3054 | -5000 | 9000 | 14000 | 1296 | 18.144 | 101.476 | 17.2794 | 86.1706 | 0 | 1001.9835 |  | 2014 | 890 | 2014 | - | 890 | 593 | 2025 | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025 | 0 | 2025 | 0 | 0
3 | 2026 | 0 | 0 | 0.657 | 0 | 0 | 0.89915 | 0 | 0 | 0.89915 | 0 | 0 | 0 | 0 | 0 | 0.89915 | 16.2046 | -5000 | 9000 | 14000 | 1344 | 18.816 | 120.292 | 17.9169 | 104.0874 | 0 | 1040.8743 |  | 2015 | 923 | 2015 | - | 923 | 582 | 2026 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 2026 | 0 | 0
3 | 2027 | 0 | 0 | 0.657 | 0 | 0 | 0.93512 | 0 | 0 | 0.93512 | 0 | 0 | 0 | 0 | 0 | 0.93512 | 17.1397 | -5000 | 9000 | 14000 | 1392.384 | 19.4934 | 139.7854 | 18.5583 | 122.6457 | 0 | 1075.8394 |  | 2016 | 942 | 2016 | - | 942 | 594 | 2027 | 0 | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 0 | 2027 | 0 | 0
4 | 2028 | 0 | 0 | 0.657 | 0 | 0 | 0.97252 | 0 | 0 | 0.97252 | 0 | 0 | 0 | 0 | 0 | 0.97252 | 18.1122 | -5000 | 9000 | 14000 | 1442.5098 | 20.1951 | 159.9805 | 19.2226 | 141.8683 | 0 | 1108.3462 |  | 2017 | 979 | 2017 | - | 979 | 666 | 2028 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 2028 | 0 | 0
4 | 2029 | 0 | 0 | 0.657 | 0 | 0 | 1.0114 | 0 | 0 | 1.0114 | 0 | 0 | 0 | 0 | 0 | 1.0114 | 19.1236 | -5000 | 9000 | 14000 | 1494.4402 | 20.9222 | 180.9027 | 19.9107 | 161.7791 | 0 | 1139.2891 |  | 2018 | 1015 | 2018 | - | 1015 | 695 | 2029 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2029 | 0 | 2029 | 0 | 0
4 | 2030 | 0 | 0 | 0.657 | 0 | 0 | 1.0519 | 0 | 0 | 1.0519 | 0 | 0 | 0 | 0 | 0 | 1.0519 | 20.1755 | -5000 | 9000 | 14000 | 1548.24 | 21.6754 | 202.578 | 20.6235 | 182.4025 | 0 | 1169.247 |  | 2019 | 1053 | 2019 | - | 1053 | 738 | 2030 | 0 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 0 | 2030 | 0 | 0
5 | 2031 | 0 | 0 | 0.657 | 0 | 0 | 1.094 | 0 | 0 | 1.094 | 0 | 0 | 0 | 0 | 0 | 1.094 | 21.2695 | -5000 | 9000 | 14000 | 1603.9767 | 22.4557 | 225.0337 | 21.3617 | 203.7643 | 0 | 1198.6133 |  | 2020 | 1092 | 2020 | - | 1092 | 783 | 2031 | 0 | 2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2031 | 0 | 2031 | 0 | 0
5 | 2032 | 0 | 0 | 0.657 | 0 | 0 | 1.1377 | 0 | 0 | 1.1377 | 0 | 0 | 0 | 0 | 0 | 1.1377 | 22.4072 | -5000 | 9000 | 14000 | 1661.7198 | 23.2641 | 248.2978 | 22.1264 | 225.8906 | 0 | 1227.6664 |  | 2021 | 1123 | 2021 | - | 1123 | 835 | 2032 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 2032 | 0 | 0
5 | 2033 | 0 | 0 | 0.657 | 0 | 0 | 1.1832 | 0 | 0 | 1.1832 | 0 | 0 | 0 | 0 | 0 | 1.1832 | 23.5904 | -5000 | 9000 | 14000 | 1721.5417 | 24.1016 | 272.3994 | 22.9184 | 248.809 | 0 | 1256.611 |  | 2022 | 1164 | 2022 | - | 1164 | 876 | 2033 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 2033 | 0 | 0
MP Complete | 2034 | 0 | 0 | 0.657 | 0 | 0 | 1.2305 | 0 | 0 | 1.2305 | 0 | 0 | 0 | 0 | 0 | 1.2305 | 24.8209 | 0 | 9000 | 9000 | 1783.5172 | 16.0517 | 288.451 | 14.8211 | 263.6301 | 0 | 1273.5753 |  | 2023 | 1205 | 2023 | - | 1205 | 917 | 2034 | 0 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034 | 0 | 2034 | 0 | 0
MP Complete | 2035 | 0 | 0 | 0.657 | 0 | 0 | 1.2798 | 0 | 0 | 1.2798 | 0 | 0 | 0 | 0 | 0 | 1.2798 | 26.1007 | 0 | 9000 | 9000 | 1847.7239 | 16.6295 | 305.0805 | 15.3497 | 278.9798 | 0 | 1291.5733 |  | 2024 | 1249 | 2024 | - | 1249 | 961 | 2035 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 2035 | 0 | 0
MP Complete | 2036 | 0 | 0 | 0.657 | 0 | 0 | 1.331 | 0 | 0 | 1.331 | 0 | 0 | 0 | 0 | 0 | 1.331 | 27.4317 | 0 | 9000 | 9000 | 1914.2419 | 17.2282 | 322.3087 | 15.8972 | 294.877 | 0 | 1310.5647 |  | 2025 | 1296 | 2025 | - | 1296 | 1008 | 2036 | 0 | 2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2036 | 0 | 2036 | 0 | 0
MP Complete | 2037 | 0 | 0 | 0.657 | 0 | 0 | 1.3842 | 0 | 0 | 1.3842 | 0 | 0 | 0 | 0 | 0 | 1.3842 | 28.8159 | 0 | 9000 | 9000 | 1983.1546 | 17.8484 | 340.1571 | 16.4642 | 311.3412 | 0 | 1330.5181 |  | 2026 | 1344 | 2026 | - | 1344 | 1056 | 2037 | 0 | 2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2037 | 0 | 2037 | 0 | 0
MP Complete | 2038 | 0 | 0 | 0.657 | 0 | 0 | 1.4396 | 0 | 0 | 1.4396 | 0 | 0 | 0 | 0 | 0 | 1.4396 | 30.2554 | 0 | 9000 | 9000 | 2054.5482 | 18.4909 | 358.648 | 17.0514 | 328.3926 | 0 | 1351.4099 |  | 2027 | 1392.384 | 2027 | 3.6% | 1392.384 | 1094.016 | 2038 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 2038 | 0 | 0
MP Complete | 2039 | 0 | 0 | 0.657 | 0 | 0 | 1.4972 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 0 | 1.4972 | 31.7526 | 0 | 9000 | 9000 | 2128.5119 | 19.1566 | 377.8047 | 17.6595 | 346.0521 | 0 | 1373.2225 |  | 2028 | 1442.5098 | 2028 | 3.6% | 1442.5098 | 1133.4006 | 2039 | 0 | 2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2039 | 0 | 2039 | 0 | 0
MP Complete | 2040 | 0 | 0 | 0.657 | 0 | 0 | 1.557 | 0 | 0 | 1.557 | 0 | 0 | 0 | 0 | 0 | 1.557 | 33.3096 | 0 | 9000 | 9000 | 2205.1384 | 19.8462 | 397.6509 | 18.2892 | 364.3413 | 0 | 1395.9436 |  | 2029 | 1494.4402 | 2029 | 3.6% | 1494.4402 | 1174.203 | 2040 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 2040 | 0 | 0
MP Complete | 2041 | 0 | 0 | 0.657 | 0 | 0 | 1.6193 | 0 | 0 | 1.6193 | 0 | 0 | 0 | 0 | 0 | 1.6193 | 34.9289 | 0 | 9000 | 9000 | 2284.5233 | 20.5607 | 418.2116 | 18.9414 | 383.2827 | 0 | 1419.5654 |  | 2030 | 1548.24 | 2030 | 3.6% | 1548.24 | 1216.4743 | 2041 | 0 | 2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2041 | 0 | 2041 | 0 | 0
MP Complete | 2042 | 0 | 0 | 0.657 | 0 | 0 | 1.6841 | 0 | 0 | 1.6841 | 0 | 0 | 0 | 0 | 0 | 1.6841 | 36.613 | 0 | 9000 | 9000 | 2366.7662 | 21.3009 | 439.5125 | 19.6168 | 402.8995 | 0 | 1444.0841 |  | 2031 | 1603.9767 | 2031 | 3.6% | 1603.9767 | 1260.2674 | 2042 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 2042 | 0 | 0
MP Complete | 2043 | 0 | 0 | 0.657 | 0 | 0 | 1.7515 | 0 | 0 | 1.7515 | 0 | 0 | 0 | 0 | 0 | 1.7515 | 38.3645 | 0 | 9000 | 9000 | 2451.9698 | 22.0677 | 461.5802 | 20.3163 | 423.2157 | 0 | 1469.4991 |  | 2032 | 1661.7198 | 2032 | 3.6% | 1661.7198 | 1305.637 | 2043 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | 0 | 0
MP Complete | 2044 | 0 | 0 | 0.657 | 0 | 0 | 1.8215 | 0 | 0 | 1.8215 | 0 | 0 | 0 | 0 | 0 | 1.8215 | 40.186 | 0 | 9000 | 9000 | 2540.2407 | 22.8622 | 484.4424 | 21.0407 | 444.2564 | 0 | 1495.8128 |  | 2033 | 1721.5417 | 2033 | 3.6% | 1721.5417 | 1352.6399 | 2044 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 2044 | 0 | 0
MP Complete | 2045 | 0 | 0 | 0.657 | 0 | 0 | 1.8944 | 0 | 0 | 1.8944 | 0 | 0 | 0 | 0 | 0 | 1.8944 | 42.0804 | 0 | 9000 | 9000 | 2631.6893 | 23.6852 | 508.1276 | 21.7908 | 466.0472 | 0 | 1523.0302 |  | 2034 | 1783.5172 | 2034 | 3.6% | 1783.5172 | 1401.335 | 2045 | 0 | 2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2045 | 0 | 2045 | 0 | 0
MP Complete | 2046 | 0 | 0 | 0.657 | 0 | 0 | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 0 | 0 | 0 | 1.9701 | 44.0505 | 0 | 9000 | 9000 | 2726.4302 | 24.5379 | 532.6655 | 22.5677 | 488.615 | 0 | 1551.1586 |  | 2035 | 1847.7239 | 2035 | 3.6% | 1847.7239 | 1451.783 | 2046 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 2046 | 0 | 0
MP Complete | 2047 | 0 | 0 | 0.657 | 0 | 0 | 2.049 | 0 | 0 | 2.049 | 0 | 0 | 0 | 0 | 0 | 2.049 | 46.0995 | 0 | 9000 | 9000 | 2824.5816 | 25.4212 | 558.0867 | 23.3723 | 511.9872 | 0 | 1580.2075 |  | 2036 | 1914.2419 | 2036 | 3.6% | 1914.2419 | 1504.0472 | 2047 | 0 | 2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 2047 | 0 | 0
MP Complete | 2048 | 0 | 0 | 0.657 | 0 | 0 | 2.1309 | 0 | 0 | 2.1309 | 0 | 0 | 0 | 0 | 0 | 2.1309 | 48.2304 | 0 | 9000 | 9000 | 2926.2666 | 26.3364 | 584.4231 | 24.2055 | 536.1927 | 0 | 1610.1883 |  | 2037 | 1983.1546 | 2037 | 3.6% | 1983.1546 | 1558.1929 | 2048 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 2048 | 0 | 0
MP Complete | 2049 | 0 | 0 | 0.657 | 0 | 0 | 2.2161 | 0 | 0 | 2.2161 | 0 | 0 | 0 | 0 | 0 | 2.2161 | 50.4465 | 0 | 9000 | 9000 | 3031.6122 | 27.2845 | 611.7076 | 25.0684 | 561.2611 | 0 | 1641.1143 |  | 2038 | 2054.5482 | 2038 | 3.6% | 2054.5482 | 1614.2879 | 2049 | 0 | 2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2049 | 0 | 2049 | 0 | 0
MP Complete | 2050 | 0 | 0 | 0.657 | 0 | 0 | 2.3048 | 0 | 0 | 2.3048 | 0 | 0 | 0 | 0 | 0 | 2.3048 | 52.7513 | 0 | 9000 | 9000 | 3140.7502 | 28.2668 | 639.9744 | 25.962 | 587.223 | 0 | 1673.0001 |  | 2039 | 2128.5119 | 2039 | 3.6% | 2128.5119 | 1672.4022 | 2050 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 0 | 2050 | 0 | 0
MP Complete | 2051 | 0 | 0 | 0.657 | 0 | 0 | 2.397 | 0 | 0 | 2.397 | 0 | 0 | 0 | 0 | 0 | 2.397 | 55.1483 | 0 | 9000 | 9000 | 3253.8172 | 29.2844 | 669.2587 | 26.8874 | 614.1104 | 0 | 1705.8622 |  | 2040 | 2205.1384 | 2040 | 3.6% | 2205.1384 | 1732.6087 | 2051 | 0 | 2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2051 | 0 | 2051 | 0 | 0
MP Complete | 2052 | 0 | 0 | 0.657 | 0 | 0 | 2.4929 | 0 | 0 | 2.4929 | 0 | 0 | 0 | 0 | 0 | 2.4929 | 57.6412 | 0 | 9000 | 9000 | 3370.9546 | 30.3386 | 699.5973 | 27.8457 | 641.9561 | 0 | 1739.7185 |  | 2041 | 2284.5233 | 2041 | 3.6% | 2284.5233 | 1794.9826 | 2052 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 0 | 2052 | 0 | 0
MP Complete | 2053 | 0 | 0 | 0.657 | 0 | 0 | 2.5926 | 0 | 0 | 2.5926 | 0 | 0 | 0 | 0 | 0 | 2.5926 | 60.2338 | 0 | 9000 | 9000 | 3492.309 | 31.4308 | 731.0281 | 28.8382 | 670.7943 | 0 | 1774.5882 | 159.3486 | 2042 | 2366.7662 | 2042 | 3.6% | 2366.7662 | 1859.602 | 2053 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 2053 | 0 | 0
MP Complete | 2054 | 0 | 0 | 0.657 | 0 | 0 | 2.6963 | 0 | 0 | 2.6963 | 0 | 0 | 0 | 0 | 0 | 2.6963 | 62.93 | 0 | 9000 | 9000 | 3618.0321 | 32.5623 | 763.5904 | 29.866 | 700.6603 | 0 | 1810.4918 |  | 2043 | 2451.9698 | 2043 | 3.6% | 2451.9698 | 1926.5477 | 2054 | 0 | 2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0 | 2054 | 0 | 0
MP Complete | 2055 | 0 | 0 | 0.657 | 0 | 0 | 2.8041 | 0 | 0 | 2.8041 | 0 | 0 | 0 | 0 | 0 | 2.8041 | 65.7342 | 0 | 9000 | 9000 | 3748.2813 | 33.7345 | 797.3249 | 30.9304 | 731.5907 | 0 | 1847.4513 |  | 2044 | 2540.2407 | 2044 | 3.6% | 2540.2407 | 1995.9034 | 2055 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 2055 | 0 | 0
MP Complete | 2056 | 0 | 0 | 0.657 | 0 | 0 | 2.9163 | 0 | 0 | 2.9163 | 0 | 0 | 0 | 0 | 0 | 2.9163 | 68.6505 | 0 | 9000 | 9000 | 3883.2194 | 34.949 | 832.2739 | 32.0327 | 763.6234 | 0 | 1885.4899 |  | 2045 | 2631.6893 | 2045 | 3.6% | 2631.6893 | 2067.7559 | 2056 | 0 | 2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056 | 0 | 2056 | 0 | 0
MP Complete | 2057 | 0 | 0 | 0.657 | 0 | 0 | 3.033 | 0 | 0 | 3.033 | 0 | 0 | 0 | 0 | 0 | 3.033 | 71.6834 | 0 | 9000 | 9000 | 4023.0153 | 36.2071 | 868.481 | 33.1742 | 796.7976 | 0 | 1924.6319 |  | 2046 | 2726.4302 | 2046 | 3.6% | 2726.4302 | 2142.1951 | 2057 | 0 | 2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2057 | 0 | 2057 | 0 | 0
MP Complete | 2058 | 0 | 0 | 0.657 | 0 | 0 | 3.1543 | 0 | 0 | 3.1543 | 0 | 0 | 0 | 0 | 0 | 3.1543 | 74.8377 | 0 | 9000 | 9000 | 4167.8439 | 37.5106 | 905.9916 | 34.3563 | 831.1539 | 0 | 1964.9029 |  | 2047 | 2824.5816 | 2047 | 3.6% | 2824.5816 | 2219.3141 | 2058 | 0 | 2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2058 | 0 | 2058 | 0 | 0
MP Complete | 2059 | 0 | 0 | 0.657 | 0 | 0 | 3.2804 | 0 | 0 | 3.2804 | 0 | 0 | 0 | 0 | 0 | 3.2804 | 78.1181 | 0 | 9000 | 9000 | 4317.8863 | 38.861 | 944.8526 | 35.5805 | 866.7345 | 0 | 2006.3298 |  | 2048 | 2926.2666 | 2048 | 3.6% | 2926.2666 | 2299.2095 | 2059 | 0 | 2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2059 | 0 | 2059 | 0 | 0
MP Complete | 2060 | 0 | 0 | 0.657 | 0 | 0 | 3.4117 | 0 | 0 | 3.4117 | 0 | 0 | 0 | 0 | 0 | 3.4117 | 81.5298 | 0 | 9000 | 9000 | 4473.3302 | 40.26 | 985.1126 | 36.8483 | 903.5828 | 0 | 2048.9405 |  | 2049 | 3031.6122 | 2049 | 3.6% | 3031.6122 | 2381.981 | 2060 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 2060 | 0 | 0
[15 empty] | Total Cost (NPV) | 35.4038 |  |  |  |  | Total Revenue (NPV) | 395.8363 | IRR | 0% |  | $/AF at Life of Project (Year 2060) | 184.8748 |  | 2050 | 3140.7502 | 2050 | 3.6% | 3140.7502 | 2467.7323
1 - If LRP Subsidies are applicable, an Increase in supplies occuring after 2125 will require a modification to the current analysis. | [28 empty] | 2051 | 3253.8172 | 2051 | 3.6% | 3253.8172 | 2556.5707
[29 empty] | 2052 | 3370.9546 | 2052 | 3.6% | 3370.9546 | 2648.6072
[29 empty] | 2053 | 3492.309 | 2053 | 3.6% | 3492.309 | 2743.9571
[29 empty] | 2054 | 3618.0321 | 2054 | 3.6% | 3618.0321 | 2842.7395
[29 empty] | 2055 | 3748.2813 | 2055 | 3.6% | 3748.2813 | 2945.0782
[29 empty] | 2056 | 3883.2194 | 2056 | 3.6% | 3883.2194 | 3051.101
[29 empty] | 2057 | 4023.0153 | 2057 | 3.6% | 4023.0153 | 3160.9406
[29 empty] | 2058 | 4167.8439 | 2058 | 3.6% | 4167.8439 | 3274.7345
[29 empty] | 2059 | 4317.8863 | 2059 | 3.6% | 4317.8863 | 3392.6249
[29 empty] | 2060 | 4473.3302 | 2060 | 3.6% | 4473.3302 | 3514.7594
Note on F10: J. Almaraz: It is assumed that anything in $Year, or prior, are actual costs with no escalation required.
Note on L10: J. Almaraz: It is assumed that anything in $Year, or prior, will be treated as cash and not financed.
Note on AT10: J. Almaraz: Only Column with equivalent Borrowing term to Cell N4 is correct
Note on S12: Valenzuela, Jaime: Shut down 3 square miles to build. Saving approximately 5,000 AFY due to shut down of SF areas. Shutdown water added back to water demand when MP Complete.
Note on AM13: Jaime Almaraz: Rate Effective 1/2009 Rate Change on 9/1/2009 to 2010 Values
Note on AM19: Jaime Almaraz: Rates approved by the MWD board in April 2014 for 2015 and 2016.